## DMCT Schedule
DCC Public
SMETS1 DMCT Schedule v12.0 - 19/10/2021
DCC DMCT ID | HUB_TYPE | HUB_FIRMWARE | E_TYPE | E_FIRMWARE | G_TYPE | G_FIRMWARE | PPMID_MANUFACTURER | PPMID_TYPE | PPMID_FIRMWARE | PLANNED EPCL ENTRY | PLANNED TESTING START DATE | PLANNED TESTING COMPLETION DATE | PLANNED DATE FOR ADDITION TO EPCL | TEST PACK
IOC_004 | Elster AM110R | 3-07-09-P49-REV09 | Elster AS300P | 55497 | Elster BKG4 | 00-10-94 | Chameleon | IHD3-MS | 2.07.00 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_004 | Elster AM110R | 3-07-09-P49-REV09 | Elster AS300P | 55497 | Elster BKG4 | 00-10-94 | Chameleon | IHD3-MS | 2.07.00 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_005 | Itron EK410-UK | 00.03.00.33/53.37 | Itron EM425-UK | 03.00.03.46/53.17 | Itron G4 RF1 sV ZB | 012-00.292/10D6 | Chameleon | IHD2-TS | v1.17 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_005 | Itron EK410-UK | 00.03.00.33/53.37 | Itron EM425-UK | 03.00.03.46/53.17 | Itron G4 RF1 sV ZB | 012-00.292/10D6 | Chameleon | IHD2-TS | v1.17 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_007 | Elster AM110R | 3-07-09-P53-REV09 | Elster AS300P | 60250 | Elster BKG4 | 00-10-94 | STI | IHDL01 | S1-1v3 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_007 | Elster AM110R | 3-07-09-P53-REV09 | Elster AS300P | 60250 | Elster BKG4 | 00-10-94 | STI | IHDL01 | S1-1v3 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_008 | GE SGC1311 | 3-3-13 | GE SGM1311 | 3-3-6 | GE G4SZTV | 4-22-16-3-6-41 | STI | IHDL01 | S1-1v5 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_008 | GE SGC1311 | 3-3-13 | GE SGM1311 | 3-3-6 | GE G4SZTV | 4-22-16-3-6-41 | STI | IHDL01 | S1-1v5 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_009 | GE SGC1311 | 3-3-13 | GE SGM1311 | 3-3-6 | GE G4SZTV | 4-24-16-3-6-42 | Chameleon | IHD3-MS | 2.11.01 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_009 | GE SGC1311 | 3-3-13 | GE SGM1311 | 3-3-6 | GE G4SZTV | 4-24-16-3-6-42 | Chameleon | IHD3-MS | 2.11.01 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_010 | Elster AM110R | 3-07-09-P49-REV09 | Elster AS300P | 55497 | Elster BK-G4 V2 EI5.03 | 02-06-17 | Chameleon | IHD3-MS | 2.11.01 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_010 | Elster AM110R | 3-07-09-P49-REV09 | Elster AS300P | 55497 | Elster BK-G4 V2 EI5.03 | 02-06-17 | Chameleon | IHD3-MS | 2.11.01 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_011 | Elster AM110R | 3-07-09-P53-REV09 | Elster AS300P | 60250 | Elster BKG4 | 00-10-94 | STI | IHDL01 | S1-1v5M | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_011 | Elster AM110R | 3-07-09-P53-REV09 | Elster AS300P | 60250 | Elster BKG4 | 00-10-94 | STI | IHDL01 | S1-1v5M | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_012 | GE SGC1311 | 3-3-13 | GE SGM1312 | 3-3-6 | GE G4SZTV | 4-24-16-3-6-42 | Geo | Duet II | 1.3.1.9.15 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
IOC_012 | GE SGC1311 | 3-3-13 | GE SGM1312 | 3-3-6 | GE G4SZTV | 4-24-16-3-6-42 | Geo | Duet II | 1.3.1.9.15 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
MDS_008 | AM110R | 3.07.09 (49)-REV09 | AS300P | ASP04.04.01-55497 | BK-G4 V2 EI2 | 00.10.94 | Chameleon Technology | SED V3 | 2.05.00 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
MDS_008 | AM110R | 3.07.09 (49)-REV09 | AS300P | ASP04.04.01-55497 | BK-G4 V2 EI2 | 00.10.94 | Chameleon Technology | SED V3 | 2.05.00 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
MDS_015 | AM110R | 3.07.09 (49) | AS300P | ASP04.04.01-55497 | BK-G4 V2 EI2 | 00.10.94 | Chameleon Technology | SED V3 | 2.08.01 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
MDS_015 | AM110R | 3.07.09 (49) | AS300P | ASP04.04.01-55497 | BK-G4 V2 EI2 | 00.10.94 | Chameleon Technology | SED V3 | 2.08.01 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
MDS_053 | AM110R | 3.07.09 (67) | AS300P | ASP04.04.01-55497 | BK-G4 V2 EI2 | 00.10.94 | Chameleon Technology | SED V3 | 2.08.01 | Active only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
MDS_053 | AM110R | 3.07.09 (67) | AS300P | ASP04.04.01-55497 | BK-G4 V2 EI2 | 00.10.94 | Chameleon Technology | SED V3 | 2.08.01 | Dormant only | Complete | Complete | On EPCL | Standard DMCT MT Test Pack & Standard DMCT SRVT Test Pack
Notes
1 | Column A (DCC DMCT ID) is a DCC internal ID and bears no relationship to either PPCL or EPCL Indexes
2 | All Substantive Equivalence entries have been removed from the DMCT Schedule