## Work Packages
MODIFICATION
Mod | Title | Priority | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
MP200 | Facilitating the CSS | High | bar: 2022-05-23
MP109 | ADT and Exit Quarantine file delivery mechanism | Medium | 2022-05-23: Vote (subject to SSI changes); 2022-06-06: SG
MP129 | Allowing the use of CNSA variant for ECDSA | Low | 2022-05-23: Vote; 2022-06-06: SG
MP193 | IRP Batch 6 | Low | 2022-05-23: Vote; 2022-06-06: SG
MP128A | Gas Network Operators SMKI Requirements | High | 2022-06-06: MRC; 2022-06-20: Vote; 2022-07-04: SG
MP125 | Correcting Device Information ESME Variant | Medium | 2022-06-20: Opine; 2022-07-11: MRC; 2022-07-25: Vote; 2022-08-08: SG
MP160 | Certificate Signing Request Forecasting | Low | 2022-05-30: RC; 2022-06-20: Opine; 2022-07-11: MRC; 2022-07-25: Vote; 2022-08-08: SG
DP204 | IRP Batch 8 (Category 3) | Medium | 2022-06-20: Opine; 2022-07-11: MRC; 2022-07-25: Vote; 2022-08-08: SG
MP096 | DNO Power Outage Alert | High | 2022-06-20: Opine; 2022-07-11: MRC; 2022-07-25: Vote; 2022-08-29: AD
MP162 | SEC changes required to deliver MHHS | Very High | 2022-05-30: WG; 2022-06-20: Opine; 2022-07-11: MRC; 2022-07-25: Vote; 2022-08-29: AD
MP186 | Section D Review (2020): further enhancements | Medium | 2022-05-30: RC; 2022-06-20: Opine; 2022-07-11: MRC; 2022-07-25: Vote; 2022-08-29: AD
MP170 | Firmware updates to Point to Point Alt HAN Devices | High | 2022-07-04: WG; 2022-07-18: Opine; 2022-08-08: MRC; 2022-08-22: Vote; 2022-09-05: SG
MP102B | Power Outage Alerts triggered by an OTA firmware upgrade - enduring solution | Medium | 2022-05-23: IA; 2022-07-04: WG; 2022-07-18: Opine; 2022-08-08: MRC; 2022-08-22: Vote; 2022-09-05: SG
MP187 | Compliance with OPR/reporting on TRTs | High | 2022-05-30: WG; 2022-06-27: RC; 2022-07-18: Opine; 2022-08-08: MRC; 2022-08-22: Vote; 2022-09-05: SG
MP176 | Customer Analytics Reporting | Medium | 2022-06-06: IA; 2022-07-04: WG; 2022-07-18: Opine; 2022-08-08: MRC; 2022-08-22: Vote; 2022-09-05: SG
MP181 | Meter Asset Provider access to asset related data held by the DCC | Medium | 2022-07-04: WG; 2022-07-18: Opine; 2022-08-08: MRC; 2022-08-22: Vote; 2022-09-05: SG
MP167 | Housekeeping Section T & Section X | Medium | 2022-05-30: WG; 2022-06-27: RC; 2022-07-18: Opine; 2022-08-08: MRC; 2022-08-22: Vote; 2022-09-26: AD
MP122B | Operational Metrics - Part 2 | Very High | 2022-06-20: IA; 2022-07-04: WG; 2022-07-25: RC; 2022-08-15: Opine; 2022-09-05: MRC; 2022-09-19: Vote; 2022-10-03: SG
MP183 | Post Commissioning Obligations Reporting | Low | 2022-05-30: WG; 2022-06-27: RC; 2022-08-01: WG; 2022-08-15: Opine; 2022-09-05: MRC; 2022-09-19: Vote; 2022-10-03: SG
DP198 | Further Changes from the Review of the SMKI and DCCKI Document Set | Medium | 2022-07-04: WG; 2022-08-15: Opine; 2022-09-05: MRC; 2022-09-19: Vote; 2022-10-03: SG
MP134B | Use of SMKI Certificates in a SoLR event Part B | High | 2022-06-20: IAR; 2022-08-15: IA; 2022-09-05: WG; 2022-09-19: Opine; 2022-10-10: MRC; 2022-10-24: Vote; 2022-11-07: SG
DP203 | Security Assurance of Device Triage Facilities | High | 2022-07-04: WG; 2022-07-25: RC; 2022-09-05: WG; 2022-09-19: Opine; 2022-10-10: MRC; 2022-10-24: Vote; 2022-11-07: SG
MP172 | Reduced CPA & CPL requirements for innovation and Device field trials | Medium | 2022-05-23: PA; 2022-06-20: Update due
MP113 | Unintended Data Disclosure when using SR8.2 | Medium | 2022-06-20: Update due
MP137 | Sharing Information on Defects and Issues | Medium | 2022-06-13: PA; 2022-06-20: Update due
SECMP0028 | Prioritising Service Requests | Low | 2022-06-13: PA; 2022-06-20: Update due
MP155 | Communications Hub Re-Flash | Low | 2022-05-30: WG; 2022-06-13: RC; 2022-06-20: Update due
MP094 | Supporting prepayment customers in no SM WAN scenarios | Low | 2022-06-20: Update due
DP197 | Reallocating Third Party Communications Hubs in the Event of a SoLR | High | 2022-06-20: Refine
DP189 | Party Obligations for Communications Hub Orders | Low | 2022-06-20: Refine
MP168 | CPL Security Improvements | Medium | 2022-06-06: PA; 2022-07-04: WG; 2022-07-18: Update due
MP184 | Increased Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage usecases | Medium | 2022-05-30: WG; 2022-07-04: PA; 2022-07-18: Update due
SECMP0010 | Triage arrangements for Comms Hubs | Low | 2022-07-04: WG; 2022-07-18: Update due
MP152 | Consumption on Smart Polyphase Electricity Meters | Medium | 2022-07-04: WG; 2022-07-18: Update due
MP202 | Enduring Solution for SMETS1 and SMETS2+ PPMIDs | Low | 2022-05-30: RWS; 2022-07-18: Update due
DP190 | Standard Event and Alerts Screens for SMETS2 Meters | Low | 2022-07-18: Refine
MP082 | 2.4GHz Channel Management | Low | 2022-07-04: WG; 2022-07-25: PA; 2022-08-01: WG; 2022-08-15: Update due
MP169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | High | 2022-08-15: Update due
MP085B | Synchronisation of smart meter voltage measurement periods | Low | 2022-05-30: WG/TA; 2022-06-27: RC; 2022-08-01: WG; 2022-08-15: Update due
MP165 | ESME Voltage Accuracy | Low | 2022-05-30: WG; 2022-06-27: RC; 2022-08-01: WG; 2022-08-15: Update due
MP178 | Removing DSP validation against the SMI join status for SR8.8.x | Low | 2022-07-11: RWS; 2022-08-15: Update due
DP205 | Updating terminology to align with the NCSC | Low | 2022-07-18: Waiting list
DP206 | Generation Licence for Export Supply | Medium | 2022-07-18: Waiting list
DP207 | RSA firmware updates | Medium | 2022-07-18: Waiting list
SECMP0032 | Prioritising Prepayment Customers in No WAN Situations | Low | 2022-07-18: Hold
SECMP0037 | Pairing Local PPMIDs | Low | 2022-07-18: Hold
SECMP0038 | Sending Commands via PPMIDs | Low | 2022-07-18: Hold
SECMP0046 | Electricity Network Operators to control HCALCS for electric vehicle chargers | High | 2022-07-18: Hold
MP166 | Adverse Weather Planned Maintenance process | Low | 2022-07-18: Hold

## Key
Change Sub-Committee | Refine | DP presented for progression to Refine Stage
| Opine | DP/MP presented for progression to Opine Stage
Change Board | IAR | IA Request
| Vote | Change Board vote
Working Group | WG | Working Group meeting
Requirements Workshop | RWS | Requirements Workshop session
DCC Assessments | PA | Preliminary Assessment
| IA | Impact Assessment
Consultations | RFI | Request for Information
| RC | Refinement Consultation
| MRC | Modification Report Consultation
Decision | AD | Authority Decision
| SG | Self-Governance referral period
On hold | Hold | On hold