## Work Packages
MODIFICATION |  |  | Key activity in week commencing…
Mod | Title | Priority | 2022-06-13 | 2022-06-20 | 2022-06-27 | 2022-07-04 | 2022-07-11 | 2022-07-18 | 2022-07-25 | 2022-08-01 | 2022-08-08 | 2022-08-15 | 2022-08-22 | 2022-08-29 | 2022-09-05 | 2022-09-12 | 2022-09-19 | 2022-09-26 | 2022-10-03 | 2022-10-10 | 2022-10-17 | 2022-10-24 | 2022-10-31 | 2022-11-07 | 2022-11-14 | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16
SECMP0032 | Prioritising Prepayment Customers in No WAN Situations | Low | WD
SECMP0037 | Pairing Local PPMIDs | Low | WD
SECMP0038 | Sending Commands via PPMIDs | Low | WD
MP109 | ADT and Exit Quarantine file delivery mechanism | Medium |  | Opine and Vote (subject to SSI changes) |  | SG
MP129 | Allowing the use of CNSA variant for ECDSA | Low | [6 empty] | Vote |  | SG
MP128A | Gas Network Operators SMKI Requirements | High |  | Opine |  |  | MRC |  | Vote |  | SG
MP160 | Certificate Signing Request Forecasting | Low |  | Opine |  |  | MRC |  | Vote |  | SG
DP204 | IRP Batch 8 (Category 3) | Medium |  | Opine |  |  | MRC |  | Vote |  | SG
MP181 | Meter Asset Provider access to asset related data held by the DCC | Medium |  | Opine |  |  | MRC |  | Vote |  | SG
DP209 | CPA re-certification arrangements | Very High |  | Opine |  |  | MRC |  | Vote |  | SG
MP096 | DNO Power Outage Alert | High |  | Opine |  |  | MRC |  | Vote |  |  |  |  | AD
MP162 | SEC changes required to deliver MHHS | Very High |  | Opine |  |  | MRC |  | Vote |  |  |  |  | AD
MP186 | Section D Review (2020): further enhancements | Medium |  | Opine |  |  | MRC |  | Vote |  |  |  |  | AD
MP125 | Correcting Device Information ESME Variant | Medium |  |  |  | WG |  | Opine |  |  | MRC |  | Vote |  | SG
MP170 | Firmware updates to Point to Point Alt HAN Devices | High |  |  |  | WG |  | Opine |  |  | MRC |  | Vote |  | SG
MP102B | Power Outage Alerts triggered by an OTA firmware upgrade - enduring solution | Medium |  |  |  | WG |  | Opine |  |  | MRC |  | Vote |  | SG
MP176 | Customer Analytics Reporting | Medium |  | IA |  | WG |  | Opine |  |  | MRC |  | Vote |  | SG
MP187 | Compliance with OPR/reporting on TRTs | High |  |  |  | WG |  |  |  | RC |  | Opine |  |  | MRC |  | Vote |  | SG
MP122B | Operational Metrics - Part 2 | Very High |  | IA |  | WG |  |  | RC |  |  | Opine |  |  | MRC |  | Vote |  | SG
MP167 | Housekeeping Section T & Section X | Medium |  |  |  | WG |  |  | RC |  |  | Opine |  |  | MRC |  | Vote |  |  |  |  | AD
DP198 | Further Changes from the Review of the SMKI and DCCKI Document Set | Medium |  |  |  | WG | [6 empty] | RC |  |  |  | Opine |  |  | MRC |  | Vote |  | SG
DP203 | Security Assurance of Device Triage Facilities | High |  |  |  | WG |  |  | RC | [5 empty] | WG |  | Opine |  |  | MRC |  | Vote |  | SG
MP134B | Use of SMKI Certificates in a SoLR event Part B | High | [5 empty] | IAR | [7 empty] | IA |  |  | WG |  | Opine |  |  | MRC |  | Vote |  | SG
MP183 | Post Commissioning Obligations Reporting | Low | [7 empty] | WG |  |  |  | RC |  |  |  |  | WG |  | Opine |  |  | MRC |  | Vote |  | SG
MP155 | Communications Hub Re-Flash | Low |  | Update due | [5 empty] | WG |  |  |  | RC |  |  |  |  | WG |  |  | IAR | [8 empty] | IA |  |  | Opine
MP172 | Reduced CPA & CPL requirements for innovation and Device field trials | Medium |  | Update due |  | WG |  |  | RC | [5 empty] | WG |  | IAR | [7 empty] | Update due | IA
MP113 | Unintended Data Disclosure when using SR8.2 | Medium |  | Update due |  |  |  | Update due
DP197 | Reallocating Third Party Communications Hubs in the Event of a SoLR | High |  | Checking with legal team |  |  |  | Update due
SECMP0028 | Prioritising Service Requests | Low |  |  |  |  | PA | Update due
MP168 | CPL Security Improvements | Medium |  | PA |  | WG |  | Update due
MP184 | Increased Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage usecases | Medium |  |  |  | WG |  | Update due
SECMP0010 | Triage arrangements for Comms Hubs | Low |  |  | Work on Use Case by SSC |  |  | Update due
MP202 | Enduring Solution for SMETS1 and SMETS2+ PPMIDs | Low |  | RWS |  |  |  | Update due
MP082 | 2.4GHz Channel Management | Low | [6 empty] | PA | WG |  | Update due
MP169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | High | RWS | [8 empty] | Update due
MP085B | Synchronisation of smart meter voltage measurement periods | Low |  |  | RC |  |  |  |  | WG |  | Update due
MP165 | ESME Voltage Accuracy | Low |  |  | RC |  |  |  |  | WG |  | Update due
MP178 | Removing DSP validation against the SMI join status for SR8.8.x | Low |  |  |  |  | RWS |  |  |  |  | Update due
DP207 | RSA firmware updates | Medium |  |  | RWS | [6 empty] | Refine
MP137 | Sharing Information on Defects and Issues | Medium | PA | Update due | [5 empty] | WG |  |  |  | RC |  |  | Update due
MP094 | Supporting prepayment customers in no SM WAN scenarios | Low |  | Update due | [12 empty] | Update due
DP189 | Party Obligations for Communications Hub Orders | Low |  | Refine | [5 empty] | WG |  |  | RC |  | WG |  | Update due
DP208 | Prioritisation of Northbound Alerts | High |  | Refine | [5 empty] | WG |  |  | PA |  | WG |  |  | RC |  |  | Update due
MP152 | Consumption on Smart Polyphase Electricity Meters | Medium | [7 empty] | WG |  |  |  |  | PA |  |  |  | WG |  | Update due
DP190 | Standard Event and Alerts Screens for SMETS2 Meters | Low | [5 empty] | Waiting list
DP205 | Updating terminology to align with the NCSC | Low | [5 empty] | Waiting list
DP206 | Generation Licence for Export Supply | Medium | [5 empty] | Waiting list
SECMP0046 | Electricity Network Operators to control HCALCS for electric vehicle chargers | High | [5 empty] | Hold
MP166 | Adverse Weather Planned Maintenance process | Low | [5 empty] | Hold

## Key
Change Sub-Committee | Refine | DP presented for progression to Refine Stage
| Opine | DP/MP presented for progression to Opine Stage
Change Board | IAR | IA Request
| Vote | Change Board vote
Working Group | WG | Working Group meeting
Requirements Workshop | RWS | Requirements Workshop session
DCC Assessments | PA | Preliminary Assessment
| IA | Impact Assessment
Consultations | RFI | Request for Information
| RC | Refinement Consultation
| MRC | Modification Report Consultation
Decision | AD | Authority Decision
| SG | Self-Governance referral period
| WD | Withdrawal adoption period
Progression paused | Hold | On hold
| Waiting | On the waiting list