## Work Packages
MODIFICATION |  | MILESTONE IN WEEK COMMENCING…
Mod | Title | Priority | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31
MP186 | Section D Review (2020): further enhancements | Medium | bar: 2022-11-28 to 2022-12-12
MP210 | RSA forecasts, orders and pay stock charges for Alt HAN Equipment | Medium | 2022-12-05: MRC; 2022-12-19: Vote; 2023-01-02: SG
MP167A | Review of SEC documents (Testing Approach Document criteria) | Medium | 2022-12-05: MRC; 2022-12-19: Vote; 2023-01-02: SG
MP172 | Reduced CPA & CPL requirements for innovation and Device field trials | Medium | 2022-12-05: MRC; 2022-12-19: Vote; 2023-01-02: SG
DP220 | MMC Changes resulting from GBCS v4.1 Device Testing | High | 2022-12-19: Opine; 2023-01-09: MRC; 2023-01-23: Vote; 2023-02-06: SG
DP221 | CHTS v1.0 and GBCS v1.1 Applicability End Date and Maintenance End Date | Very High | 2022-11-28: RC; 2022-12-05: WG; 2022-12-19: Opine; 2023-01-09: MRC; 2023-01-23: Vote; 2023-02-06: SG
MP198 | Further Changes from the Review of the SMKI and DCCKI Document Set | Medium | 2022-11-28: RC; 2022-12-19: Opine; 2023-01-09: MRC; 2023-01-23: Vote; 2023-02-06: SG
MP183 | Post Commissioning Obligations Reporting | Low | 2022-11-28: RC; 2022-12-19: Opine; 2023-01-09: MRC; 2023-01-23: Vote; 2023-02-06: SG
MP216 | IRPs Batch 9 - Category 2 | Medium | 2022-12-05: WG; 2023-01-02: TABASC; 2023-01-16: Opine; 2023-02-06: MRC; 2023-02-20: Vote; 2023-03-06: SG
MP215 | Communications Hub Forecasting and Ordering | Medium | 2022-12-05: WG; 2022-12-12: OPSG; 2023-01-09: PA; 2023-01-16: Opine; 2023-01-30: WG; 2023-02-06: MRC; 2023-02-20: Vote; 2023-03-06: SG
MP211 | Aligning the SMI with the CPL | Low | 2022-12-19: IAR; 2023-02-13: IA; 2023-03-06: WG; 2023-03-20: Opine; 2023-04-10: MRC; 2023-04-24: Vote; 2023-05-08: SG
MP178 | Removing DSP validation against the SMI join status for SR8.8.x | Low | 2022-12-19: IAR; 2023-02-20: IA; 2023-03-06: WG; 2023-03-20: Opine; 2023-04-10: MRC; 2023-04-24: Vote; 2023-05-08: SG
SECMP0028 | Prioritising Service Requests | Low | 2023-01-30: WG; 2023-02-13: IAR; 2023-03-20: IA; 2023-05-01: WG; 2023-05-15: Opine; 2023-06-05: MRC; 2023-06-19: Vote; 2023-07-03: SG
MP137 | Sharing Information on Defects and Issues | Medium | 2022-12-26: RC; 2023-01-23: IAR; 2023-03-20: IA; 2023-05-01: WG; 2023-05-15: Opine; 2023-06-05: MRC; 2023-06-19: Vote; 2023-07-03: SG
MP168 | CPL Security Improvements | Medium | 2023-01-23: PA; 2023-02-20: Update due
MP208 | Northbound prioritisation of N56 Alerts | High | 2022-12-12: PA; 2022-12-19: Update due
MP184 | Increased Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage usecases | Medium | 2022-12-05: PA; 2022-12-19: Update due; 2023-02-27: TABASC
MP169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | High | 2022-12-05: WG; 2022-12-19: Update due; 2023-01-30: WG; 2023-02-27: RC
DP217 | Obtaining Timestamps to allow Target Response Time Measurements | High | 2022-11-28: TABASC; 2022-12-05: WG; 2022-12-19: Update due
MP085B | Synchronisation of smart meter voltage measurement periods | Low | 2022-12-19: Update due
MP165 | ESME Voltage Accuracy | Low | 2022-12-19: Update due
DP218 | Review of SEC Charging Methodology | Medium | 2023-01-02: RFI; 2023-01-16: Update due
MP094 | Supporting prepayment customers in no SM WAN scenarios | Low | 2023-01-16: Update due
MP207 | RSA firmware updates | Medium | 2022-11-28: PA; 2023-01-02: WG/TA; 2023-01-23: RC; 2023-01-30: WG; 2023-02-20: Update due
MP202 | Enduring Solution for SMETS1 and SMETS2+ PPMIDs | Low | 2022-12-05: WG/TA; 2022-12-26: RC; 2023-01-30: WG; 2023-02-20: Update due
DP219 | Accessing Consumption Data on behalf of SEC Parties | High | 2022-12-19: Refine; 2023-01-16: RC
DP222 | CPL submission efficiency improvements | High | 2022-12-19: Refine; 2023-01-30: WG; 2023-02-20: SSC
DP223 | WAN coverage reporting | Medium | 2022-12-19: New DP; 2023-01-16: Refine; 2023-02-06: RC
MP205 | Updating terminology to align with the NCSC | Low | 2023-01-02: Waiting list
DP214 | Clarification of Acceptable DCC User IDs for Import and Export Suppliers | Low | 2023-01-02: Waiting list
DP206 | Generation Licence for Export Supply | Medium | 2022-12-05: Hold
MP187 | Compliance with OPR/reporting on TRTs | High | 2022-12-05: Hold
SECMP0010 | Triage arrangements for Comms Hubs | Low | 2022-12-05: Hold
SECMP0046 | Electricity Network Operators to control HCALCS for electric vehicle chargers | High | 2022-12-05: Hold
MP166 | Adverse Weather Planned Maintenance process | Low | 2022-12-05: Hold
DP197 | Reallocating Third Party Communications Hubs in the Event of a SoLR | High | 2022-12-05: Hold
MP176 | Customer Analytics Reporting | Medium | 2022-12-05: Hold

## Key
Change Sub-Committee | Refine | DP presented for progression to Refine Stage
| Opine | DP/MP presented for progression to Opine Stage
Change Board | IAR | IA Request
| Vote | Change Board vote
Working Group | WG | Working Group meeting
Requirements Workshop | RWS | Requirements Workshop session
DCC Assessments | PA | Preliminary Assessment
| IA | Impact Assessment
Consultations | RFI | Request for Information
| RC | Refinement Consultation
| MRC | Modification Report Consultation
Decision | AD | Authority Decision
| SG | Self-Governance referral period
On hold | Hold | On hold