## Overview (hidden)
Row Labels | Count of Process Stage
Awaiting Implementation | 5
Consultation | 3
Final Assessment | 2
Initial Assessment | 11
Preliminary Assessment | 5
REC Party Impact Assessment | 1
Service Provider Impact Assessment | 1
Solution Development | 8
(blank)
Grand Total | 36

## Portfolio View
PRIORITY | DEVELOPMENT STAGE | REFINEMENT PROCESS | MRC | CHANGE BOARD VOTE | AWAITING AUTHORITY DETERMINATION
VERY HIGH
HIGH
MEDIUM
LOW
TOTAL | 6 | 24 | 2 | 2 | 0
KEY
- PURPLE MARKS ON HOLD MODIFICATIONS
- BLUE MARKS ACTIVE MODIFICATIONS
SECMP0010
MP085B
SECMP0028
SECMP0046
MP094
MP137
MP165
MP166
MP167B
MP168
MP169
MP176
MP178
MP184
MP187
DP197
MP198
MP202
DP206
MP207
MP208
MP211
MP214
MP215
MP216
MP217
DP218
MP219
MP222
MP223
DP224
DP226
DP227
DP228
DP229
DP230
DP231
DP232
DP233
DP234
DP235

## Prioritisation Matrix
Prioritisation Matrix
URGENCY
3 |  | P215 | P197 | P208
|  | P218 | P211 | P221
P227
2 |  | P172 | P167A | P0046
|  | P210 | P167B | P094
|  |  | P217 | P187
P223
P231
1 | P202 | P165 | P137 | P169
| P229 | P216 | P168 | P219
|  | P226 | P184 | P222
|  | P232 | P198 | P224
P206
P207
P228
P230
0 | P166 | P0010 | P176
| P178 | P0028
| P205 | P085B
| P214 | P233
P234
P235
| 0 | 1 | 2 | 3 | VALUE

## Prioritisation Scoring
Prioritisation scoring
Mod | Title | L | O | B | C | S | V | U | Priority | Key
SECMP0010 | Introduction of triage arrangements for Communication Hubs | 0 | 1 | 2 | 1 | 0 | 1 | 0 | Low | L | Legal & regulatory compliance
SECMP0028 | Prioritising Over The Air Messages | 1 | 2 | 1 | 0 | 0 | 1 | 0 | Low | O | Operational performance
SECMP0046 | Allow DNOs to control Electric Vehicle chargers connected to Smart Meter infrastructure | 1 | 3 | 3 | 3 | 0 | 3 | 2 | High | B | Cost benefits
MP085B | Synchronisation of smart meter voltage measurement periods (meters currently installed) | 1 | 2 | 1 | 1 | 0 | 1 | 0 | Low | C | Consumer impacts
MP094 | Supporting prepayment customers in no SM WAN scenarios | 2 | 2 | 0 | 2 | 1 | 3 | 2 | High | S | Security impacts
MP137 | Sharing Information on Defects and Issues | 1 | 2 | 2 | 2 | 1 | 2 | 1 | Medium
MP165 | ESME Voltage Accuracy | 0 | 2 | 2 | 1 | 0 | 1 | 1 | Medium
MP166 | Adverse Weather Planned Maintenance process | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Low
MP167A | Review of SEC documents (Testing Approach Document criteria) | 3 | 0 | 1 | 0 | 0 | 2 | 2 | High
MP167B | Review of SEC documents (DCC Internal Systems change governance) | 3 | 0 | 1 | 0 | 0 | 2 | 2 | High
MP168 | CPL Security Improvements | 2 | 0 | 0 | 1 | 2 | 2 | 1 | Medium
MP169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | 3 | 2 | 0 | 2 | 1 | 3 | 1 | High
MP172 | Reduced CPA & CPL requirements for innovation and Device field trials | 0 | 0 | 1 | 1 | 2 | 1 | 2 | Medium
MP176 | Customer Analytics Reporting | 1 | 2 | 1 | 2 | 0 | 2 | 0 | Medium
MP178 | Removing DSP validation against the SMI join status for SR8.8.x | 0 | 1 | 0 | 0 | 0 | 0 | 0 | Low
MP184 | Increase Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage use cases | 1 | 1 | 2 | 2 | 1 | 2 | 1 | Medium
MP187 | Incorporation of Target Round Trip Times and Target Success Rates into the SEC | 3 | 3 | 2 | 2 | 0 | 3 | 2 | High
DP197 | Reallocating Third Party Communications Hubs in the Event of a SoLR | 1 | 2 | 3 | 1 | 0 | 2 | 3 | High
MP198 | Further Changes from the Review of the SMKI and DCCKI Document Set | 2 | 0 | 0 | 0 | 2 | 2 | 1 | Medium
MP202 | Enduring Solution for SMETS1 and SMETS2+ PPMIDs | 0 | 1 | 1 | 1 | 0 | 0 | 0 | Low
MP205 | Updating terminology to align with the NCSC | 2 | 0 | 0 | 0 | 0 | 1 | 0 | Low
DP206 | Allowing Generation Licence Holders to Apply Export MPANs | 2 | 2 | 1 | 2 | 0 | 2 | 1 | Medium
MP207 | Allowing Registered Supplier Agents to Maintain Meter Firmware | 2 | 3 | 1 | 2 | 0 | 2 | 1 | Medium
MP208 | Northbound Prioritisation of N56 Alerts | 1 | 2 | 1 | 3 | 0 | 2 | 2 | High
MP210 | RSA forecasts, orders and pay stock charges for Alt HAN Equipment | 1 | 2 | 0 | 2 | 0 | 1 | 2 | Medium
MP211 | Aligning the SMI with the CPL | 0 | 0 | 0 | 0 | 3 | 1 | 2 | Medium
MP214 | Clarification of Acceptable DCC User IDs for Import and Export Suppliers | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Low
MP215 | Communications Hub Ordering and Forecasting | 1 | 2 | 1 | 1 | 0 | 1 | 1 | Medium
MP216 | Incorporation of Category 2 Issue Resolution Proposals into the SEC – Batch 9 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | Medium
MP217 | Obtaining Timestamps to allow Target Response Time Measurements | 2 | 2 | 1 | 1 | 0 | 2 | 2 | High
DP218 | Review of the SEC Charging Methodology | 1 | 2 | 2 | 0 | 0 | 1 | 3 | High
MP219 | Accessing consumption data on behalf of SEC Parties | 2 | 2 | 1 | 0 | 2 | 3 | 1 | High
MP222 | CPL Supplier endorsement | 1 | 2 | 1 | 2 | 2 | 1 | 3 | High
MP223 | No WAN reporting | 2 | 2 | 2 | 1 | 0 | 2 | 2 | High
DP224 | PAF | 3 | 2 | 0 | 2 | 0 | 1 | 3 | High
DP226 | IRP Cat 3 Batch 10 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | Medium
DP227 | SMETS pre v4.2 extension | 2 | 1 | 2 | 1 | 0 | 3 | 2 | High
DP228 | Other User Demand Forecasting | 0 | 3 | 1 | 3 | 0 | 1 | 2 | Medium
DP229 | De-commissioning of User Systems | 0 | 0 | 0 | 0 | 1 | 1 | 0 | Low
DP230 | Aclara SMETS1 ESME Firmware Delivery SLA | 1 | 2 | 0 | 1 | 2 | 1 | 2 | Medium
DP231 | Firmware upgrade pathways | 0 | 2 | 1 | 2 | 2 | 2 | 2 | High
DP232 | ACB certs on I&C | 0 | 2 | 0 | 1 | 1 | 1 | 1 | Medium
DP233 | Review of Appendix AG Incident categorisation | 0 | 2 | 1 | 2 | 0 | 0 | 1 | Low
DP234 | Addition of GDPR Principles of Public Task and Legitimate Interest into the SEC | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
DP235 | Enhanced Meter Data Access for Other Users | 0 | 0 | 0 | 2 | 0 | 0 | 0 | Low

## On Hold
Modifications on hold
Mod | Title | Criteria to come off hold
SECMP0010 | Introduction of triage arrangements for Communication Hubs | Until a new Use Case 005 has been developed and agreed by the SSC and the NCSC.
SECMP0046 | Allow DNOs to control Electric Vehicle chargers connected to Smart Meter infrastructure | The Energy Systems Catapult (ESG) working group has completed its assessment of the wider solution for managing electric vehicle and determined whether the SECMP0046 solution is the appropriate way forward.
MP166 | Adverse Weather Planned Maintenance process | The DCC has completed its challenge of the Service Providers’ costs provided through the Preliminary Assessment.
MP187 | Incorporation of Target Round Trip Times and Target Success Rates into the SEC | DP217 has introduced mechanism to measure RTTs.
DP197 | Reallocating Third Party Communications Hubs in the Event of a SoLR | The Proposer has provided confirmation on whether and how they wish to proceed with this modification.
DP206 | Allowing Generation Licence Holders to Apply Export MPANs | BSC changes suitably developed to inform SEC changes.

## Waiting List
Modifications on waiting list
Mod | Title | Criteria to come off waiting list
MP205 | Updating terminology to align with the NCSC | SECAS have availability to work on this as it is a lower priority modification.

## CP priority heatmap (hidden)
Urgency | 3
2
1
0
|  | 0 | 1 | 2 | 3
Significance
| R06 | R0006 - Missing Meter Technical Details
| R09 | R0009 - Introduction of SDEP and EES User Maintenance API
| R10 | R0010 - New Meter Types for Auxiliary Proportional Controllers (APCs)
| R15 | R0015 - Remote communication obligations for Advanced Meters
| R16 | R0016 - Resolution of Bilateral Erroneous Transfers
| R17 | R0017 - Invalid Requests for Site Technical Details
| R21 | R0021 - Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier
| R22 | R0022 - Amendment to REC Data Access Matrix
| R24 | R0024 - EAC information in the EES API
| R25 | R0025 - Service Provider Performance Charges (ERDS, GRDS, DCC)
| R26 | R0026 - Whole current (WC)/Current Transformer (CT) certificates
| R30 | R0030 - Erroneous Transfer Cancellations
| R32 | R0032 - New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS)
| R36 | R0036 - Housekeeping amendments
| R37 | R0037 - Housekeeping amendments - Prepayment Credit Balance & Debt Transfer Processes
| R40 | R0040 - CSS Switch Synchronisation to ERDA at SecuredActive |  |  |  | Awaiting Initial Assessment
| R43 | R0043 - Commissioning of Works using shared Meter Operator services by the Crowded Meter Room Co-ordinator (CMRC) |  |  |  | Awaiting Initial Assessment
| R44 | R0044 - MHHS Programme Changes required to Central Switching Service
| R45 | R0045 - Changes to SDEP Messages for REC V3.0
| R47 | R0047 - Metering Code of Practice Consolidation Review
| R48 | R0048 - DCC Service Organisation Control 2 (SOC2) Assessments |  |  |  | Awaiting Initial Assessment
| R49 | R0049 - Intellectual Property Rights and Services Data Main Body changes |  |  |  | Awaiting Initial Assessment
| R50 | R0050 - Clarification of REC Maintenance of Qualification Schedule |  |  |  | Awaiting Initial Assessment
| R51 | R0051 - Switch Request Objections (Change of Occupier) |  |  |  | Awaiting Initial Assessment
| R52 | R0052 - GES Service Definition Document
| R53 | R0053 - 24/7 Emergency Metering Service |  |  |  | Awaiting Initial Assessment
| R54 | R0054 - EES Access for Virtual Lead Parties
| R55 | R0055 - Switching Operator Outage Notification Lead Time
| R56 | R0056 - EES/GES Additional Service Request for Housing Associations to be added to the Data Access Matrix |  |  |  | Awaiting Initial Assessment
| R57 | R0057 - Clarification of Supplier of Last Resort Obligations under the REC |  |  |  | Awaiting Initial Assessment
| R58 | R0058 - REC Services Procurement Clarification |  |  |  | Awaiting Initial Assessment
| R59 | R0059 - Maintenance of Qualification Schedule Change |  |  |  | Awaiting Initial Assessment
| R60 | R0060 - ERDS Service Definition timezone correction |  |  |  | Awaiting Initial Assessment
| R61 | R0061 - Resolution of invalid CSS data by Data Owners |  |  |  | Awaiting Initial Assessment
| R62 | R0062 - Removal of ERDA meteringPointEnergyFlow change restriction |  |  |  | Awaiting Initial Assessment
| R63 | R0063 - Addition of key information to all Service Now tickets |  |  |  | Awaiting Initial Assessment
| R64 | R0064 - Creating a Meter Operator Agent and MOCoP Installer |  |  |  | Awaiting Initial Assessment
| R65 | R0065 - Registration of Smart Export Guarantee (SEG) Sites |  |  |  | Awaiting Initial Assessment
| R66 | R0066 - Inclusion of new DNO mastered SMRS Data Items in the EES. |  |  |  | Awaiting Initial Assessment
| R67 | R0067 - Introduction of CSS refresh functionality |  |  |  | Awaiting Initial Assessment
| R68 | R0068 -REC Main Body Data Protection Changes |  |  |  | Awaiting Initial Assessment
| R69 | R0069 - Amendments to Sample Access Agreement |  |  |  | Awaiting Initial Assessment
| R70 | R0070 - Provision of Enduring Test Environments |  |  |  | Awaiting Initial Assessment
| R71 | R0071 - DCC access to EES and GES |  |  |  | Awaiting Initial Assessment
| R72 | R0072 - Introduction of a new Meter Asset Condition Code |  |  |  | Awaiting Initial Assessment
| R73 | R0073 - Housekeeping Change Process |  |  |  | Awaiting Initial Assessment
| R74 | R0074 - Release of Community View Data Items to MEMs in GES |  |  |  | Awaiting Initial Assessment
| R75 | R0075 - Enabling Software Product Qualification |  |  |  | Awaiting Initial Assessment
| R76 | R0076 - DNOs notifying Suppliers about Crossed Meters |  |  |  | Awaiting Initial Assessment
R06
R10
R09
R16
R15
R25
R26
R17
R22
R21
R30
R32
R37
R36
R44
R47
R43
R54
R55
R52
R66