## Overview (hidden)
Row Labels | Count of Process Stage
Awaiting Implementation | 5
Consultation | 3
Final Assessment | 2
Initial Assessment | 11
Preliminary Assessment | 5
REC Party Impact Assessment | 1
Service Provider Impact Assessment | 1
Solution Development | 8
(blank)
Grand Total | 36

## Portfolio View
PRIORITY | DEVELOPMENT STAGE | INITIAL WORKING GROUP | SUB-COMMITTEE INPUT | PRELIMINARY ASSESSMENT | SOLUTION DEVELOPMENT (RC+WG) | IMPACT ASSESSMENT | PENDING DECISION | ON HOLD/WAITING LIST
VERY HIGH
HIGH
MEDIUM
LOW
TOTAL | 3 | 2 | 1 | 0 | 9 | 1 | 9 | 13
MP085B
MP094
MP137
MP165
MP169
MP223
MP187
DP197
DP206
MP207
DP218
MP224
MP230
MP234
MP235
MP242
MP184
MP205
MP239
MP231
MP241
DP238
MP176
MP244
MP246
DP247
MP248
MP252
MP253
MP219
MP254
DP255
DP256
DP257
DP258
DP259
DP260

## Prioritisation Matrix
Prioritisation Matrix
URGENCY | [9 empty] | Mod | Title | Raised | Status | L | O | B | C | S | Urgency | Value | Priority
3 |  | #N/A | P218 | #N/A |  | #N/A | P242 | #N/A |  | P085B | Synchronisation of smart meter voltage measurement periods | 2019-09-10 | On Hold | 1 | 2 | 1 | 1 | 0 | 1 | 1 | Medium
|  | #N/A | #N/A | #N/A |  | #N/A |  | #N/A |  | P094 | Supporting prepayment customers in no SM WAN scenarios | 2019-11-12 | Active | 2 | 2 | 0 | 2 | 1 | 0 | 3 | Medium
| #N/A | #N/A | #N/A | #N/A |  | #N/A | #N/A | #N/A |  | P137 | Sharing Information on Defects and Issues | 2020-07-20 | Active | 1 | 2 | 2 | 2 | 1 | 0 | 2 | Medium
| #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | P165 | ESME Voltage Accuracy | 2021-05-27 | On Hold | 0 | 2 | 2 | 1 | 0 | 1 | 1 | Medium
| #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | P169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | 2021-06-14 | Active | 3 | 2 | 0 | 2 | 1 | 1 | 3 | High
| #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | P176 | Customer Analytics Reporting | 2021-07-08 | Active | 1 | 2 | 1 | 2 | 0 | 0 | 2 | Medium
2 |  | #N/A | P246 | #N/A | P231 | #N/A | P224 | #N/A |  | P184 | Increase Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage use cases | 2021-09-20 | Waiting | 1 | 1 | 2 | 2 | 1 | 0 | 1 | Low
| #N/A | #N/A | P255 | #N/A | P252 | #N/A | P262 | #N/A |  | P187 | Incorporation of Target Round Trip Times and Target Success Rates into the SEC | 2021-11-02 | On Hold | 3 | 3 | 2 | 2 | 0 | 0 | 3 | Medium
| #N/A | #N/A | P256 | #N/A |  | #N/A | #N/A | #N/A |  | P197 | Reallocating Third Party Communications Hubs in the Event of a SoLR | 2022-01-11 | On Hold | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Low
| #N/A | #N/A | P261 | #N/A | #N/A | #N/A | #N/A | #N/A |  | P205 | Updating terminology to align with the NCSC | 2022-05-10 | Waiting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Low
| #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | P206 | Allowing Generation Licence Holders to Apply Export MPANs | 2022-05-10 | On Hold | 2 | 2 | 1 | 2 | 0 | 0 | 1 | Low
| #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A |  | P207 | Allowing Registered Supplier Agents to Maintain Meter Firmware | 2022-05-10 | Active | 2 | 3 | 1 | 2 | 0 | 1 | 2 | Medium
1 | P235 | #N/A | P085B | #N/A | P207 | #N/A | P169 | #N/A |  | P218 | Revising Charging Methodology | 2022-09-30 | Active | 1 | 2 | 3 | 0 | 0 | 3 | 1 | High
| P238 | #N/A | P165 | #N/A | P223 | #N/A | #N/A | #N/A |  | P219 | Accessing Consumption Data on behalf of SEC Parties | 2022-10-10 | Active | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Medium
| P244 | #N/A | P219 | #N/A | P230 | #N/A | #N/A | #N/A |  | P223 | WAN Coverage Reporting | 2022-11-07 | Active | 2 | 2 | 2 | 1 | 0 | 1 | 2 | Medium
| P248 | #N/A | P239 | #N/A | P247 | #N/A | #N/A | #N/A |  | P224 | SEC Performance Assurance Framework | 2023-01-09 | Active | 3 | 2 | 0 | 2 | 0 | 2 | 3 | High
| P260 | #N/A | P253 | #N/A | #N/A | #N/A | #N/A | #N/A |  | P230 | SMETS1 firmware delivery SLA | 2023-02-08 | Active | 1 | 2 | 0 | 1 | 2 | 3 | 2 | High
| #N/A | #N/A | P257 | #N/A | #N/A | #N/A | #N/A | #N/A |  | P231 | Firmware upgrade pathways | 2023-02-13 | Active | 0 | 2 | 1 | 2 | 2 | 2 | 2 | High
0 | P197 | #N/A | P184 | #N/A | P137 | #N/A | P094 | #N/A |  | P234 | Addition of GDPR Principles of Public Task and Legitimate Interests into the SEC | 2023-02-14 | On Hold | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
| P205 | #N/A | P206 | #N/A | P176 | #N/A | P187 | #N/A |  | P235 | Enhanced Meter Data Access for Other Users | 2023-02-14 | Waiting | 0 | 0 | 0 | 2 | 0 | 1 | 0 | Low
| P234 | #N/A | P241 | #N/A |  | #N/A | #N/A | #N/A |  | P238 | TSAT Expired Communication Hubs | 2023-03-14 | On Hold | 0 | 1 | 1 | 1 | 0 | 1 | 0 | Low
| P258 | #N/A | P254 | #N/A |  | #N/A | #N/A | #N/A |  | P239 | Enduring Solution for Resolving SMETS2 Device Certificate Misalignment Issue | 2023-04-03 | Active | 0 | 3 | 1 | 1 | 0 | 1 | 1 | Medium
| P259 | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A |  | P244 | Device Alerts for Smart Meter Credit Replenishment | 2023-08-08 | Waiting | 0 | 2 | 0 | 1 | 0 | 1 | 0 | Low
| #N/A | #N/A |  | #N/A | #N/A | #N/A | #N/A | #N/A |  | P246 | DCC User access to metadata via the DCC Self-Service Interface | 2023-08-30 | Active | 1 | 0 | 0 | 2 | 1 | 2 | 1 | Medium
| 0 |  | 1 |  | 2 |  | 3 |  | VALUE | P247 | Future Dating of Service Requests for SMETS1 Devices | 2023-09-12 | Active | 1 | 3 | 2 | 2 | 0 | 1 | 1 | Medium
[10 empty] | P248 | RDP Requirements for DCC Gateway Connections | 2023-09-12 | Active | 0 | 2 | 0 | 0 | 3 | 1 | 2 | Medium
[10 empty] | P250 | GBCS Correction | 2023-10-05 | Active | 3 | 2 | 2 | 0 | 0 | 3 | 2 | High
[10 empty] | P251 | Transfer of Secret Key Material | 2023-10-05 | Active | 3 | 3 | 3 | 0 | 3 | 3 | 3 | Very High
[10 empty] | P252 | Amending the process for Communications Hub returns | 2023-10-05 | Active | 2 | 3 | 2 | 0 | 0 | 2 | 2 | High
[10 empty] | P253 | Traffic Management for Price Control Events - User Actions Required | 2023-10-05 | Active | 0 | 2 | 1 | 1 | 0 | 1 | 1 | Medium
[10 empty] | P254 | Changes to GFI Arrangements | 2023-10-09 | Active | 2 | 1 | 1 | 0 | 0 | 0 | 1 | Low
[10 empty] | P255 | WAN issues during Smart Meter installations | 2023-11-14 | Active | 0 | 1 | 0 | 1 | 0 | 0 | 0 | Low
[10 empty] | P256 | SEC Alignment with DCC SMETS1 MHHS Capacity Requirements | 2023-12-07 | Active | 1 | 1 | 0 | 1 | 0 | 2 | 1 | Medium
[10 empty] | P257 | DCC Management of Duplicate Messages | 2023-12-11 | Active | 1 | 1 | 0 | 1 | 0 | 1 | 1 | Medium
[10 empty] | P258 | Aligning requirements for System Outage notifications | 2023-12-11 | Waiting | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Low
[10 empty] | P259 | Triage System Interface Definition | 2023-12-11 | Active | 0 | 0 | 0 | 0 | 1 | 0 | 0 | Low
[10 empty] | P260 | June 2024 SEC Release housekeeping | 2023-12-11 | On Hold | 0 | 3 | 0 | 0 | 0 | 1 | 0 | Low
[10 empty] | P261 | Extending the Organisation Certificate Validity Period | 2023-12-14 | Active | 0 | 2 | 0 | 0 | 1 | 2 | 1 | Medium
[10 empty] | P262 | Extending the Installation End Date for CHTS v1.0 and GBCS v1.1 | 2024-01-09 | Active | 3 | 1 | 3 | 2 | 0 | 2 | 3 | High

## CP priority heatmap (hidden)
Urgency | 3
2
1
0
|  | 0 | 1 | 2 | 3
Significance
| R06 | R0006 - Missing Meter Technical Details
| R09 | R0009 - Introduction of SDEP and EES User Maintenance API
| R10 | R0010 - New Meter Types for Auxiliary Proportional Controllers (APCs)
| R15 | R0015 - Remote communication obligations for Advanced Meters
| R16 | R0016 - Resolution of Bilateral Erroneous Transfers
| R17 | R0017 - Invalid Requests for Site Technical Details
| R21 | R0021 - Allowing REC accredited MEMs to de-energise and re-energise supply points independent of the Supplier
| R22 | R0022 - Amendment to REC Data Access Matrix
| R24 | R0024 - EAC information in the EES API
| R25 | R0025 - Service Provider Performance Charges (ERDS, GRDS, DCC)
| R26 | R0026 - Whole current (WC)/Current Transformer (CT) certificates
| R30 | R0030 - Erroneous Transfer Cancellations
| R32 | R0032 - New Registration data items and processes to support the transition to Market-wide Half-Hourly Settlement (MHHS)
| R36 | R0036 - Housekeeping amendments
| R37 | R0037 - Housekeeping amendments - Prepayment Credit Balance & Debt Transfer Processes
| R40 | R0040 - CSS Switch Synchronisation to ERDA at SecuredActive |  |  |  | Awaiting Initial Assessment
| R43 | R0043 - Commissioning of Works using shared Meter Operator services by the Crowded Meter Room Co-ordinator (CMRC) |  |  |  | Awaiting Initial Assessment
| R44 | R0044 - MHHS Programme Changes required to Central Switching Service
| R45 | R0045 - Changes to SDEP Messages for REC V3.0
| R47 | R0047 - Metering Code of Practice Consolidation Review
| R48 | R0048 - DCC Service Organisation Control 2 (SOC2) Assessments |  |  |  | Awaiting Initial Assessment
| R49 | R0049 - Intellectual Property Rights and Services Data Main Body changes |  |  |  | Awaiting Initial Assessment
| R50 | R0050 - Clarification of REC Maintenance of Qualification Schedule |  |  |  | Awaiting Initial Assessment
| R51 | R0051 - Switch Request Objections (Change of Occupier) |  |  |  | Awaiting Initial Assessment
| R52 | R0052 - GES Service Definition Document
| R53 | R0053 - 24/7 Emergency Metering Service |  |  |  | Awaiting Initial Assessment
| R54 | R0054 - EES Access for Virtual Lead Parties
| R55 | R0055 - Switching Operator Outage Notification Lead Time
| R56 | R0056 - EES/GES Additional Service Request for Housing Associations to be added to the Data Access Matrix |  |  |  | Awaiting Initial Assessment
| R57 | R0057 - Clarification of Supplier of Last Resort Obligations under the REC |  |  |  | Awaiting Initial Assessment
| R58 | R0058 - REC Services Procurement Clarification |  |  |  | Awaiting Initial Assessment
| R59 | R0059 - Maintenance of Qualification Schedule Change |  |  |  | Awaiting Initial Assessment
| R60 | R0060 - ERDS Service Definition timezone correction |  |  |  | Awaiting Initial Assessment
| R61 | R0061 - Resolution of invalid CSS data by Data Owners |  |  |  | Awaiting Initial Assessment
| R62 | R0062 - Removal of ERDA meteringPointEnergyFlow change restriction |  |  |  | Awaiting Initial Assessment
| R63 | R0063 - Addition of key information to all Service Now tickets |  |  |  | Awaiting Initial Assessment
| R64 | R0064 - Creating a Meter Operator Agent and MOCoP Installer |  |  |  | Awaiting Initial Assessment
| R65 | R0065 - Registration of Smart Export Guarantee (SEG) Sites |  |  |  | Awaiting Initial Assessment
| R66 | R0066 - Inclusion of new DNO mastered SMRS Data Items in the EES. |  |  |  | Awaiting Initial Assessment
| R67 | R0067 - Introduction of CSS refresh functionality |  |  |  | Awaiting Initial Assessment
| R68 | R0068 -REC Main Body Data Protection Changes |  |  |  | Awaiting Initial Assessment
| R69 | R0069 - Amendments to Sample Access Agreement |  |  |  | Awaiting Initial Assessment
| R70 | R0070 - Provision of Enduring Test Environments |  |  |  | Awaiting Initial Assessment
| R71 | R0071 - DCC access to EES and GES |  |  |  | Awaiting Initial Assessment
| R72 | R0072 - Introduction of a new Meter Asset Condition Code |  |  |  | Awaiting Initial Assessment
| R73 | R0073 - Housekeeping Change Process |  |  |  | Awaiting Initial Assessment
| R74 | R0074 - Release of Community View Data Items to MEMs in GES |  |  |  | Awaiting Initial Assessment
| R75 | R0075 - Enabling Software Product Qualification |  |  |  | Awaiting Initial Assessment
| R76 | R0076 - DNOs notifying Suppliers about Crossed Meters |  |  |  | Awaiting Initial Assessment
R06
R10
R09
R16
R15
R25
R26
R17
R22
R21
R30
R32
R37
R36
R44
R47
R43
R54
R55
R52
R66