## Portfolio View
PRIORITY | DEVELOPMENT STAGE | SOLUTION DEVELOPMENT (Business Reqs, Working Group, Sub-Committee Input, Preliminary Assessment) | SOLUTION REFINEMENT (Refinement Consultation, Working Group, Impact Assessment) | PENDING DECISION | ON HOLD/WAITING LIST
VERY HIGH
HIGH | DP218 | MP252 | MP169 | MP224
MP262
MEDIUM | DP265 | MP094 | MP085B | MP207 | MP137
| DP266 | MP247 | MP253 | MP219 | MP165
| DP267 | MP255 |  | MP230 | DP257
|  | MP268 |  | MP239
MP246
LOW |  | MP205 | MP241 | DP269 | MP184 | DP258
|  | MP235 | MP244 |  | DP197
|  | MP263 | MP248 |  | DP206
MP234
DP238
TOTAL | 4 | 8 | 6 | 8 | 9
SEC Modification Progression

## Prioritisation Matrix
Prioritisation Matrix
URGENCY | [6 empty] | Mod | Title | Raised | Status | L | O | B | C | S | Urgency | Value | Priority
3 |  | P218 |  |  |  |  | P085B | Synchronisation of smart meter voltage measurement periods | 2019-09-10 | Active | 1 | 2 | 1 | 1 | 0 | 1 | 1 | Medium
[7 empty] | P094 | Supporting prepayment customers in no SM WAN scenarios | 2019-11-12 | Active | 2 | 2 | 0 | 2 | 1 | 0 | 3 | Medium
[7 empty] | P137 | Sharing Information on Defects and Issues | 2020-07-20 | On Hold | 1 | 2 | 2 | 2 | 1 | 0 | 2 | Medium
[7 empty] | P165 | ESME Voltage Accuracy | 2021-05-27 | On Hold | 0 | 2 | 2 | 1 | 0 | 1 | 1 | Medium
[7 empty] | P169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | 2021-06-14 | Active | 3 | 2 | 0 | 2 | 1 | 1 | 3 | High
[7 empty] | P184 | Increase Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage use cases | 2021-09-20 | On Hold | 1 | 1 | 2 | 2 | 1 | 0 | 1 | Low
2 |  | P246 |  | P252 | P224 |  | P197 | Reallocating Third Party Communications Hubs in the Event of a SoLR | 2022-01-11 | On Hold | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Low
|  | P255 |  |  | P262 |  | P205 | Updating terminology to align with the NCSC | 2022-05-10 | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Low
|  | P267 |  |  |  |  | P206 | Allowing Generation Licence Holders to Apply Export MPANs | 2022-05-10 | On Hold | 2 | 2 | 1 | 2 | 0 | 0 | 1 | Low
[7 empty] | P207 | Allowing Registered Supplier Agents to Maintain Meter Firmware | 2022-05-10 | Active | 2 | 3 | 1 | 2 | 0 | 1 | 2 | Medium
[7 empty] | P218 | Revising Charging Methodology | 2022-09-30 | Active | 1 | 2 | 3 | 0 | 0 | 3 | 1 | High
[7 empty] | P219 | Accessing Consumption Data on behalf of SEC Parties | 2022-10-10 | Active | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Medium
1 | P235 | P085B | P265 | P207 | P169 |  | P224 | SEC Performance Assurance Framework | 2023-01-09 | Active | 3 | 2 | 0 | 2 | 0 | 2 | 3 | High
| (P238) | (P165) |  | P230 |  |  | P230 | SMETS1 firmware delivery SLA | 2023-02-08 | Active | 1 | 2 | 0 | 1 | 2 | 1 | 2 | Medium
| P244 | P219 |  | P247 |  |  | P234 | Addition of GDPR Principles of Public Task and Legitimate Interests into the SEC | 2023-02-14 | On Hold | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
| P248 | P239 |  | P266 |  |  | P235 | Enhanced Meter Data Access for Other Users | 2023-02-14 | Active | 0 | 0 | 0 | 2 | 0 | 1 | 0 | Low
| P263 | P253 |  | P268 |  |  | P238 | TSAT Expired Communication Hubs | 2023-03-14 | On Hold | 0 | 1 | 1 | 1 | 0 | 1 | 0 | Low
| P269 | (P257) |  |  |  |  | P239 | Enduring Solution for Resolving SMETS2 Device Certificate Misalignment Issue | 2023-04-03 | Active | 0 | 3 | 1 | 1 | 0 | 1 | 1 | Medium
0 | (P197) | (P184) |  | (P137) | P094 |  | P241 | Interoperability Checker Update | 2023-05-05 | Active | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Low
| P205 | (P206) |  |  |  |  | P244 | Device Alerts for Smart Meter Credit Replenishment | 2023-08-08 | Active | 0 | 1 | 0 | 1 | 0 | 1 | 0 | Low
| (P234) | P241 |  |  |  |  | P246 | DCC User access to Metadata on the DCC Self-Service Interface (SSI) | 2023-08-30 | Active | 1 | 0 | 0 | 2 | 1 | 2 | 1 | Medium
| (P258) | [5 empty] | P247 | Future Dating of Service Requests for SMETS1 Devices | 2023-09-12 | Active | 1 | 3 | 2 | 2 | 0 | 1 | 2 | Medium
[7 empty] | P248 | RDP Requirements for DCC Gateway Connections | 2023-09-12 | Active | 0 | 2 | 0 | 0 | 0 | 1 | 0 | Low
[7 empty] | P252 | Amending the process for Communications Hub returns | 2023-10-05 | Active | 2 | 3 | 2 | 0 | 0 | 2 | 2 | High
| 0 | 1 |  | 2 | 3 | VALUE | P253 | Traffic Management for Price Control Events - User Actions Required | 2023-10-05 | Active | 0 | 2 | 1 | 1 | 0 | 1 | 1 | Medium
[7 empty] | P255 | WAN issues during Smart Meter installations | 2023-11-14 | Active | 0 | 1 | 1 | 2 | 0 | 2 | 1 | Medium
| () = ON HOLD | [5 empty] | P257 | DCC Management of Duplicate Messages | 2023-12-11 | On Hold | 1 | 1 | 0 | 1 | 0 | 1 | 1 | Medium
| [] = WAITING LIST | [5 empty] | P258 | Aligning requirements for System Outage notifications | 2023-12-11 | On Hold | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Low
[7 empty] | P262 | Extending the Installation End Date for CHTS v1.0 and GBCS v1.1 | 2024-01-09 | Active | 3 | 1 | 3 | 2 | 0 | 2 | 3 | High
[7 empty] | P263 | Improving transparency of DCC indicative costs | 2024-01-24 | Active | 0 | 0 | 1 | 1 | 0 | 1 | 0 | Low
[7 empty] | P265 | Implementing ADT changes in response to a Security incident | 2024-02-13 | Active | 0 | 0 | 0 | 1 | 2 | 1 | 1 | Medium
[7 empty] | P266 | Alternative SMETS1 UTRN Generation | 2024-02-13 | Active | 1 | 1 | 1 | 3 | 0 | 1 | 2 | Medium
[7 empty] | P267 | Facilitating the installation and commisioning of meters triaged under Use Case 004 | 2024-02-13 | Active | 0 | 2 | 2 | 1 | 0 | 2 | 1 | Medium
[7 empty] | P268 | Certificate rotation and expired Certificates | 2024-02-13 | Active | 0 | 0 | 0 | 1 | 3 | 1 | 2 | Medium
[7 empty] | P269 | June 2024 SEC Release Supporting Changes | 2024-05-16 | Active | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Low

## Sense Check (hidden)
| Portfolio | Matrix | List
Very High | 0 | 0 | 0
High | 5 | 5 | 5
Medium | 17 | 17 | 17
Low | 13 | 13 | 13
Total | 35 | 35 | 35