## Portfolio View
PRIORITY | DEVELOPMENT STAGE | SOLUTION DEVELOPMENT (Business Reqs, Working Group, Sub-Committee Input, Preliminary Assessment) | SOLUTION REFINEMENT (Refinement Consultation, Working Group, Impact Assessment) | PENDING DECISION | ON HOLD/WAITING LIST
VERY HIGH | DP277 |  | MP275
HIGH | DP218 |  | MP169 | MP262
MP252
MP268
MEDIUM | DP278 | MP094 | MP085B | MP219 | MP137
|  | MP255 | MP247 |  | DP257
|  | MP265 |  |  | DP266
MP273
LOW | DP206 | MP184 | MP241 | MP274 | MP165
|  | MP205 | MP244 |  | MP234
|  | MP235 | MP271
TOTAL | 4 | 7 | 9 | 3 | 5
SEC Modification Progression

## Prioritisation Matrix
Prioritisation Matrix
URGENCY | [5 empty] | Mod | Title | Raised | Status | L | O | B | C | S | Urgency | Value | Priority
3 |  | P218 |  | P275 |  | P085B | Synchronisation of smart meter voltage measurement periods | 2019-09-10 | Active | 1 | 2 | 1 | 1 | 0 | 1 | 1 | Medium
|  |  |  | P277 |  | P094 | Supporting prepayment customers in no SM WAN scenarios | 2019-11-12 | Active | 2 | 2 | 0 | 2 | 1 | 0 | 3 | Medium
[6 empty] | P137 | Sharing Information on Defects and Issues | 2020-07-20 | On Hold | 1 | 2 | 2 | 2 | 1 | 0 | 2 | Medium
[6 empty] | P165 | ESME Voltage Accuracy | 2021-05-27 | On Hold | 0 | 2 | 2 | 1 | 0 | 0 | 1 | Low
[6 empty] | P169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | 2021-06-14 | Active | 3 | 2 | 0 | 2 | 1 | 1 | 3 | High
[6 empty] | P184 | Increase Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage use cases | 2021-09-20 | Active | 1 | 1 | 2 | 2 | 1 | 0 | 1 | Low
2 |  | P255 | P252 |  |  | P205 | Updating terminology to align with the NCSC | 2022-05-10 | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Low
|  | P278 | P268 | P262 |  | P206 | Allowing Generation Licence Holders to Apply Export MPANs | 2022-05-10 | Active | 2 | 2 | 1 | 2 | 0 | 0 | 1 | Low
[6 empty] | P218 | Revising Charging Methodology | 2022-09-30 | Active | 1 | 2 | 3 | 0 | 0 | 3 | 1 | High
[6 empty] | P219 | Accessing Consumption Data on behalf of SEC Parties | 2022-10-10 | Active | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Medium
[6 empty] | P234 | Addition of GDPR Principles of Public Task and Legitimate Interests into the SEC | 2023-02-14 | On Hold | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
[6 empty] | P235 | Enhanced Meter Data Access for Other Users | 2023-02-14 | Active | 0 | 0 | 0 | 2 | 0 | 1 | 0 | Low
1 | P235 | P085B | P247 | P169 |  | P241 | Interoperability Checker Update | 2023-05-05 | Active | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Low
| P244 | P219 | (P266) |  |  | P244 | Device Alerts for Smart Meter Credit Replenishment | 2023-08-08 | Active | 0 | 1 | 0 | 1 | 0 | 1 | 0 | Low
| P271 | (P257) | P273 |  |  | P247 | Future Dating of Service Requests for SMETS1 Devices | 2023-09-12 | Active | 1 | 3 | 2 | 2 | 0 | 1 | 2 | Medium
|  | P265 |  |  |  | P252 | Amending the process for Communications Hub returns | 2023-10-05 | Active | 2 | 3 | 2 | 0 | 0 | 2 | 2 | High
[6 empty] | P255 | WAN issues during Smart Meter installations | 2023-11-14 | Active | 0 | 1 | 1 | 2 | 0 | 2 | 1 | Medium
[6 empty] | P257 | DCC Management of Duplicate Messages | 2023-12-11 | On Hold | 1 | 1 | 0 | 1 | 0 | 1 | 1 | Medium
0 | P205 | (P165) | (P137) | P094 |  | P262 | Extending the Installation End Date for CHTS v1.0 and GBCS v1.1 | 2024-01-09 | Active | 3 | 1 | 3 | 2 | 0 | 2 | 3 | High
| (P234) | P184 |  |  |  | P265 | Implementing ADT changes in response to a Security incident | 2024-02-13 | Active | 0 | 0 | 0 | 1 | 2 | 1 | 1 | Medium
| P274 | P206 |  |  |  | P266 | Alternative SMETS1 UTRN Generation | 2024-02-13 | On Hold | 1 | 1 | 1 | 3 | 0 | 1 | 2 | Medium
|  | P241 |  |  |  | P268 | Certificate rotation and expired Certificates | 2024-02-13 | Active | 0 | 0 | 0 | 1 | 3 | 2 | 2 | High
[6 empty] | P271 | Sub-Committee seats for Other Users, Meter Data Retrievers and Registered Supplier Agents | 2024-08-13 | Active | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Low
[6 empty] | P273 | User Demand and Network Traffic Insights | 2024-10-01 | Active | 2 | 2 | 1 | 0 | 0 | 1 | 2 | Medium
| 0 | 1 | 2 | 3 | VALUE | P274 | Requirements for DCC Users to set TPS limits | 2024-10-04 | Active | 0 | 1 | 0 | 0 | 1 | 0 | 0 | Low
[6 empty] | P275 | Section K changes to support 4G Communications Hubs rollout | 2024-10-07 | Active | 2 | 3 | 2 | 3 | 0 | 3 | 3 | Very High
| () = ON HOLD |  |  |  |  | P277 | Virtual Gateway Connection | 2024-11-08 | Active | 0 | 2 | 0 | 2 | 0 | 2 | 1 | Very High
| [] = WAITING LIST |  |  |  |  | P278 | MHHS SMETS1 Cache Solution Amendment | 2024-11-11 | Active | 0 | 2 | 0 | 2 | 0 | 2 | 1 | Medium

## Sense Check (hidden)
| Portfolio | Matrix | List
Very High | 2 | 2 | 2
High | 5 | 5 | 5
Medium | 11 | 11 | 11
Low | 10 | 10 | 10
Total | 28 | 28 | 28