## Portfolio View
PRIORITY | DEVELOPMENT STAGE | SOLUTION DEVELOPMENT (Business Reqs, Working Group, Sub-Committee Input, Preliminary Assessment) | SOLUTION REFINEMENT (Refinement Consultation, Working Group, Impact Assessment) | PENDING DECISION | ON HOLD/WAITING LIST
VERY HIGH |  | MP277 |  | MP275
HIGH | DP218 |  | MP169 | MP280
| DP282 |  | MP252
| DP284 |  | MP268
MEDIUM | DP266 | MP094 | MP085B |  | MP137
| DP281 | MP255 | MP219 |  | MP247
| DP283 | MP265 | MP257
MP273
LOW | DP206 | MP165 | MP241 |  | MP244
|  | MP184 | MP271 |  | DP279
MP205
MP234
MP235
TOTAL | 7 | 9 | 9 | 2 | 4
SEC Modification Progression

## Prioritisation Matrix
Prioritisation Matrix
URGENCY | [5 empty] | Mod | Title | Raised | Status | L | O | B | C | S | Urgency | Value | Priority
3 |  | P218 | P284 | P275 |  | P085B | Synchronisation of smart meter voltage measurement periods | 2019-09-10 | Active | 1 | 2 | 1 | 1 | 0 | 1 | 1 | Medium
|  |  |  | P277 |  | P094 | Supporting prepayment customers in no SM WAN scenarios | 2019-11-12 | Active | 2 | 2 | 0 | 2 | 1 | 0 | 3 | Medium
[6 empty] | P137 | Sharing Information on Defects and Issues | 2020-07-20 | On Hold | 1 | 2 | 2 | 2 | 1 | 0 | 2 | Medium
[6 empty] | P165 | ESME Voltage Accuracy | 2021-05-27 | Active | 0 | 2 | 2 | 1 | 0 | 0 | 1 | Low
[6 empty] | P169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | 2021-06-14 | Active | 3 | 2 | 0 | 2 | 1 | 1 | 3 | High
[6 empty] | P184 | Increase Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage use cases | 2021-09-20 | Active | 1 | 1 | 2 | 2 | 1 | 0 | 1 | Low
2 |  | P255 | P252 | P280 |  | P205 | Updating terminology to align with the NCSC | 2022-05-10 | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Low
|  |  | P268 |  |  | P206 | Allowing Generation Licence Holders to Apply Export MPANs | 2022-05-10 | Active | 2 | 2 | 1 | 2 | 0 | 0 | 1 | Low
|  |  | P282 |  |  | P218 | Revising Charging Methodology | 2022-09-30 | Active | 1 | 2 | 3 | 0 | 0 | 3 | 1 | High
[6 empty] | P219 | Accessing Consumption Data on behalf of SEC Parties | 2022-10-10 | Active | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Medium
[6 empty] | P234 | Addition of GDPR Principles of Public Task and Legitimate Interests into the SEC | 2023-02-14 | Active | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
[6 empty] | P235 | Enhanced Meter Data Access for Other Users | 2023-02-14 | Active | 0 | 0 | 0 | 2 | 0 | 1 | 0 | Low
1 | P235 | P085B | (P247) | P169 |  | P241 | Interoperability Checker Update | 2023-05-05 | Active | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Low
| (P244) | P219 | P266 |  |  | P244 | Device Alerts for Smart Meter Credit Replenishment | 2023-08-08 | On Hold | 0 | 1 | 0 | 1 | 0 | 1 | 0 | Low
| P271 | P257 | P273 |  |  | P247 | Future Dating of Service Requests for SMETS1 Devices | 2023-09-12 | On Hold | 1 | 3 | 2 | 2 | 0 | 1 | 2 | Medium
|  | (P265) | P281 |  |  | P252 | Amending the process for Communications Hub returns | 2023-10-05 | Active | 2 | 3 | 2 | 0 | 0 | 2 | 2 | High
|  |  | P283 |  |  | P255 | WAN issues during Smart Meter installations | 2023-11-14 | Active | 0 | 1 | 1 | 2 | 0 | 2 | 1 | Medium
[6 empty] | P257 | DCC Management of Duplicate Messages | 2023-12-11 | Active | 1 | 1 | 0 | 1 | 0 | 1 | 1 | Medium
0 | P205 | P165 | (P137) | P094 |  | P265 | Implementing ADT changes in response to a Security incident | 2024-02-13 | On Hold | 0 | 0 | 0 | 1 | 2 | 1 | 1 | Medium
| P234 | P184 |  |  |  | P266 | Alternative SMETS1 UTRN Generation | 2024-02-13 | Active | 1 | 1 | 1 | 3 | 0 | 1 | 2 | Medium
| P279 | P206 |  |  |  | P268 | Certificate rotation and expired Certificates | 2024-02-13 | Active | 0 | 0 | 0 | 1 | 3 | 2 | 2 | High
|  | P241 |  |  |  | P271 | Sub-Committee seats for Other Users, Meter Data Retrievers and Registered Supplier Agents | 2024-08-13 | Active | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Low
[6 empty] | P273 | User Demand and Network Traffic Insights | 2024-10-01 | Active | 2 | 2 | 1 | 0 | 0 | 1 | 2 | Medium
[6 empty] | P275 | Section K changes to support 4G Communications Hubs rollout | 2024-10-07 | Active | 2 | 3 | 2 | 3 | 0 | 3 | 3 | Very High
| 0 | 1 | 2 | 3 | VALUE | P277 | Virtual Gateway Connection | 2024-11-08 | Active | 0 | 2 | 0 | 2 | 0 | 2 | 1 | Very High
[6 empty] | P279 | June 2025 SEC Releases & DUIS Housekeeping Changes' | 2025-01-16 | Active | 0 | 3 | 0 | 0 | 0 | 0 | 0 | Low
| () = ON HOLD |  |  |  |  | P280 | CPA Scheme Transition to SSC | 2025-01-16 | Active | 2 | 2 | 3 | 0 | 3 | 2 | 2 | High
| [] = WAITING LIST |  |  |  |  | P281 | Install Codes in the SMI | 2025-02-11 | Active | 1 | 2 | 1 | 1 | 2 | 1 | 2 | Medium
[6 empty] | P282 | CC/DESNZ Duis Change | 2025-02-11 | Active | 1 | 3 | 1 | 1 | 0 | 2 | 3 | High
[6 empty] | P283 | Other User Data Breach Reporting | 2025-02-11 | Active | 2 | 0 | 0 | 1 | 2 | 1 | 2 | Medium
[6 empty] | P284 | Extend S1SPKI Certificates | 2025-02-11 | Active | 1 | 1 | 2 | 1 | 1 | 3 | 3 | High

## Sense Check (hidden)
| Portfolio | Matrix | List
Very High | 2 | 2 | 2
High | 7 | 7 | 7
Medium | 12 | 12 | 12
Low | 10 | 10 | 10
Total | 31 | 31 | 31