## Portfolio View
PRIORITY | DEVELOPMENT STAGE | SOLUTION DEVELOPMENT (Business Reqs, Working Group, Sub-Committee Input, Preliminary Assessment) | SOLUTION REFINEMENT (Refinement Consultation, Working Group, Impact Assessment) | PENDING DECISION | ON HOLD/WAITING LIST
VERY HIGH
HIGH | DP218 | MP255 | MP169
MP268
MP282
MP285
MEDIUM | DP257 | MP281 | MP273 | MP219 | MP094
| DP266 | MP287 |  | MP283 | MP137
| DP289 | MP288 |  |  | MP247
LOW | DP206 | MP165 | MP241 | MP271 | MP085B
| DP279 | MP184 |  |  | MP244
| DP286 | MP205 |  |  | MP265
| DP290 | MP234
MP235
TOTAL | 8 | 9 | 6 | 3 | 6
SEC Modification Progression

## Prioritisation Matrix
Prioritisation Matrix
URGENCY | [5 empty] | Mod | Title | Raised | Status | L | O | B | C | S | Urgency | Value | Priority
3 |  | P218 | P285 |  |  | P085B | Synchronisation of smart meter voltage measurement periods | 2019-09-10 | On Hold | 2 | 1 | 1 | 0 | 0 | 0 | 1 | Low
[6 empty] | P094 | Supporting prepayment customers in no SM WAN scenarios | 2019-11-12 | On Hold | 2 | 2 | 0 | 2 | 1 | 0 | 3 | Medium
[6 empty] | P137 | Sharing Information on Defects and Issues | 2020-07-20 | On Hold | 1 | 2 | 2 | 2 | 1 | 0 | 2 | Medium
[6 empty] | P165 | ESME Voltage Accuracy | 2021-05-27 | Active | 0 | 2 | 2 | 1 | 0 | 0 | 1 | Low
[6 empty] | P169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | 2021-06-14 | Active | 3 | 2 | 0 | 2 | 1 | 1 | 3 | High
[6 empty] | P184 | Increase Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage use cases | 2021-09-20 | Active | 1 | 1 | 2 | 2 | 1 | 0 | 1 | Low
2 |  | P287 | P255 |  |  | P205 | Updating terminology to align with the NCSC | 2022-05-10 | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Low
|  |  | P268 |  |  | P206 | Allowing Generation Licence Holders to Apply Export MPANs | 2022-05-10 | Active | 2 | 2 | 1 | 2 | 0 | 0 | 1 | Low
|  |  | P282 |  |  | P218 | Revising Charging Methodology | 2022-09-30 | Active | 1 | 2 | 3 | 0 | 0 | 3 | 1 | High
[6 empty] | P219 | Accessing Consumption Data on behalf of SEC Parties | 2022-10-10 | Active | 0 | 1 | 1 | 0 | 1 | 1 | 1 | Medium
[6 empty] | P234 | Addition of GDPR Principles of Public Task and Legitimate Interests into the SEC | 2023-02-14 | Active | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
[6 empty] | P235 | Enhanced Meter Data Access for Other Users | 2023-02-14 | Active | 0 | 0 | 0 | 2 | 0 | 1 | 0 | Low
1 | P235 | P219 | P266 | P169 |  | P241 | Interoperability Checker Update | 2023-05-05 | Active | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Low
| P271 | P257 | P273 |  |  | P244 | Device Alerts for Smart Meter Credit Replenishment | 2023-08-08 | On Hold | 0 | 1 | 0 | 1 | 0 | 1 | 0 | Low
| P290 | P288 | P281 |  |  | P247 | Future Dating of Service Requests for SMETS1 Devices | 2023-09-12 | On Hold | 1 | 3 | 2 | 2 | 0 | 1 | 2 | Medium
|  |  | P283 |  |  | P255 | WAN issues during Smart Meter installations | 2023-11-14 | Active | 0 | 3 | 2 | 3 | 0 | 2 | 1 | High
[6 empty] | P257 | DCC Management of Duplicate Messages | 2023-12-11 | Active | 1 | 1 | 0 | 1 | 0 | 1 | 1 | Medium
[6 empty] | P265 | Implementing ADT changes in response to a Security incident | 2024-02-13 | On Hold | 0 | 0 | 0 | 1 | 2 | 0 | 1 | Low
0 | P165 | (P085B) | (P137) | (P094) |  | P266 | Alternative SMETS1 UTRN Generation | 2024-02-13 | Active | 1 | 1 | 1 | 3 | 0 | 1 | 2 | Medium
| P205 | P184 | (P247) | P289 |  | P268 | Certificate rotation and expired Certificates | 2024-02-13 | Active | 0 | 0 | 0 | 1 | 3 | 2 | 2 | High
| P234 | P206 |  |  |  | P271 | Sub-Committee seats for Other Users, Meter Data Retrievers and Registered Supplier Agents | 2024-08-13 | Active | 1 | 0 | 1 | 0 | 0 | 1 | 0 | Low
| (P244) | P241 |  |  |  | P273 | User Demand and Network Traffic Insights | 2024-10-01 | Active | 2 | 2 | 1 | 0 | 0 | 1 | 2 | Medium
| P279 | (P265) |  |  |  | P279 | June 2025 SEC Releases & DUIS Housekeeping Changes' | 2025-01-16 | Active | 0 | 3 | 0 | 0 | 0 | 0 | 0 | Low
| P286 |  |  |  |  | P281 | Install Codes in the SMI | 2025-02-11 | Active | 1 | 2 | 1 | 1 | 2 | 1 | 2 | Medium
| 0 | 1 | 2 | 3 | VALUE | P282 | Removal of Registration Check for Suppliers using SR8.9 targeting SMETS2+ CHF | 2025-02-11 | Active | 1 | 3 | 1 | 1 | 0 | 2 | 3 | High
[6 empty] | P283 | Other User Data Breach Reporting | 2025-02-11 | Active | 2 | 0 | 0 | 1 | 2 | 1 | 2 | Medium
| () = ON HOLD |  |  |  |  | P285 | Radio Teleswitch Service switch off | 2025-03-10 | Active | 1 | 2 | 0 | 3 | 0 | 3 | 3 | High
| [] = WAITING LIST |  |  |  |  | P286 | Establishment of the Privacy Sub-Committee into the SEC | 2025-03-11 | Active | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
[6 empty] | P287 | Access to historic GSME battery Alerts | 2025-03-11 | Active | 0 | 2 | 2 | 2 | 0 | 2 | 3 | Medium
[6 empty] | P288 | Erroneous Section J Default Notices | 2025-03-11 | Active | 1 | 2 | 1 | 0 | 0 | 1 | 2 | Medium
[6 empty] | P289 | BCDR Engagement | 2025-04-08 | Active | 3 | 3 | 1 | 1 | 0 | 0 | 0 | Medium
[6 empty] | P290 | IRP Batch 11 | 2025-04-08 | Active | 0 | 1 | 0 | 0 | 0 | 1 | 2 | Low

## Sense Check (hidden)
| Portfolio | Matrix | List
Very High | 0 | 0 | 0
High | 6 | 6 | 6
Medium | 12 | 12 | 12
Low | 14 | 14 | 14
Total | 32 | 32 | 32