## Portfolio View
PRIORITY | DEVELOPMENT STAGE | SOLUTION DEVELOPMENT (Business Reqs, Working Group, Sub-Committee Input, Preliminary Assessment) | SOLUTION REFINEMENT (Refinement Consultation, Working Group, Impact Assessment) | PENDING DECISION | ON HOLD/WAITING LIST
VERY HIGH
HIGH | DP218 | MP255 | MP169
MP268
MEDIUM | DP257 | MP094 | MP283 |  | MP137
| DP266 | MP281 | MP292 |  | MP247
| DP293 | MP288 |  |  | MP287
| DP294 | MP289
| DP295 | MP291
LOW | DP206 | MP165 | MP241 |  | MP085B
|  | MP184 | MP286 |  | MP244
|  | MP205 | MP290 |  | MP265
MP234
MP235
TOTAL | 7 | 11 | 7 | 0 | 6
SEC Modification Progression

## Prioritisation Matrix
Prioritisation Matrix
URGENCY | [5 empty] | Mod | Title | Raised | Status | L | O | B | C | S | Urgency | Value | Priority
3 |  | P218 |  |  |  | P085B | Synchronisation of smart meter voltage measurement periods | 2019-09-10 | On Hold | 2 | 1 | 1 | 0 | 0 | 0 | 1 | Low
[6 empty] | P094 | Supporting prepayment customers in no SM WAN scenarios | 2019-11-12 | Active | 2 | 2 | 0 | 2 | 1 | 0 | 3 | Medium
[6 empty] | P137 | Sharing Information on Defects and Issues | 2020-07-20 | On Hold | 1 | 2 | 2 | 2 | 1 | 0 | 2 | Medium
[6 empty] | P165 | ESME Voltage Accuracy | 2021-05-27 | Active | 0 | 2 | 2 | 1 | 0 | 0 | 1 | Low
[6 empty] | P169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | 2021-06-14 | Active | 3 | 2 | 0 | 2 | 1 | 1 | 3 | High
[6 empty] | P184 | Increase Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage use cases | 2021-09-20 | Active | 1 | 1 | 2 | 2 | 1 | 0 | 1 | Low
2 |  | (P287) | P255 |  |  | P205 | Updating terminology to align with the NCSC | 2022-05-10 | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Low
|  | P292 | P268 |  |  | P206 | Allowing Generation Licence Holders to Apply Export MPANs | 2022-05-10 | Active | 2 | 2 | 1 | 2 | 0 | 0 | 1 | Low
|  | P295 |  |  |  | P218 | Revising Charging Methodology | 2022-09-30 | Active | 1 | 2 | 3 | 0 | 0 | 3 | 1 | High
[6 empty] | P234 | Addition of GDPR Principles of Public Task and Legitimate Interests into the SEC | 2023-02-14 | Active | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
[6 empty] | P235 | Enhanced Meter Data Access for Other Users | 2023-02-14 | Active | 0 | 0 | 0 | 2 | 0 | 1 | 0 | Low
[6 empty] | P241 | Interoperability Checker Update | 2023-05-05 | Active | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Low
1 | P235 | P257 | P266 | P169 |  | P244 | Device Alerts for Smart Meter Credit Replenishment | 2023-08-08 | On Hold | 0 | 1 | 0 | 1 | 0 | 1 | 0 | Low
| P290 | P288 | P281 |  |  | P247 | Future Dating of Service Requests for SMETS1 Devices | 2023-09-12 | On Hold | 1 | 3 | 2 | 2 | 0 | 1 | 2 | Medium
|  | P291 | P283 |  |  | P255 | WAN issues during Smart Meter installations | 2023-11-14 | Active | 0 | 3 | 2 | 3 | 0 | 2 | 1 | High
|  |  | P293 |  |  | P257 | DCC Management of Duplicate Messages | 2023-12-11 | Active | 1 | 1 | 0 | 1 | 0 | 1 | 1 | Medium
[6 empty] | P265 | Implementing ADT changes in response to a Security incident | 2024-02-13 | On Hold | 0 | 0 | 0 | 1 | 2 | 0 | 1 | Low
[6 empty] | P266 | Alternative SMETS1 UTRN Generation | 2024-02-13 | Active | 1 | 1 | 1 | 3 | 0 | 1 | 2 | Medium
0 | P165 | (P085B) | (P137) | P094 |  | P268 | Certificate rotation and expired Certificates | 2024-02-13 | Active | 0 | 0 | 0 | 1 | 3 | 2 | 2 | High
| P205 | P184 | (P247) | P289 |  | P281 | Install Codes in the SMI | 2025-02-11 | Active | 1 | 2 | 1 | 1 | 2 | 1 | 2 | Medium
| P234 | P206 |  | P294 |  | P283 | Other User Data Breach Reporting | 2025-02-11 | Active | 2 | 0 | 0 | 1 | 2 | 1 | 2 | Medium
| (P244) | P241 |  |  |  | P286 | Establishment of the Privacy Sub-Committee into the SEC | 2025-03-11 | Active | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
| P286 | (P265) |  |  |  | P287 | Access to historic GSME battery Alerts | 2025-03-11 | On Hold | 0 | 2 | 2 | 2 | 0 | 2 | 3 | Medium
[6 empty] | P288 | Erroneous Section J Default Notices | 2025-03-11 | Active | 1 | 2 | 1 | 0 | 0 | 1 | 2 | Medium
| 0 | 1 | 2 | 3 | VALUE | P289 | BCDR Engagement | 2025-04-08 | Active | 3 | 3 | 1 | 1 | 0 | 0 | 0 | Medium
[6 empty] | P290 | IRP Batch 11 | 2025-04-08 | Active | 0 | 1 | 0 | 0 | 0 | 1 | 2 | Low
| () = ON HOLD |  |  |  |  | P291 | DNO Alerts to Suppliers | 2025-05-13 | Active | 1 | 2 | 0 | 2 | 0 | 1 | 1 | Medium
| [] = WAITING LIST |  |  |  |  | P292 | DSP DBT Finance Facility | 2025-05-13 | Active | 1 | 0 | 1 | 1 | 0 | 2 | 1 | Medium
[6 empty] | P293 | Deferment of DCC Planned Maintenance during Adverse Weather | 2025-06-09 | Active | 1 | 2 | 1 | 2 | 0 | 1 | 2 | Medium
[6 empty] | P294 | Review of DCC Maintenance Activities and Temporary Additional Allowance | 2025-06-10 | Active | 3 | 3 | 1 | 1 | 0 | 0 | 3 | Medium
[6 empty] | P295 | Amendment to SMETS1 Cache Solution | 2025-06-10 | Active | 0 | 2 | 0 | 2 | 0 | 2 | 1 | Medium

## Sense Check (hidden)
| Portfolio | Matrix | List
Very High | 0 | 0 | 0
High | 4 | 4 | 4
Medium | 15 | 15 | 15
Low | 12 | 12 | 12
Total | 31 | 31 | 31