## Portfolio View
PRIORITY | DEVELOPMENT STAGE | SOLUTION DEVELOPMENT (Business Reqs, Working Group, Sub-Committee Input, Preliminary Assessment) |  | SOLUTION REFINEMENT (Refinement Consultation, Working Group, Impact Assessment) | PENDING DECISION | ON HOLD/WAITING LIST
VERY HIGH |  |  |  | MP312
HIGH |  | DP218 |  | MP169
MP255
MP302
MP300
MEDIUM | DP305 | DP257 | MP294 | MP289 |  | MP137
| DP306 | MP281 | DP305 | MP301 |  | MP094
|  | MP291 |  | MP313 |  | DP266
MP293
LOW |  | MP205 |  | MP265 | MP234 | MP085B
|  | MP235 |  | MP244 |  | DP206
|  | MP184 |  |  |  | MP165
TOTAL | 2 | 13 |  | 7 | 1 | 6
SEC Modification Progression

## Prioritisation Matrix
Prioritisation Matrix
URGENCY | [5 empty] | Mod | Title | Raised | Status | L | O | B | C | S | Urgency | Value | Priority
3 |  | P218 |  | P312 |  | P085B | Synchronisation of smart meter voltage measurement periods | 2019-09-10 | On Hold | 2 | 1 | 1 | 0 | 0 | 0 | 1 | Low
[6 empty] | P094 | Supporting prepayment customers in no SM WAN scenarios | 2019-11-12 | On Hold | 2 | 2 | 0 | 2 | 1 | 0 | 3 | Medium
[6 empty] | P137 | Sharing Information on Defects and Issues | 2020-07-20 | On Hold | 1 | 2 | 2 | 2 | 1 | 0 | 2 | Medium
[6 empty] | P165 | ESME Voltage Accuracy | 2021-05-27 | On Hold | 0 | 2 | 2 | 1 | 0 | 0 | 1 | Low
[6 empty] | P169 | Managing SEC Obligations and the Consumer's Right to refuse a Smart Meter | 2021-06-14 | Active | 3 | 2 | 0 | 2 | 1 | 1 | 3 | High
[6 empty] | P184 | Increase Smart Capability of SMETS2 Twin Element ESME to support Solar and Storage use cases | 2021-09-20 | Active | 1 | 1 | 2 | 2 | 1 | 0 | 1 | Low
2 |  | P305 | P255 | P293 |  | P205 | Updating terminology to align with the NCSC | 2022-05-10 | Active | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Low
|  |  | P302 |  |  | P206 | Allowing Generation Licence Holders to Apply Export MPANs | 2022-05-10 | On Hold | 2 | 2 | 1 | 2 | 0 | 0 | 1 | Low
[6 empty] | P218 | Revising Charging Methodology | 2022-09-30 | Active | 1 | 2 | 3 | 0 | 0 | 3 | 1 | High
[6 empty] | P234 | Addition of GDPR Principles of Public Task and Legitimate Interests into the SEC | 2023-02-14 | Active | 0 | 0 | 0 | 1 | 0 | 0 | 0 | Low
[6 empty] | P235 | Enhanced Meter Data Access for Other Users | 2023-02-14 | Active | 0 | 0 | 0 | 2 | 0 | 1 | 0 | Low
[6 empty] | P244 | Device Alerts for Smart Meter Credit Replenishment | 2023-08-08 | Active | 0 | 1 | 0 | 1 | 0 | 1 | 0 | Low
[6 empty] | P255 | WAN issues during Smart Meter installations | 2023-11-14 | Active | 0 | 3 | 2 | 3 | 0 | 2 | 1 | High
1 | P235 | P257 | P266 | P169 |  | P257 | DCC Management of Duplicate Messages | 2023-12-11 | Active | 1 | 1 | 0 | 1 | 0 | 1 | 1 | Medium
| P307 | P291 | P281 | P300 |  | P265 | Implementing ADT changes in response to a Security incident | 2024-02-13 | Active | 0 | 0 | 0 | 1 | 2 | 0 | 1 | Low
|  | P306 |  |  |  | P266 | Alternative SMETS1 UTRN Generation | 2024-02-13 | On Hold | 1 | 1 | 1 | 3 | 0 | 1 | 2 | Medium
|  | P313 |  |  |  | P281 | Install Codes in the SMI | 2025-02-11 | Active | 1 | 2 | 1 | 1 | 2 | 1 | 2 | Medium
[6 empty] | P289 | BCDR Engagement | 2025-04-08 | Active | 3 | 3 | 1 | 1 | 0 | 0 | 0 | Medium
[6 empty] | P291 | DNO Alerts to Suppliers | 2025-05-13 | Active | 1 | 2 | 0 | 2 | 0 | 1 | 1 | Medium
0 | (P165) | (P085B) | (P137) | (P094) |  | P293 | Deferment of DCC Planned Maintenance during Adverse Weather | 2025-06-09 | Active | 1 | 2 | 1 | 2 | 0 | 1 | 2 | Medium
| P205 | P184 | P301 | P289 |  | P294 | Review of DCC Maintenance Activities and Temporary Additional Allowance | 2025-06-10 | Active | 3 | 3 | 1 | 1 | 0 | 0 | 3 | Medium
| P234 | (P206) |  | P294 |  | P300 | Additional Operational Metrics to Measure on Success | 2025-09-08 | Active | 2 | 3 | 2 | 2 | 0 | 1 | 3 | High
| P244 | P265 |  |  |  | P301 | Review of Additional Registration Data (Gas Transporters) | 2025-09-09 | Active | 2 | 0 | 2 | 0 | 1 | 0 | 2 | Medium
[6 empty] | P302 | Supplier Alerts for ENOs | 2025-09-09 | Active | 1 | 2 | 1 | 2 | 0 | 2 | 2 | High
[6 empty] | P305 | CH Return Process Review | 2025-10-13 | Active | 0 | 2 | 2 | 1 | 0 | 2 | 1 | Medium
| 0 | 1 | 2 | 3 | VALUE | P306 | Alternative Self Service Data solution for Service Users | 2025-10-14 | Active | 0 | 2 | 1 | 0 | 1 | 1 | 1 | Medium
[6 empty] | P307 | Extension to MP219 concept to SEC Section I 1.3 | 2025-11-11 | Active | 0 | 1 | 1 | 1 | 0 | 1 | 0 | Low
| () = ON HOLD |  |  |  |  | P312 | Caching SRV 4.10 for SMETS1 Devices | 2025-12-09 | Active | 0 | 3 | 3 | 3 | 2 | 3 | 3 | Very High
| [] = WAITING LIST |  |  |  |  | P313 | Remove the DCC requirement to delete CHs from the SMI’ | 2025-12-09 | Active | 0 | 3 | 1 | 0 | 0 | 1 | 1 | Medium

## Sense Check (hidden)
| Portfolio | Matrix | List
Very High | 1 | 1 | 1
High | 5 | 6 | 5
Medium | 14 | 12 | 13
Low | 9 | 10 | 10
Total | 29 | 29 | 29