## Risk Dashboard
OPSG Risk Register
Risk ID | Risk Title | Latest action plan update | Current Severity Score | Post-action severity score | OPSG Response | Raised by | Owner | Category | Associated Issue ID | Reviewed | Open/ Closed | Effect on Severity As Rollout Progresses
OPSG001 | Device Model Combinations | This report has now been delivered for over 12 months - it is also shared with SEC, BEIS and industry in general. | 12 | 4 | Monitor | OPSG | OPSG | Legal & Regulatory Client & Customer Reputation | 69 - HAN Stability | OPSG | Open | Increases - more installations implies greater probability of risk. As Device Model Combinations increase, the HAN will become progressively harder to maintain at an appropriate standard (in terms of Supplier functions, no. of OTA updates etc.)
OPSG002 | HAN/WAN Stability | SECAS proceeding with actions from Interoperability Workshop after the SEC Panel agreed the approach and next steps in October 2021. | 15 | 5 | Monitor | OPSG | OPSG | Legal & Regulatory Client & Customer Reputation | 69 - HAN Stability | OPSG | Open | Increases - more installations implies greater probability of risk. As Device Model Combinations increase, the HAN will become progressively harder to maintain at an appropriate standard (in terms of Supplier functions, no. of OTA updates etc.)
OPSG003 | CH Exceptions | DCC provided an update to OPSG in January 2022 and noted that CH exclusions will be managed via reporting rather than raising individual incidents.The OPSG endorsed this process, notingthat it will be easier cross check exclusions.The DCC agreed to provide regular updates at the OPSG. | 9 | 9 | Accept Monitor | OPSG | OPSG | Reputation Client & Customer Legal & Regulatory | 2 - CH Exceptions | OPSG | Open | Increases - unless Supplier processes are corrected, probability of risk is likely to increase
OPSG004 | DNO Certificates | SECAS continue to capture all relevant updates via the OPSG Issue Log and present a bi-monthly issue summary to OPSG. | 12 | 4 | Mitigate Monitor | OPSG | OPSG | Legal & Regulatory | 4 - DNO Certs | OPSG | Open | Increases - unless Supplier processes are corrected, probability of risk is likely to increase
OPSG005 | DCC Delivery Capabilities for DNO POA and PRA Alerts | DCC are currently undertaking a project to measure the power outage and power restoration alert performance as it fluctuates depending on the size of the outage. Performance is being measured between August 2021 through to February 2022 to collect six months of data specifically over the winter months where there are more outages. MP96 is on hold until February 202 | 12 | 12 | Monitor | OPSG | OPSG | Legal & Regulatory | 54 - POA/PRA | OPSG | Open | Increases - more installations, especially if focussed around a single feeder, increase the potential impact of the risk
OPSG006 | CSP North Services | The DCC/CSP N to provide the OPSG assurance on its capability to meet the requirements in the proposed plan, following the CSP N Technical Review | 20 | 12 | Mitigate | OPSG | OPSG | Customer & Client Legal & Regulatory Reputation | DCC Operations/Design | OPSG | Open | Increases - probability increases as the chance that a Supplier might want a tailored firmware delivery increases. Prepayment, OTA and delivery of SR issues in CSPN could aggravate as the estate grows.
OPSG007 | DCC BCDR Arrangements Relating to Government regulations on the Pandemic | The DCC presented the Business Continuity and Disaster Recovery (BCDR)Test Calendar for April 2022 - March 2023.The OPSG conditionally approved the testing calendar for April 2022 -March 2023, subject to review when the full picture of DCC maintenance for 2022 is available. | 5 | 4 | Accept Mitigate | OPSG | OPSG | Client & Customer Legal & Regulatory | N/A | OPSG | Open | Decreases - as Pandemic is likely to recede soon, this risk should decrease in Severity long term
OPSG008 | CSP N PM2 Performance | OPSG to monitor CSP N plans towards 92% SLA with a follow up plan to be required for 99% SLA. January 2022 Update. | 15 | 12 | Monitor Mitigate | OPSG | OPSG | Client & Customer Legal & Regulatory | DCC Operations/Design | OPSG | Open | Increases - the impact of the risk increases as installations grow in the North and as these installations cannot be properly served
OPSG009 | CSPs SEC required performance levels and capacity demands at peak rollout/end of rollout. | TABASC to monitor the arrival dates for C&S Next Gen Hubs, their relevant communication technology, and timeline of introduction. TABASC to also undertake a review of the CSP N architecture to assess its scalability. | 12 | 12 | Monitor Mitigate | OPSG | OPSG | Client & Customer Legal & Regulatory | N/A | OPSG | Open | No impact - risk depends on the number of final installations, not on the number of installations and its trend over time. Note though that, while this Risk concerns performance levels towards end of rollout, a similar risk arguably exists for performance levels at end of CSP contract (which is more imminent)
OPSG010 | SMETS1 DCO Service across different Device cohorts. | The OPSG agreed that it is necessary to align the capability of the firmware download service and the SEC requirement. OPSG agreed with DCC's proposal for a SEC Modification to be raised to consider the adjustment of the requirement in the SEC in parallel with a DCC Change Request to consider enhancement of the service capability to meet the current SEC requirement. | 8 | 4 | Monitor | OPSG | OPSG | Client & Customer Legal & Regulatory | N/A | OPSG | Open | Probably Increases. The severity could be expected to grow as the number of SMETS1 migrations rises; the end of FOC is expected to see 15 million Meters and the impact of the DCO going down in this instance is significant.
OPSG011 | Progression of Critical Operational Modifications | Tracked under TABASC Risk Register as TABASC011.3 and SEC Panel Risk Register as Risk 1. | 9 | 9 | Accept Monitor | OPSG | OPSG | Client & Customer | N/A | OPSG | Open | No impact - Modifications and their progressions are not dependent on the SMETS2 rollout. However, there may be a higher Severity with the general passage of time as Modifications concerning the potential integration of Smart Metering to innovations and new standards (e.g. PAS) are proposed
OPSG012 | Ancilliary DCC Service Demands | TBD | 9 | 9 | Accept Monitor | OPSG | OPSG | Client & Customer | N/A | OPSG | Open | Increases - More installed Devices means service management is likely to be strained more are issues are discovered in live installations
OPSG014 | Risk Suppliers cannot fulfill certain post-commissioning obligations as it is unlikely that iDNOs will become DCC Users. | TBD | 8 | 8 | Accept & Monitor | OPSG | OPSG | Client & Customer | N/A | OPSG | Open | Unclear - depends on the number of meters in iDNO areas. If there are more such meters, then risk increases. If not, then risk stays unchanged
OPSG015 | CH Supply Chain - Global Component Shortage. | The DCC presented the outcome on the TCHODR following the consultation. The DCC reported that the proposed changes to the TCHODR rules had been approved by the SEC Panel in December 2021. The DCC will engage with CSPs and SEC parties to implement these new rules. | 15 | 3 | Mitigate Monitor | OPSG | OPSG | Client & Customer | N/A | OPSG | Open | Increases - the impact of the risk increases as installations grow
This document is classified as White in accordance with the Panel Information Policy. Information can be shared with the public, and any members may publish the information, subject to copyright.
Note on D9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Linked to predetermined action plan, most of which have not been kicked off. Summary of risk should replace this.