## OPSG Escalated SEC Panel Risks
# | There is a risk that… | Impact | Likelihood | Severity | Mitigation | RAG Status
(Completed actions in italics)
OPSG/006 | Services delivered in CSP N in the future will fail to meet SEC requirements in areas beyond those where serious issues have already been encountered, or as use of the services increases. | 5 | 4 | 20 | • DCC/Arqiva to present a clear Optimisation and Scaling Plan that shows how the service will evolve to meet the needs of Users throughout the rollout - The DCC and CSP N are working on Phase 1 of the project. The OPSG commented that it will need some assurance from CSP N on its capability to meet the requirements in the proposed plan. | AMBER
• The DCC/CSP N to provide the OPSG assurance on its capability to meet the requirements in the proposed plan, following the CSP N Technical Review - OPSG to review action plan following the CSP N Technical Review. Dependant on results of the independent review, DCC to progress with implementation of remediations identified in the review.
OPSG/008 | The DCC will be unable deliver the expected Performance Improvements as part of the Service Improvement Plan (SIP) for CSP N on PM2 'Firmware Payload delivery'. | 4 | 3 | 12 | • CSPN to undertake several tactical improvements and remediations to improve performance on PM2 - Plan started in Jan 2021 with an expectation of completion in Jun 2022. This is to deliver the enduring plan with the aim of 99% performance. | AMBER
• CSPN presented its Service Improvement Plan (SIP) for short to medium term remediations resolving performance issues on the network. The plan has been accepted by industry and is reported against monthly to the OPSG.
• OPSG to monitor CSP N plans towards 92% SLA with a follow up plan to be required for 99% SLA. In CSPN, metric PM2 (OTA Firmware Delivery) continues to be below the Minimum Service Level: The tactical remediation plan is now approaching a conclusion, having considerably improved performance. DCC reported that CSP N had achieved 98.11% performance in February 2022 and 98.01% in March 2022, which meant performance had hit the plan’s target for the third month in a row.
• DCC to provide follow up plan to achieve 99% SLA - The OPSG thanked DCC on its execution of the remediation plan for PM2 in CSP N and noted that it expects a full ‘Project Closure Report’ for discussion. OPSG also asked DCC to consider and report to OPSG on whether the 99% SLA was achievable or not.
OPSG/002 | Change (CH/Meter Firmware, CSP Infrastructure) will cause unstable connections between Comms Hubs and HAN devices impeding the Service User's ability to send Commands to the devices and the device's ability to send Responses & Alerts to the Service Users. | 5 | 3 | 15 | • DCC to identify the triggers and their causes via the HANSIT report and present those findings at TSIRS moving forward: SECAS to follow TSIRS and actively report developments to OPSG. This report has now been delivered for over 12 months and is also shared with SECAS, BEIS and industry in general. | AMBER
• The OPSG sponsored a workstream to provide recommendations on measures of Interoperability at a DMC and Device level, the project is ongoing.
• SECAS has confirmed with the SMDA Scheme Operator the proportion of deployed DMCs that have been assured by SMDA to gain a better approximation of the scale of untested DMCs.
• DCC to consider providing aggregate success and failure rates of for SRs and associated responses. MP176 is currently going through the refinement process and will include “aggregate success and failure rates for SRs and associated responses, the modification may allow Users to identify non-comms as a result of HAN issues as opposed to WAN issues with interrogation.
• SECAS to carry out actions taken from the Interoperability Workshop: SECAS provided the Panel with the proposed reporting requirements, cost, and timescales for DCC to deliver agreed new reporting. The Panel noted the Problem Statements provided and approved the draft reporting requirements. Interoperability reporting is now looking to include SMETS1 Devices per request from SEC Panel so the project will be refered to as SMETS Interoperability Project going forward. SECAS met with DCC in March 2022 to discuss the reporting requirements in more detail and DCC now want to carry out a full impact assessment rather than go straight to delivery. Latest estimate on developing the reports is 3-6 months.
• SECAS to monitor the development of the agreed reporting as an output of the SMETS2 Interoperability project.
OPSG/015 | DCC’s Comms Hubs Supply chain will not be able to deliver to Service User's requirements due to a global component shortage and increasing costs of the components. | 4 | 5 | 20 | • SECAS monitors the risk via the Comms Hub Supply Chain Working Group and the DCC reports regular updates to the OPSG. | AMBER
• DCC has explored options for better management of supply chain and forecasting with Users. The DCC has conducted an appraisal against current forecasts, stock and project supply as well as liaised with BEIS regarding industry level install targets for 2022. DCC has also engaged with customers via the Supply Chain Working Group, SMDG and held bilateral discussions on how the process can be supported through temporary ordering arrangements that would continue to aid the delivery of CHs through 2022 and into 2023. The DCC also proposed a set of actions including raising an urgent modification to adjust the Temporary Communication Hub Ordering and Delivery Rules (TCHODR) to extend the applicable end date and include the Global Component Shortage risk.
• DCC to carry out broader assessment on the current ordering and forecasting rules: The DCC has reported that the majority of SEC Parties agreed with the proposed option 2, to extend the ordering and delivery rules to cover Comms hub delivery up to September 2023. SEC Panel endorsed the proposal on 14 April 2022.
• OPSG to monitor Supply Chain challenges in C&S: OPSG members have raised further concerns and have asked DCC to provide regular updates on the challenges to members.
OPSG/016 | The full required 2G/3G service will not be provided until the final sunset date at the currently agreed price. | 5 | 3 | 15 | • DCC to confirm actions taken under the contract to ensure continuity of complete service until 2033: DCC provided SEC Panel with a Network Transition and Sunset update in March 2022. DCC outlined to SEC Panel, the current SMETS2 and SMETS1 network contracts that are due to reach first break or expiry between 2028 and 2031. DCC are waiting for formal confirmation from their network service providers on their sunset plans. | AMBER
• DCC to continue the development of a transition plan, taking account of any commercial and technical uncertainties related to 2G/3G sunsetting: DCC informed SEC Panel that it expects to award the 4G Communications Hubs (CH) contract in May or June 2022, subject to BEIS’s approval of the Business Case
• DCC to confirm implications, if any, for SMETS1 providers announced intentions to close 3G services in 2023: DCC confirmed to SEC Panel that SMETS1 services are supported by 2G networks stating it was modelling the options to optimise extensions to existing SMETS1 network contracts. The earliest SMETS1 network contract is due to expire in 2028. DCC will engage with customers for bilateral reviews of initial SMETS1 contract extension modelling work, assumptions and options in April 2022.
• DCC to detail the impact for customers during transition: DCC outlined the high level transitional impacts at SEC Panel, related to the replacement of Devices, ahead of the 2G/3G Sunset. - Customers will have to carry out 4G Comms Hub testing and integration into supply chain and field installation operations. - SMETS2 2G/3G Comms Hub will need to be replaced with 4G Comms Hub - And SMETS1 meters and Comms Hub will have to be replaced with 4G Comms Hub and SMETS2 meters.