## Issues Log
Item | Date Raised | Team/individual | Topic | Device/System | Description | Impact to Other Parties | Considerations | Allocated to | Status | Suggested review date | SECAS update | Outcomes
1 | 2020-10-01 | Ali - Change | Firmware Upgrades | PPMID/HCALCS | A sensible pathway needed to implement SECMP0007 and supporting peripheral Devices on the HAN. | High | Include the ability to undertake ‘local upgrade’ (as long as it does not impact the ZigBee SE profile). | SECMP0007 WG The SSC, TABASC and OPSG reviewed the solution. DSP System and SEC Changes to be implemented in Nov 2021 Release. SECAS to engage OPSG and TABASC on the implementation of the CSP System and Comms Hub updates. | Closed | 2021-11-01 | SECAS Change Team will manage the implementation of SECMP0007. SECAS has engaged the OPSG and TABASC on the Implementation approach for the CSP System and Communications Hub firmware updates. | The Panel agreed an approach on 16 April 2021 whereby SECMP0007 CSP System changes will be implemented in the June 2022 SEC Release, and SECMP0007 Communications Hub firmware updates will then be implemented as and when they are ready from each CSP. There is a lot of pressure on CSPs to roll out as soon as possible. There will be a consequential mod to amend some of the technical specifications but this will be implemented in Nov 2021 in the tech spec uplift.
2 | 2020-10-01 | Ali - Change | Gas Data accuracy | GSME/GPF | Timestamp of gas data SECMP0015 – was a major inhibitor to using gas data for purposes beyond just billing. | High | Needed a resolution to allow accurate data to be used for analytical and service delivery. | TSIRs SECMP0015 WG | Closed | Q1 2021 | SECMP0015 encountered challenges due to significant changes in the cost estimation which resulted in the Change Board rejecting the modification. The SEC Panel and the Authority overturned this decision. Outcome: Ofgem approved the Modification. Likely to be included in the June 2022 Release. Lessons learned. | Ofgem approved SECMP0015. Further information can be found: https://smartenergycodecompany.co.uk/modifications/gpf-timestamp-for-reading-instantaneous-gas-values/ PLEASE NOTE: SECAS wrote to Ofgem to request the implementation date be moved to November 2022 as agreed at Panel on 16 April 2021 to ensure the cost savings secured by implementing mods together are retained.
9 | 2020-10-01 | Tech Ops | HAN | DBCH/Interoperability | Dual band CH implementation – not yet off the ground and many issues around implementation. | High | Ongoing testing should identify issues, however this is an ongoing process and significantly delayed, impacting roll-out and supply chain. | DCC SMDG IMF OPSG | Closed | Q3 2022 | 16/04/2021: OPSG Issue 68 'The lack of Dual Band CHs is a growing concern and no real clarity of when the chipset issues will be resolved'. DBCHs are now available in CSP CandS and CSP N, with over 800 installed since Sept 2020. SMDG/IMF are currently monitoring the progress and issues related to the deployment of DBCHs. Individual issues have been identified across the three devices, firmware fixes are currently in test for two of the devices. Root cause investigation is still underway for one of the devices. 21/07/2021: OPSG Issue 68 was closed at June OPSG as DBCHs are now available and over 1000 installed. However, separate Issues have been raised on the OPSG Issue log to track the two outstanding defects associated to CSP C&S DBCHs (OPSG Issue 80 for Display issue and Issue 81 for N25 Sub Ghz Join issue) with firmware available in UIT for the WNC (v2.0.0.6) and Toshiba CHs (Release 13.3). The DCC acknowledge that the Toshiba fix will require proving in Production and are planning on providing initial volumes in December 2021 and January 2022 for piloting. 20/09/2021 - This issue is now being tracked across two individual Issues on the OPSG Log. For Issue 80 (PPMID Issue) The WNC firmware v2.0.0.6 received Operational Acceptance (OA) on 19 August 2021 with Over-the-Air (OTA) pilot commencing on 24 August 2021. Initial manufactured versions are on track to be available from January 2022. Next steps will be to track pilot to completion and confirmation of resolution of defect and then request closure of OPSG Issue. For issue 81 (N25 Join Issue) the Toshiba firmware release 13.3 achieved OA with Central Products List (CPL) entry and OTA Pilot commencing on 16 August 2021. Initial manufactured versions are on track to be available for the Pilot in November 2021, with a Mass Manufacturing decision point in December 2021. OPSG Issue will be requested for closure following pilot completion and confirmation of the defect fix. 28/02/2022 - Issue tracked under OPSG Issues #80 and #81. Mass manufacturing for the release of WNC DB 2.0.0.6 (GBCS v3.2) and Tosh DB 13.3 (GBCS v3.2) are underway. WNC’s units are in the UK with VMO2, with first shipments planned for 1 March 2022. IMF noted that some Energy Suppliers having been waiting for this firmware release to address some known operational challenges. OPSG Issue will be proposed for closure following pilot completion and confirmation of the defect fix. Quarterly OSP Call - agreed to close item 9. | Issue is being tracked across two individual Issues on the OPSG Log #80 & #81.
10 | 2020-10-01 | Tech Ops | WAN | CH | Next generation Communication Hubs – who determines these? What is desirable? Is it right for costs to be smeared? What functionality should be supported? | High | Need to have clear definition of requirements that includes fixing current CH issues as well as solving loss of 2G/3G WAN service availability. | TABASC SEC Panel | Closed | Q1 2022 | 11/12/20: TBDG Strategic Design Review agreed by Panel. 16/04/2021: LC13B plan for the Communications Hub and Networks programme sent to IMF members for comment, consultation close on 7 May 2021. DCC will be presenting on the plan at the IMF on 29 April 2021. Concerns regarding the scope, cost and approach should be raised as part of the SEC Panel and Sub-Committee reviews of the next gen comms hubs (4G). BEIS are making the final decision but have sought Panel input into the programme. 21/07/2021: LC13B consultation completed and minimal changes made to the plan. The SEC Panel and Sub-Committees will be reviewing the Candidate Optional Requirements to provide a recommendation to BEIS in September on whether any requirements should be considered for Day 1, As soon as possible following Go Live, future requirement or not required. 01/10/2021 - Propose to close this item as the LC13B plan for the Communications Hub and Networks programme has been sent to IMF. SEC Panel wrote to BEIS endorsing the view of SEC Sub-Committees on the Candidate Optional Requirements. BEIS have oversight of the programme and set the criteria for what MVP will deliver. | Propose close this item as members can feed their views and opinions to the SEC Panel or Sub-Committees or directly to BEIS which would include the points raised on this issue
5 | 2021-01-01 | Ash | TOU tariffs | ESME | TOU tariffing – not being implemented in tariff registers by any retailer (that we are aware of) in contravention to SMETS and to the restriction of value creation. DCC say all is in place to allow this to happen. | N/A | Need to confirm that TOU has been tested and is theoretically operable. | DCC SMDA | Closed | 2021-04-28 | Need confirmation that complex tariffs are being used or have been tested, and are fully operable. This may be worth referring to the OPSG to confirm whether it has been raised as an issue with them/TSiRs. | Attendees asked in April 2021 if there are concerns about complex tariffs. Group agreed to close the issue.
6 | 2021-01-01 | Ash | DSR (Demand Side Response) | HCALCs/EV chargers | HCALCs and EV chargers – do these become a mandated brake for DNOs or just one of the routes to control EVs? | N/A | Need clarity over the ‘Party’ role in performing load management across the range of switching services (SRs) | Subject to SECMP0062 WG TABASC - SAPC and EV use cases BSI – PAS1878/1879 proposals | Closed | 2021-04-28 | For consideration by TABASC. SECAS to provide further information in the next Issues log update. | Attendees asked in April 2021 if this is still considered an issue. Group agreed to close the issue.
11 | 2021-01-01 | Joey - Tech Ops | Enrolment and Adoption | SMETS1 | Risk associated with DCC failing to complete E&A for all assets leading to premature replacement. | High | Without a churn contract in place MAPs can’t charge suppliers for an early removal. Not all suppliers have contracts with all MAPs despite it being a licence requirement. Future innovation should always bear in mind that these assets are costed to last for a long period of time (10-20 years?) | BEIS/TBDG – Transitional Governance TABASC SEC Panel | Closed | Q2 2021 | Pre-Migration and Migration issues are currently sat with the BEIS led TBDG Enrolment and Adoption Sub Group. Post Migration issues can be raised at the SEC Panel and Sub Committees for consideration. 16/04/2021: SMETS1 Final Operating Capability (FOC) was deployed at the end of February. The first FOC EPCL entries went live at the beginning of April 2021. Enrolment rates remain high with over 97% of devices attempted being successfully enrolled. Over 3.8 million SMETS1 devices have been migrated (as of w/e 21 March 2021). BEIS continue to review DMC eligibility and seek enrolment of as many combinations as possible, however some small DMCs may prove uneconomic to progress.
8 | 2021-01-01 | Ash | Data | ESME/GSME/GPF | Range of meter data available over the HAN – currently restricted to just SMETS specified IHD/PPMID data – restricts further use of SM functionality. | Low | Needs clarification of what additional data needs to be accessible. | Suggest TABASC consider when data types identified. | Propose to close | Q3 2021 | For consideration by TABASC. It's thought that there are more than just IHD/PPMIDs able to retrieve data over the HAN i.e. CAD devices and the HCALCS. SECAS will provide further updates in next Issues Log. Will be raised for discussion at Feb 23 Quarterly Call. | There are a number of modifications that may be raised which could help resolve this issue. These have not been formally raised but once they are, SECAS will update Other SEC Parties. We haven’t received any requests for identifying data items and therefore propose to close, but if you are aware of what data items you’d like to see available please inform SECAS or Ash by 6 August 2021. New information suggests that merging requirements for additional data to be added to the HAN, further work is required to clarify this with BEIS.
16 | 2021-01-01 | Tech Ops | Firmware | SMETS | Ability of CSPs/DCC to deliver reliable firmware upgrade capabilities – we have seen meters removed because it’s so difficult sometimes to get the firmware upgrade through, this isn’t acceptable. | High | On Panel 87 agenda – 92% Firmware OTA success rate. | DCC OPSG | In progress | Q2 2022 | 01/04/2021 - The DCC provided an update at the OPSG_46 on 6 April 2021 under agenda item 9. The DCC and CSPN have developed two forward approaches: • Tactical improvement plan. • Enduring architecture uplift plan. To note the Tactical Implementation Plan is targeted to deliver performance as high as 94% by the end of the summer 2021. 21/07/2021: CSP C&S continue to achieve above the Target Service Level for Meter Firmware downloads. The DCC are providing regular updates via the SEC Operations Group and DCC's CSP North Common Issues Forum (CIF) on progress against plan, with performance in June seeing a significant performance increase, although still below the Minimum Service Level expected. A review of the Q2 results against plan will be undertaken at the SEC Ops Group in August. 01/10/2021 - CSP C&S continue to achieve above the Target Service Level for Meter Firmware downloads. The DCC reported that Communication Service Provider North (CSP N) had achieved 78.06% PM2 performance in August, in advance of the remediation plan upper target of 69%. The DCC noted that performance in September had been impacted by configuration issues and had been tracking at approximately 71%. The DCC developed and implemented a change to address the configuration issue on 22 September 2021 and will continue to monitor performance. April 2022 - The DCC reported that CSP N had achieved 98.11% performance for PM2 ‘Percentage of Category 1 firmware payloads completed within the relevant TRT’ in February 2022, against the upper target set out in the remediation plan of 99%. The DCC noted that it is on target to achieve approximately 97% in the February. The OPSG are discussing the outcomes and new steps from the CSP N remediations plans at the 25 April 2022 meeting (OPSG_70). DCC to provide OPSG with the follow up plan to achieve 99% SLA. | Update to be provided following OPSG has undertaken its review. Leave open as of 28 Jul 2022 following quarterly call on PM2 update. Being taken to OPSG 9 Augu 22.
22 | 2021-01-01 | Tech Ops | GBCS/DUIS/DUGIDs | DCC – DSP/CSP/CH/SMETS | Ongoing problems with unproven SRs that fail to complete successfully, e.g., SR4.8.1 | High | This issue refers to some SRs that are fully documented but have not been ‘tested’ sufficiently to confirm end-to-end success in UIT across all of the devices deployed. | DCC SMDA TAG OPSG | In progress | Q3 2022 | 06/04/2021 - The DCC provided an update at the OPSG_46 on 6 April 2021 under agenda item 10. Testing has been undertaken across 4 Meter Manufacturers (MM). Evidence from testing suggests the latest firmware versions improves performance of 4.8.1 SRVs, or that the issue not evident. One MM has accepted an issue and the next steps are for the firmware fix to be tested in UIT to confirm resolution. The DCC are setting up an 'Other User' Common Issues Forum from April 2021 to capture concerns and experiences. 21/07/2021: The OPSG has requested a breakdown of Half Hourly Reads (SRV4.8.1) by DCC User Role (Other Users) as part of the Performance Indicator Reporting which provides Round-Trip-Times for SRVs. Meter Manufacturers outlined that latest firmware versions either have fixes/improvements or planned versions will. Service Users will then need to be encouraged to move their estate to the latest FW versions on the CPL to ensure that this capability is available to all ‘Other Users’. Next ‘Other User’ common issues forum is being planned for July by DCC Service Management. 28/09/2021 - Testing with most meter manufacturers is underway, and Firmware is being released to fix the problem. albeit some may need to make three service requests to get the full 13 months of data (5 months, 5 months, plus 3 months). A full fix should be available next year so that Other Users can make the request in one go. This will take some time to filter through as it will require Suppliers to update the firmware on the assets to enable the Other Users to then make use of the functionality. Fixes are in testing for 3 Meter Manufacturers, whilst the DCC are engaging with 3 other Meter Manufacturers regarding status of fixes and testing. 08/04/2022 - The symptoms exhibited in the ‘Other User Data Retrieval’ SR 4.8.1 issue seem to be reflective of the behaviour displayed in the SR 4.10 (Read Network Data) issue, therefore SECAS believe the root causes are similar in nature (i.e. Larger Response Size leads to lower success compounded with localized volume based on Geographic Location). Both issues are currently tracked via the OPSG Issue Log (#73 - Other User Data Retrieval’, #75 - SR4.10 (DNO Issue)). OPSG members requested both issues are tracked under one issue relating to congestion in the CSP N region. 12/04/2022 - SECAS have reviewed the SEC Operations Risk Register and Issues log and have suggested the following non-Compliances are added to the DCC log of non-Compliances - OPSG Issue #73 - 'Other Party' User type SR 4.8.1 Issue OPSG Issue #75 - SR4.10 (DNO Issue) DCC are currently reviewing against the SEC and will add these non-Compliances if agreed and feed back via SEC Operations Group. 12/04/2022 - DCC to confirm if fix going in for meter type(s) will address this issue or whether the root cause relates to wider read retreaval issues in the CSP N region. This issue will be a confirmed a DCC non-compliance If parties are still unable to retreave the SEC permitted 13 months of read data in one go after the meter manufacturer fixes. | Issue is being tracked via OPSG Issue #73.
17 | 2021-01-01 | Tech Ops | Firmware | SMETS | The ability of suppliers to manage firmware for installed and churned meters to ensure compatibility with the latest DCC CH FW. | Low | Failure to effectively manage FW will result in unnecessary meter removals. Need for an effective Firmware management approach. | TABASC OPSG SSC | Closed | Q3 2021 | Related to Issue 7 and 16. SECAS has drafted a Best Practice Firmware Management guidance document for Users, which is under review by Suppliers before publication. Firmware versions are recorded centrally. IVP and MVP dates are published. 01/10/2021 - SECAS published a Best Practice Firmware Management guidance document for Users on the website in July 2021. Proposing to close as this issue will continuously be looked into. This issue is linked to Issue 17, Issue 24 and Issue 33 which come under the remit of the BEIS-commissioned review of Smart Metering Assurance for SMETS2 Device interoperability. As part of the SMETS2 Device Interoperability Project, SECAS hosted a workshop on 28 September 2021. The workshop was arranged to discuss and agree next steps to address the recommendations in response to the National Audit Office (NAO) Review of ‘Smart Metering Assurance for Device Interoperability on Change’ report. The scope of the workshop was limited to Recommendations 5 and 7: Recommendation 5 - SEC Panel to consider options for increasing monitoring and reporting of device model combinations and interoperability testing. Recommendation 7 - SEC Panel to monitor energy supplier firmware management processes over time and monitor developing commercial arrangements to ensure necessary access to firmware images. The outcomes of the workshop were presented to SEC Panel in October 2021 to agree an approach and next steps to the following actions: - SECAS to split the Problem Statement regarding the proliferation of combinations of Device Models into two statements, one for firmware driven combinations and one for non-firmware. - SECAS to ascertain from the DCC what reporting is possible, and to obtain another set of SMI data to determine the rate of unique combination of Device Models proliferation. - SECAS to refer the longer-term strategic view of the implications of a high volume of combinations of Device Models potentially in relation to asset life to the SWG. - SECAS to obtain a list of Device functions which have not or cannot be tested. 27/10/2021 - Discussed at Quarterly Issues Call and agreed to close the issue on condition the issue is followed, which will happen as SECAS has released a Best Practice Firmware Management guidance document which will require updates and therefor view of the issue | This issue will continuously be looked into.
12 | 2021-01-01 | Joey - Tech Ops | Enrolment and Adoption | SMETS1 | All meters should be enrolled and adopted - maximising the volume of meters made eligible for enrolment by DCC testing AND ensuring that suppliers/DCC enrol all eligible meters and suppliers do not remove eligible meters pre-enrolment. | High | It is a DCC obligation to enrol all ‘eligible meters’, however within the bounds of ‘economic and effective’ considerations. Future innovation should always bear in mind that these assets are costed to last for a long period of time (10-20 years?) | BEIS/TBDG – Transitional Governance | Closed - see issue 11 for details | Q2 2021 | The only interactions with eligibility and the SEC are the Operating Capability reviews and Device Model Combination Testing (DMCT). SECAS suggests that maximising eligibility sits with BEIS, TBDG and the DCC. Please refer to issue 11 which is similar to this issue.
13 | 2021-01-01 | Security? | Triage? | SMETS | Unnecessary removal of working SMETS2 meters and enrolled SMETS1 meters | High | Inability to triage effectively, prior to removal. Consider improvements in in-situ/remote testing to minimise site interventions and wasted visits due to ‘no fault found’ events. | TBC | Open | 2023-09-01 | SSC and BEIS have both been working extremely hard to resolve the outstanding issues with the NCSC and secure their approval for the Security Characteristic review that was completed in Aug2020 and shared with Industry in the Nov20 workshops/CPS industry days. Progress continues to be slow due to new staff in NCSC. A recent workshop in March was held between SSC, BEIS and NCSC to address some of NCSC concerns and progress their outstanding actions from the November workshops. SSC Chair and BEIS were also invited to attend CMAP on 15 April. Further updates pending. (Links to issue 14 and 29) | Closed. Triage issues have been discussed as a priority issue at monthly SCIRS meetings throughout 2022. Updates have been provided in the slides for the 24 February 2023 OSP Quarerly meeting. Discussed this being reassigned, oustanding issues are not security related.
14 | 2021-01-01 | Security | Triage | SMETS2 | The ability to remove working SMETS2 meters and be able to triage and re-use | High | The ability to triage effectively and efficiently to be able to re-use meters is essential to keep smart metering costs down. | SSC, SMKI PMA | Propose to close (once proof of concept observed) | 2023-11-01 | Continuing Uncertainty about the requirements for being able to perform triage and the device requirements presents financial risk to Suppliers and MAPS and presents an ongoing blocker to manufacturers ability to address this issue. The SSC has invited industry to submit Use cases for consideration and held a series of ‘Industry Days’ to develop solutions to problems arising from aborted installs and Devices returned to Suppliers and MAPs. SSC has produced guidance following consultation with industry, BEIS and NCSC of four currently approved use cases to enable devices to be re-furbished. Click this link to find the latest guidance which is available on the SEC website. Any ‘tinkering’ with SMKI Certs is a major security risk since they are there to ensure that no-one can break the trust established between the originator of the Certificate and the device. However, SSC is open to receive further Use cases and there is a methodology published on the website of how to go about it (the process is also in the Use case guidance). (Links to Issue 13 and 29) | Closed. MP203 was raised to help address this issue, and was implemented in the November 2022 SEC Release. Use Cases 1-4 have been defined, helping with guidance around device functionality (established by MP195 and codified). At the last meeting it was agreed to keep this open as parties would like to observe outcomes of the guidance being put into practice and the first Triage Facility Assessemnt being completed successfully.
3 | 2021-01-01 | Tech Ops | HAN | SMS devices | HAN stability issues – many are not visible to DCC. | Medium | Need investigation into the significance and extent of current issues and the risk of future issues. | On the OPSG Issues Log (Issue 69), however the TSIRs HAN/WAN Working Group is leading on the investigation. | Pending (Under Investigation) | Q2 2022 | 28/01/2021: Currently on the OPSG Issues Log (Issue 69), however the TSIRs HAN/WAN Working Group is leading on the investigation. A HAN Stability Tracker (HANST) has been developed by the DCC to report to TSIRs on defects and issues identified by Device and Manufacturer. 16/04/2021: HAN Stability monitoring tracking in place for identified issues under PBI000000118425. The aim is by the end of Q4 2021 to move to BAU processes for ESME HAN stability. Firmware rollout to meters and CHs is expected by the end of Q4. 20/09/2021 - HAN Stability - trend has decreased (from 50997 to 44,733). DCC's aim by the end of Q4 2021 is to move to BAU processes for ESME HAN stability. By the end of the year mass roll out of the CH FW with the stack fixes will be complete and ESME FW with robustness should be in the majority. CH fix upgrades needed with target mass roll out to be completed in Q4 2021. Currently 64% of the SMETS2 ESMEs are on enhanced robust ESME FW. TSIRS and OPSG will continue to monitor until device fixes rolled out. 21/02/2022 - HAN Stability - trend has decreased (from 40,772 to 38,663). | Issue is being tracked via OPSG Issue #69 & at TSiRS. OPSG to monitor until meter defect fixes rolled out
7 | 2021-01-01 | Joey - Tech Ops | Firmware maintenance | ESME/GSME | Maintenance of meters and firmware upgrade on churn – many smaller suppliers/MOPs not resourced to maintain effectively. | Medium | Consideration needed for how meters can consistently and effectively be maintained on CoS, notably how the new supplier can assure that the meters are at a current standard/firmware version. | Suggest TBDG/TABASC to consider. | Pending | Q3 2022 | This likely covers a multitude of areas, including the SMETS2 National Audit Office Interoperability work and recommendations regarding assurance and access to firmware. SECAS is exploring a project of work for a Performance Assurance Framework on meter, firmware and user performance to ensure key standards and requirements are being met. SSC will have an interest in this as it may impact CPA monitoring and decisions to remove devices with expired certificates (an SSC responsibility). Same update as 17 16/04/2021: SECAS have drafted a Best Practice Firmware Management guidance document for Users, which is under review by Suppliers before publication. 29/07/2021: The interoperability work was outlined at the EUA JMM on the 20 April. Best Practice Firmware Guide was published in July 2021 via the SECAS website. 01/10/2021 - This issue is linked to Issue 7, Issue 24 and Issue 33 which come under the remit of the BEIS-commissioned review of Smart Metering Assurance for SMETS2 Device interoperability. As part of the SMETS2 Device Interoperability Project, SECAS hosted a workshop on 28 September 2021. The workshop was arranged to discuss and agree next steps to address the recommendations in response to the National Audit Office (NAO) Review of ‘Smart Metering Assurance for Device Interoperability on Change’ report. The scope of the workshop was limited to Recommendations 5 and 7: Recommendation 5 - SEC Panel to consider options for increasing monitoring and reporting of device model combinations and interoperability testing. Recommendation 7 - SEC Panel to monitor energy supplier firmware management processes over time and monitor developing commercial arrangements to ensure necessary access to firmware images. The outcomes of the workshop are to be presented to SEC Panel in October 2021 to agree an approach and next steps to the following actions: - SECAS to split the Problem Statement regarding the proliferation of combinations of Device Models into two statements, one for firmware driven combinations and one for non-firmware. - SECAS to ascertain from the DCC what reporting is possible, and to obtain another set of SMI data to determine the rate of unique combination of Device Models proliferation. - SECAS to refer the longer-term strategic view of the implications of a high volume of combinations of Device Models potentially in relation to asset life to the SWG. - SECAS to obtain a list of Device functions which have not or cannot be tested. January 2022 - SECAS provided the Panel with the proposed reporting requirements, cost, and timescales for DCC to deliver agreed new reporting. The Panel noted the Problem Statements provided and approved the draft reporting requirements. March 2022 - March 2022 - SECAS have met with DCC to discuss the requirements in more detail and DCC now want to carry out a full impact assessment rather than go straight to delivery. Latest estimate on developing the reports is 3-6 months. | SEC Panel have agreed to the DCC producing reporting to assist with monitoring Firmware Deployment and Firmware management processes. The development of the reports is tracked via the Interoperability Project & OPSG.
4 | 2021-01-01 | Joey - Tech Ops | MWHHS | ESME | Market Wide Half Hourly Settlements (not a SEC Panel issue directly, it is for Ofgem, but the implementation of MWHHS is not yet fully defined/visible). | Unknown | Uncertainty over how the HH data issues will be resolved, and how MWHHS will be implemented/introduced. | Elexon/Ofgem | Closed | Q1 2021 | MWHHS has been discussed at TABASC and OPSG. TABASC wrote to Ofgem on behalf of the Panel. SECAS reviewed whether Business Processes would be covered. | MWHHS has moved on since this action was raised. It has been addressed through liaising with Ofgem and Elexon, 3 official consultation responses and the MWHHS survey.
18 | 2021-01-01 | Joey - Tech Ops | WAN comm’s | DSP | The removal of the 2G/3G network can pose a risk to both SMETS1 and SMETS2. | High | Determine life/economics of 2G/3G services and impact on growing asset base. | TABASC – CH use case OPSG SSC TAG SEC Panel | Closed | Q2 2021 | This concern has been raised by the TABASC and OPSG when reviewing the CH Network project Cost Benefit Analysis (CBA). The OPSG has specifically asked the DCC to consider the implications on the Benefits case for SMETS1 Enrolment and Adoption. | LC13B plan for the Communications Hub and Networks programme sent to IMF members for comment, consultation close on 7 May 2021. DCC will be presenting on the plan at the IMF on 29 April 2021. Concerns regarding the scope, cost and approach should be raised as part of the SEC Panel and Sub-Committee reviews of the next gen comms hubs (4G). BEIS are making the final decision but have sought Panel input into the programme.
19 | 2021-01-01 | Ash | Reporting | DCC | Access to accurate asset reporting from DCC. | Medium | Expecting a consultation to be issued on this shortly. | To be confirmed | Propose to close | Q4 2021 | This has been discussed directly between the DCC and MAPs/Other Users at the moment. Unaware of any SEC Panel/Sub Committee or SECAS engagement on reporting being developed by the DCC on assets yet. DCC consultation has been issued in January 2021on sharing Supplier Party data with Meter Manufacturers and MAP. There has not yet been a response to the consultation. Concerns regarding the scope, cost and approach should be raised as part of the SEC Panel and Sub-Committee reviews of the next gen comms hubs (4G). BEIS are making the final decision but have sought Panel input into the programme. | A consultation has been issued to MAPs. Awaiting output from it. CMAP received an update from DCC a couple in July. The DCC legal advice is that they can’t currently share information like FW versions with MAPs. DCC is suggesting two different ways forward for MAPs: • MAPs approach Ofgem as the Authority to allow DCC to share this information; or • MAPs raise a SEC mod to change the SEC so that data can be shared with MAPs in certain circumstances CMAP has a subgroup meeting arranged for week commencing 2 August to decide next steps. MP181 is covering this issue, and was agreed at July 2022 Change Board and was implemented in the Nov 22 SEC Release.
20 | 2021-01-01 | Ash | Reporting | DCC | Access to Gas data and access to accurate information from Xoserve continues to be difficult despite faster switching | Other Codes | Need to understand the data types and more specific details of the issue. | TBDG Xoserve/Ofgem | Closed | Q1 2021 | Unfortunately this falls outside of SECAS/SEC. If there are Registration Data Provider (RDP) or DCC data issues then they can be raised at the OPSG for investigation.
21 | 2021-01-01 | Ash | Switching service | DCC - CSS | The impact of faster switching on ‘Other Parties’ including MAPs – need to confirm this has a positive impact on data access | Unknown | Determine impacts/benefits on ‘Other parties’. | Elexon | Closed | Q1 2021 | SECAS may be able to raise this as a cross code concern but I would expect that Elexon is best placed to answer any benefits to MAPs from faster switching.
15 | 2021-01-01 | Ali - Change | Install and Commission | SMETS | Industry solution is required to address the availability of the install code on meters that only got part way through Install and Commission before churning | Unknown | Need to address incomplete Install and Commission to allow meters to be operable after churn. | TSiRs/TBDG TABASC OPSG SSC | Closed | Q3 2021 | SECMP121 'Commissioning non-commissioned Devices after CoS' has been raised to look at a process for Installing parties to be able to provide the churned supplier with the install code in the event of partially or incomplete device commissions. 21/07/2021: The Refinement consultation was issued on 11 June 2021 and responses will be discussed at the Working Group on 4 August 2021. 11/10/21: This was approved by October CB and will be implemented in the February 21 SEC Release. 31/03/22: Implemented in Feb 22 Release. Only one month since went live so too early to review success of solution.
23 | 2021-01-01 | Ash | Data | ESME/ Tesla Powerwall | Over-recording of energy demand on some sites where a Tesla Powerwall has been installed | Low | Impacted some users but low volume. | TSIRS TABASC | Closed | Q1 2021 | This may be a TABASC/TSIRS issue as it is related to meter behaviour. It is noted that if this issue may have implications it should be raised/discussed at SEC Panel (or OPSG). | Appears to have been resolved now, unless there are any new instances of ESME/Tesla Powerwall incompatibility events.
24 | 2021-01-01 | Tech Ops | Interoperability/NAO | Device testing | Need to ensure that all users can be confident that all devices are interoperable and can be operated effectively on CoS. | Unknown | Consistent and complete testing to ensure interoperability and interchangeability are assured. | DCC TAG SMDA | In progress | Q2 2022 | The SEC Panel has previously discussed the potential synergy of SMDA becoming a service under the SEC and how this may improve interoperability assurance. SECAS are exploring a Performance Assurance Framework project whereby device interoperability and assurance will be a key objective of the project. 16/04/2021: BEIS have developed a Device Assurance Framework User Guide to support the delivery of fully functional and interoperable devices on Home Area Network (HAN). 21/07/2021: The SEC Section F - Smart Metering System Requirements (F4.3-F4.4) outlines the obligations on Responsible Suppliers for ensuring each Enrolled Smart Metering System are interoperable with the DCC Total System including testing and retaining evidence. 01/10/2021 - This issue is linked to Issue 7, Issue 17 and Issue 33 which come under the remit of the BEIS-commissioned review of Smart Metering Assurance for SMETS2 Device interoperability. As part of the SMETS2 Device Interoperability Project, SECAS hosted a workshop on 28 September 2021. The workshop was arranged to discuss and agree next steps to address the recommendations in response to the National Audit Office (NAO) Review of ‘Smart Metering Assurance for Device Interoperability on Change’ report. The scope of the workshop was limited to Recommendations 5 and 7: Recommendation 5 - SEC Panel to consider options for increasing monitoring and reporting of device model combinations and interoperability testing. Recommendation 7 - SEC Panel to monitor energy supplier firmware management processes over time and monitor developing commercial arrangements to ensure necessary access to firmware images. The outcomes of the workshop are to be presented to SEC Panel in October 2021 to agree an approach and next steps to the following actions: - SECAS to split the Problem Statement regarding the proliferation of combinations of Device Models into two statements, one for firmware driven combinations and one for non-firmware. - SECAS to ascertain from the DCC what reporting is possible, and to obtain another set of SMI data to determine the rate of unique combination of Device Models proliferation. - SECAS to refer the longer-term strategic view of the implications of a high volume of combinations of Device Models potentially in relation to asset life to the SWG. - SECAS to obtain a list of Device functions which have not or cannot be tested. January 2022 - SECAS provided the Panel with the proposed reporting requirements, cost, and timescales for DCC to deliver agreed new reporting. The Panel noted the Problem Statements provided and approved the draft reporting requirements. March 2022 - March 2022 - SECAS have met with DCC to discuss the requirements in more detail and DCC now want to carry out a full impact assessment rather than go straight to delivery. Latest estimate on developing the reports is 3-6 months. | SEC Panel have agreed to the DCC producing reporting to assist with monitoring Device Model proliferation and combinations. The development of the reports is tracked via the Interoperability Project & OPSG.
25 | 2021-01-01 | Ali - Change | Consumer | SMS/DCC | Ensure that any change or release does not adversely impact consumers, or if unavoidable that the risk is accurately assessed. | Unknown | Recognise the importance of the consumer as a key stakeholder, not just for core services but new energy services as they emerge. | Modification WG’s DCC | Closed | Q1 2021 | Energy Consumer impact is now a standard on all new modifications. The OPSG monitors the DCC's Change Management and review whether change resulted in an adverse impact to users and energy consumers. A recent change being trialled is the management of Change during Adverse Weather and protocols to avoid any impact or risk to DCC Users and the Energy Consumers. | Sections added to the mod report which set out consumer impacts, and will be considered for every modification. Please see more information on this here: https://smartenergycodecompany.co.uk/latest-news/enhanced-consumer-benefit-analysis-for-modifications/
26 | 2021-03-01 | Tech Ops | RFI (Radio Frequency Interference) | ESME/CH | Need clarification on the impact on those devices that have failed to meet ICHIS by derogation end date. | Unknown | Creating uncertainty over the action required to address RFI risks for installed Devices. | BEIS/DCC OPSG/DCC | Closed | Q2 2022 | 16/04/2021: OPSG has been reviewed the DCC's developments on RF Noise. The current arrangement is to extend the 'derogation' to March 2022 for devices that meet the relevant RF Noise results (ICHIS and SM WAN Coverage). The OSPG is expecting an update on the DCC Change Request at the May meeting (OPSG_48) DCC and SECAS have sent out a remediation approach for the removal/replacement of devices that are either non-compliant to ICHIS or have been installed incorrectly according to the RF Noise ratings on SMWAN Coverage. 21/07/2021: The DCC Change Request has yet to be finalised. The DCC are looking to provide an update on Derogation Stock rundown rates, non-compliant installs and progress of the CR at the August meeting (OPSG_54) 07/10/2021: The OPSG discussed the progress and update on RF Noise activities at the August meeting (OPSG_54). The OPSG noted the progress on reducing the number of non-compliant meters being installed. The DCC reported that there has been a significant reduction in the weekly installation of non-compliant meters. The DCC noted that under 10% of the meters declared as part of the ICHIS Derogation have been installed so far and highlighted the request for Suppliers to ensure the installation of these Devices by the end of the derogation in March 2022. The DCC reported that it is in discussion with Suppliers regarding remediation plans for installed meters which are not compliant with the derogation. 28/02/2022 - The DCC provided an update on progress made in relation to outstanding derogated stock and non-compliant installs. The DCC highlighted that there was a spike in the installations of non-compliant meters in CSP C&S, however DCC noted that the majority of these were L&G meters which will become compliant following a firmware upgrade. The DCC noted that only 12.17% of the of declared derogated stock had been installed in the agreed derogated locations. The DCC noted that on 31 March 2022 the option to install derogated meters on the network will end. DCC noted that Service Users installing a non-compliant meter after this date will be requested to change the meter or make it compliant to ensure the CSP will support the device. DCC will send out final communications to Users to install declared derogated stock by 31 March 2022. DCC to also identity a process for how non-compliant meters in the triage process will be managed and update OPSG. Has now been implemented. | Issue is being tracked via OPSG Issue #74.
27 | 2021-04-01 | Ofgem issue | Until Government enforces replacement of legacy meters, there is likely to be a long-tail to complete roll-out. | Legacy Meters | Raises questions in particular around continuing to administer PPM under the BSC, and the cut-off or otherwise for the transition to SEC. | Low | Guidance is needed for the AMO amongst other parties, on their responsibilities to maintain legacy equipment beyond the point of economic return. | Authority | Not considered a SEC issue, but can pass it to the Authority for their consideration | Closed |  | If Other SEC Parties believe that SECAS should pass to the Authority for their consideration please contact SECAS@gemserv.com.
28 | 2021-04-01 | Fiona Chestnutt | Transparency of Events of Default | Parties | To look at improving the transparency of Events of Default where Parties have not complied with their SEC obligations. SECAS reports on these monthly to the SEC Panel and the paper is classified as red. | Low |  | SECAS - Party Engagement team | Closed | Closed | Number of Events of Default are currently communicated in the monthly Operations report paper. SECAS has agreed to also communicate the number and nature of defaults in the monthly News bulletin sent to Other SEC Parties.
29 | 2021-04-01 | Security | Triage | SMETS1 | The ability to remove working SMETS1 meters and be able to triage and re-use | High | The ability to triage effectively and efficiently to be able to re-use meters is essential to keep smart metering costs down. Similar to issue 14 but for SMETS1 - the separation will allow the tracking and associated escalation to be noted and communicated. | SSC | Closed |  | SSC introduced a mitigation of not having CPA Certification; a SEC obligation was introduced on DCC last year to undertake independent testing of SMETS1 devices to be enrolled into the DCC. NCC were engaged to conduct independent penetration testing to a scope agreed by SSC and to present the report to SSC. Haven't previously addressed a requirement for triage of SMETS1 enrolled Devices since these are outside the scope of CPA assurance and are subject to SEC obligations on Suppliers in G3.26 to G3.28 SSC has provided individual manufacturers with the Test Lab findings for their own devices so that they are aware of vulnerabilities and we have provided an update to the Agreed Interpretations and reflected in the Security Controls Framework on meeting SEC G3.26 to G3.28 obligations for ensuring security of SMETS1 Devices. | Linked to 14
30 | 2021-04-01 | Security | CPA/NCSC | CPA Governance Arrangements | A concern has been raised regarding potential changes to the CPA governance arrangements which may affect how 'substantive equivalents' and 'product families' may be treated. | High | SSC input. Raised with Gordan Hextall (SSC Chair) | SSC | Open | 2023-11-01 | This issue was escalated to SSC Chair who has been in contact with NCSC on the matter. NCSC have responded but there are still outstanding concerns from the party who raised this issue initially. There is a link to other CPA matters in progress with NCSC and a plea for more transparency regarding the process and the escalation communications being able to be shared with SEC Parties. Further updates pending. | Closed. This and other CPA related issues have been discussed and resolved over the course of the monthly SCIRS meetings in 2022. Agreed at the last meeting to keep this open as one to watch - not currently an issue but could become one and would then be esclated to SCIRS for resolution
31 | 2021-04-01 | Tech Ops - Joey? | P375 | P375 metering | P375 - how will SEC recognise P375 metering and what changes, if any, will be required to accommodate such meters. |  | Change is coming from Elexon. TABASC have been working on this. | Elexon/TABASC | Closed | 2021-04-01 | 01/04/2021 - Requires a BSC sponsored SEC Mod' to develop the necessary changes needed to connect, transact and process SRs and Alerts with P375 meters 01/10/2021 - Workflow from the BSC & Elexon has been completed. Due for implementation July 2022, the BSC have introduced a specification (COP11) which sets out minimum functional requirements for assets which can execute the P375 requirements as stated in the BSC. The TABASC have discussed P375 notably the implementation of the solution and therefore the impacts of that solution on the SEC. A piece of work is underway which looks at if there are any current solution which consolidate both COP11 and SMETS, this study is due to complete in November 2021. | Tracked via TABASC Oct 22 Quarterly OSP Call - Proposed to close and participants agreed for Item 31 to be closed following resolution.
32 | 2021-04-01 | Change and Privacy | Change/Privacy | MDR Role | Issue raised regarding the best option to address the PCF obligations and the introduction of the MDR role. | Medium | Increases the obligations on MDR agents despite being instructed directly by Suppliers and subject to assurance under the BSC. | SECAS to engage with the BSC over how Privacy will be governed and whether there is a need for specific requirements to be included in any Mod Proposal. | Closed | Q3 2021 | The SEC Panel agreed that the Data Privacy aspects of MHHS is a topic that should be discussed under MP162, as part of the full MHHS solution. This requirement has since been included in the MP162 business requirements and is being assessed by the SSC and the Working Group. 27/10/2021 - Was reviewed at Quarterly Issues Call and agreed to be closed as the issue is currently being considered under MP162 'SEC changes required to deliver MHHS'. | MP162 is currently looking at the issue.
33 | 2021-04-01 | Tech Ops | Interoperability | SMETS1 and SMETS2 | Concern raised about the sustainability of the extremely large and growing number of DMCs, both S1 and S2, assuring interoperability and ensuring assets remain serviceable and 'on the wall' for their economic life. | High | Tech Ops are looking at reporting to manage the risk. This has consequences across every release or new service being introduced, notably including CH and Network Evolution. | SECAS | In progress | Q2 2022 | SECAS has been investigating DMC and assurance reporting as part of the SEC Panel NAO Interoperability Recommendations. A workshop is targeted for end of August/early September with Industry Parties, DCC and BEIS to discuss the risk, reporting and next steps. An update will be provided at the September SEC Panel (and subsequently at the next quarterly issues awareness call in October). 01/10/2021 - This issue is linked to Issue 7, Issue 17 and Issue 24 which come under the remit of the BEIS-commissioned review of Smart Metering Assurance for SMETS2 Device interoperability. As part of the SMETS2 Device Interoperability Project, SECAS hosted a workshop on 28 September 2021. The workshop was arranged to discuss and agree next steps to address the recommendations in response to the National Audit Office (NAO) Review of ‘Smart Metering Assurance for Device Interoperability on Change’ report. The scope of the workshop was limited to Recommendations 5 and 7: Recommendation 5 - SEC Panel to consider options for increasing monitoring and reporting of device model combinations and interoperability testing. Recommendation 7 - SEC Panel to monitor energy supplier firmware management processes over time and monitor developing commercial arrangements to ensure necessary access to firmware images. The outcomes of the workshop are to be presented to SEC Panel in October 2021 to agree an approach and next steps to the following actions: - SECAS to split the Problem Statement regarding the proliferation of combinations of Device Models into two statements, one for firmware driven combinations and one for non-firmware. - SECAS to ascertain from the DCC what reporting is possible, and to obtain another set of SMI data to determine the rate of unique combination of Device Models proliferation. - SECAS to refer the longer-term strategic view of the implications of a high volume of combinations of Device Models potentially in relation to asset life to the SWG. - SECAS to obtain a list of Device functions which have not or cannot be tested. January 2022 - SECAS provided the Panel with the proposed reporting requirements, cost, and timescales for DCC to deliver agreed new reporting. The Panel noted the Problem Statements provided and approved the draft reporting requirements. March 2022 - March 2022 - SECAS have met with DCC to discuss the requirements in more detail and DCC now want to carry out a full impact assessment rather than go straight to delivery. Latest estimate on developing the reports is 3-6 months. | SEC Panel have agreed to the DCC producing reporting to assist with monitoring Device Model proliferation and combinations. The development of the reports is tracked via the Interoperability Project & OPSG.
34 | 2021-04-01 | Ash | Compatibility | SMETS1 | Concern over how SMETS1 meters will be made compatible with changing requirements, e.g., EV, DSR, etc., to avoid early obsolescence of SMETS1 SMS. Are all Mods now subject to consideration against the impact on SMETS1 as well as SMETS2? | Medium | SMETS1 will be considered under these changing requirements and dependent upon design and architecture. Not all sits within SECAS but will sit within various programmes such as EV. | DCC/TABASC | Pending | Q4 2021 | SECAS will inform the Strategic Working Group about this issue. | To be discussed at next SWG meeting in September 2022.
35 | 2021-04-01 | Terry | Testing | CH | CH's need to be subject to interoperability testing to ensure compliance. | Medium | DCC CH's updates need to be subject to interoperability testing in order to identify any issues, defects and/or HAN stability issues prior to introduction of new firmware and/or hardware updates. This will also support the recommendations made in the NAO report. | TABASC, DCC and SMDA. Trials have been completed between SMDA and DCC. The DCC are actively looking to 'move left' testing and assurance and SMDA assurance of firmware could aid that ambition. | Propos to close | Q4 2021 | Provisional agreements are in place and expected trials in Q3/4 of this year. DCC and SMDA have completed a proof of concept trial with initial CH firmware update test. It is planned for further CH to be provided for testing by SMDA, within the UIT window. | Who does this action sit best with now Terry has left? CH updates coming through SMDA.
36 | 2021-04-01 | Ali - Change | Privacy | Costs | Concerns over MP144. The current arrangements allow for the sharing of OU Privacy Assessment costs across all users, however this Mod' proposes changing this to each OU being accountable for relevant PA costs. |  | Some OUs are objecting to bearing PA costs on the grounds that they are not significant users and yet would be required to pay a disproportionate cost for the assessment. | Reflect concerns as part of the Mod' working group and consultation. | Closed |  | SECAS noted a reply from an OU to the MP144 Refinement Consultation, which was included in the Modification Report. MP144 has since been approved by the Change Board and was implemented in the Jun 21 Release. | Not to include in update.
37 | 2021-04-01 | Ali - Change | IRP | Device compliance | Concerns over MP143. The decision to incorporate IRP changes in to GBCS v4.x and not earlier GBCS v3.x releases has raised a concern over compatibility between devices which have incorporated some of these changes, but not the full suite of v4.0 changes. | High | How can manufacturers devices maintain compliance when IRPs are introduced alongside other changes for which compliance is not yet required? | SECAS | Closed | Q3 2021 | The SECAS Change Team are seeking your views on this, please email us at sec.change@gemserv.com. This modification is currently being assessed for a Nov 22 Release implementation. 29/07/2021: This has been updated with a number of IRPs and is continuing to progress. 11/10/21: Awaiting return of the PA. 27/10/2021: Taken to Quarterly Issues Call and agreed for the issue to be closed as MP121 has covered this issue and has been implemented. | Included under MP121.
38 | 2021-04-01 | Joey - Tech Ops | Loss of functionality | SMETS1 and SMETS2 | Concern over the rising number of Devices losing comm's and never being recovered. Both S1 and S2. Issue is that devices may be replaced by default as investigation too costly/time-consuming. |  | SECAS has not seen any evidence to suggest that there is a significant issue. May be an issue between Suppliers and MAPs. Can we validate through metrics on the number of non-communicating devices and how this is trending? | SECAS | Pending | Q4 2021 | SECAS and DCC are investigating in Estate Health Reporting that would be include things like communication status. 21/07/2021: BEIS are undertaking a number of workshops through SMDG on Managing Smart Metering Ecosystem Health Best Practice to discuss and agree metrics with Industry on what is considered a 'healthy' system (Meter Reads, Comms times etc). The first workshop will be held on Tuesday 27 July 2021. Suggestion to return to group in Q4 2021 following BEIS led work has completed and outline the recommendations and outcomes. 07/10/2021: BEIS hosted two workshops to discuss 'Post Install Consumer Experience Project' in July and August to discuss and consider reporting and challenges to Ecosystem 'Health'. BEIS have proposed reporting with Suppliers regarding a monthly view at the Smart Metering Delivery Group (SMDG) of: o % of installed SMETS2 meters that are in “commissioned” status o All commissioned SMETS2 or enrolled SMETS1 credit meters where a meter reading was attempted or expected within the last month, % where at least one successful meter reading. o All commissioned SMETS2 or enrolled SMETS1 prepayment meters, % where there has been at least one successful top up within the last month. This will be piloted over Autumn 2021, with the intention of implementing reporting from January 2022.
39 | 2021-04-01 | Joey - Tech Ops | CH | CH | Concern over the risk of unacceptable/non-compliant time-synchronisation in CH. See TSIR report. | Low | This relates to the CHs not complying with the SEC regarding time synchronisation and the risk that errors could occur in the time recording associated with data across devices. | TSIRs | In progress | Q2 2022 | 01/04/2021 - SECAS acknowledges that this is an issue and recommends that the issue is being tracked via TSIRs. Parties can reach out to BEIS to find report. 01/10/2021 - There are two elements to this issue - ensuring Suppliers can identify and resynchronise the clocks when they drift and also ensuring that there are enduring fixes in devices to ensure the issue does not occur on a regular basis. DCC currently investigating the issue and so far have found a small percentage of CH's timeclock drift occurrences with the majority of incidences relating to ESME's. The fix for CSP C&S CH's will be rolled out in the next firmware version however Telefonica have highlighted to the DCC that they believe the main issue may lie within ESMEs. The DCC are to engage with meter manufacturers to investigate further. SECAS to catch up with DCC October 2021 to discuss examples, root cause and remediation plan. 08/10/2021 - The DCC guidance document for Communication Hub Usage was recommended during discussions at TSiRS when Suppliers stated they were not able to get Devices into a 'reliable' time state. The document explains how: • Arqiva CHs update the time; • Telefonica CHs update the time; • Suppliers can reset the time on meters to a ‘reliable’ state. The document is available on the SECAS website at: https://smartenergycodecompany.co.uk/document-download-centre/download-info/dcc-guidance-note-communications-hub-usage-v1-0/ 08/02/2022 - DCC have built new report that covers this issue which is sent to individual Suppliers. 24/02/2022 - DCC are engaging with a Large Supplier with the highest occurences to assist in correcting time clock drift occurences in batches. 24/03/2020 - Time Clock Drift has been shared with both Energy Suppliers and DNOs: • The two Energy Suppliers with the most unresolved time clock drifts have been engaged and actions agreed. • Largest – ADT thresholds have been increased to allow batches of 50,000 which have now commenced. • Second Largest – Have cleared the majority of theirs over the last two weeks. • Conversations will commence with other suppliers. | Issue is being tracked via OPSG Issue #88.
40 | 2021-07-01 | Security | Security Characteristics | Devices | There are currently uncertainties around the Security Characteristic requirements for devices at the point of product re-certification, clarification is needed as this is an emerging risk to Manufacturers and MAPs alike. | Medium | It is unclear if there will be an updated version of SC1.4 and if so what are the timescale. It must be noted that if there any updates these must be available in sufficient time for any required product developments to be established and delivered. This is especially critical where firmware and/or changes or third party stack changes are required. Given that the first recertification’s are due in 2023, clarity needs to be established during Q3 2021 | SSC | Closed | Q4 2021 | Update to be provided in Q4 (next quarterly issues awareness call). | Closed. MP209 has covered this issue and was implemented on 1 August 2022 in ad hoc Release.
41 | 2021-11-01 | Security | Triage fuinctionality | Devices | Continuing lack of clarity over Use Case 4 requirements is delaying manufacturer ability to implement a solution with the effect of increasing unworkable assets at MAP and supplier premises. | High | The implementation and CPA approval timescales are expected to mean that manufacturers wil not get this functionality to market until c.9months after ratification of the specification. At this point there will be siginificant stock without this functionality that cannot be upgraded and decreasign opportunity to redepoly these during the rollout resulting in an increasing likelyhood of scrapped ( but perfectly good) devices | SSC | Closed |  |  | Closed. This and other Use Case related issues have been discussed and resolved over the course of the monthly SCIRS meetings in 2022.
42 | 2022-03-01 | Tech Ops | GBCS/DUIS/DUGIDs | DCC – DSP/CSP/CH/SMETS | Ongoing problems with unproven SRs that fail to complete successfully, e.g., SR4.8.1 - in particular where a Supplier is not returning responses to either DCC or the Other User in question. | High | This issue refers to some SRs that are fully documented but have not been ‘tested’ sufficiently to confirm end-to-end success in UIT across all of the devices deployed. Relates to earlier issues with SR 4.8.1. | DCC SECAS | In progress | Q1 2022 | 16/03/2022 - An Other User raised issues relating to Issue 21 at the Monthly OSP Engagement Call on 16 March 2022. SECAS and OSP Call Chairs acknowledged this and stated they would investigate this. 07/04/2022 - Issue has been escalated to DCC and is currently under investigation. 04/05/2022 - 8.7.2 (SMETS2 join service non-critical SR)has been acting in a similar manner and asked if this is lined.
43 | 2022-09-14 | Tech Ops | TCSO | Devices (namely CHs) | Ongoing problems with the Trust Centre Swap Out (TCSO) process where consumers are having issues and the party who raised the issue is being looked to for resolution, even where the fault lies elsewhere in the process (supplier or installation). | Low | This issue refers to where Devices are "swapped out" and the replacement Device Model Combination has faults, even if the correct process has been followed. | DCC SECAS | In progress | Q4 2022 | 14/09/2022 - An Other User raised the issue at the Monthly OSP Engagement Call on 14 September 2022. SECAS and OSP Call Chairs acknowledged this and stated they would investigate this.
44 | 2022-11-01 | Tech Ops | CH/CAD | Devices | It has been noted that attempting to pair a CAD with Trilliant CHs has been unsuccessfl in multiple instances. Trilliant and the DCC need contacting to investigate and resolve the pairing issue. | Medium | Trying to pair CAD with the Trilliant CH isn't responding. It's an industry wide issue for anyone who has a CAD to pair. | SECAS DCC | In progress | Q1 2023 | 27/03/2023 - DCC & Hildebrand have held talks over the connectivity issues, with DESNZ contacts copied in to communications. DCC have been contacted since for any further updates on this. 3 /05/2023 - DCC has confirmed that a CR has been raised with the Service Provider - CR4774. proof of concept will be undertaken to help determine what an enduring solution could look like and Hildebrand have agreed to support the proof of concept (PoC).
45 | 2023-08-01 | Tech Ops | IHD | Devices | A significant portion of connection attempts, for both display and app, fail. We are blocked by error messages including E101 (bespoke to adapter), E21 and E62(SMETS 1). Investigation via adapter/DCC is slow and information returned is minimal and there has been limited success in getting suppliers to take action on meters where a 'soft' or 'hard' reset has been needed. | Medium | Suppliers need to be contacted to assist where the IHD connection on smart meters appears to be failing. There are commercial implications for inaction, as this could lead to consumers returning purchased equipment from providers. | SECAS, DCC | In Progress | Q1 2024
46 | 2023-09-01 | Tech Ops | CH/CAD | Devices | It has been reported where the are non-functioning Devices in the ecosystem that haven't gone through TCSO. What can happen is that a consumer may inherit a dead Device which needs a lot of time and effort on the part of the affected Parties to fix the issue. This comes as EUIs are still linked to decomissioned CHs. | Medium | Raised when it was noted that the DCC and Trilliant were difficult to get progress on Hildebrand's issues with Trilliant CHs and raised that they had issues with other Devices which other OSPs validated. | SECAS DCC | In progress | Q1 2024

## Acronyms
Acronym | Acronym expanded
CAD | Consumer Access Device
CoS | Change of Supplier
CPA | Commercial Product Assurance
CSP | Communication Service Provider
CSS | Central Switching Service
DBCH | Dual Band Communications Hub
DCC | Data Communications Group
DMC | Device Model Combination
DMCT | Device Model Combination Testing
DSP | Data Service Provider
DUIS | Data Communications Company User Interface Specification
ESME | Electricity Smart Meter Equipment
FW | Firmware
GBCS | Great Britain Companion Specification
GPF | Gas Proxy Function
GSME | Gas Smart Metering Equipment
HAN | Home Area Network
HANST | HAN Stability Tracker
HCALCS | Home Area Network Connected Auxiliary Load Control Switch
ICHIS | Intimate Communications Hub Interface Specifications
IHD | In Home Device
IMF | Impletation Metering Forum
IVP | Installation Validity Period
MAP | Meter Asset Provider
MM | Meter Manufacturers
MVP | Maintenance Validity Period
MWHHS | Market Wide Half Hourly Settlement
OPSG | Operations Group
OTA | Over The Air
PPMID | Prepayment Meter Interface Device
RFI | Radio Frequency Interference
SECMP | Smart Energy Code Modification Proposal
SMDA | Smart Metering Device Assurance
SMDG | Smart Meter Delivery Group
SMKI | Smart Metering Key Infrastructure
SR | Service Request
SSC | Security Sub-Committee
TABASC | Technical Architecture and Business Architecture Sub-Committee
TAG | Testing Advisory Group
TBDG | Technical and Business Design Group
TOU | Time of Use
TSiRs | Technical Specification Issue Resolution Subgroup
UIT | User Integration Testing
WAN | Wide Area Network
WG | Working Group