## Slide 1: SECMP0007 ‘Firmware updates to IHDs and PPMIDs’
Proposer: Robert Williams of E.ON

## Slide 2: Purpose of the meeting
The DCC has provided its draft Impact Assessment response
Noting the TABASC’s comments, we want the Working Group to provide feedback on the overall solution, including the benefits case, before we present the final Modification Report to the Panel
We note that this modification will not be allowed to progress to the Report Phase until:
  The implementation costs have been provided
  Parties have reviewed the legal text

## Slide 3: Agenda
Brief overview of the modification
The Proposed Solution:
DCC’s Impact Assessment
Review of DCC’s firmware distribution control proposals
Legal text
Benefits case assessment
Implementation approach
Next steps
DCC implementation costs

## Slide 4: SECMP0007 summary

## Slide 5: Summary
Currently OTA firmware updates via the DCC can only be made to the CH, ESME and GSME.
The Proposer of this modification seeks to address the lack of capability to update firmware for other mandated Home Area Network (HAN) Devices.
Note, the scope of this modification only applies to SMETS2+ PPMIDs and HCALCS
  Standalone IHDs have been dropped from the Proposed Solution

## Slide 6: PPMID solution
A ZigBee OTA delivery mechanism will be used to deliver firmware images to PPMIDs
A new Service Request (11.4) will be introduced for the PPMID
  This will combine both distribution and activation of the firmware into the Service Request
The firmware will be activated immediately upon successful distribution and a future activation date-time is not permitted.

## Slide 7: HCALCS solution
HCALCSs will utilise the existing OTA firmware update procedure used by ESME and GSME.
This requires a distinct separation between the distribution and activation of the firmware image.
This will be achieved by extending existing SRs 11.1 ‘Update Firmware’ and 11.3 ‘Activate Firmware’ to support HCALCS.
Only the Import Supplier shall be able carry out firmware updates to an HCALCS

## Slide 8: Summary of OTA firmware rules

## Slide 9: OTA firmware rules
PPMID/HCALCS firmware shall only be able to occupy the GSME memory block on the CH, with GSME firmware taking priority
The CH shall hold an Image for at least 14 days before it is discarded (to be agreed on the next slide)
Images shall be no larger than 750KB – firmware requiring more than 750KB shall be fragmented by the User
Future activation date-time is not be permitted for PPMIDs; firmware will be activated upon successful distribution
  For fragmented Images, activation shall occur once the last fragmented Image has successfully been distributed
Activation of HCALCS firmware shall be carried out via a GBCS Critical Command

## Slide 10: CH Image SLA
Recommended approach
DCC have advised that storing the image in the CH RAM will not be feasible
Previous proposal
Once distributed to the CH the Image would initially be stored in the flash memory for up to a week
If the Image had not been sent to the PPMID after one week, it would be moved to the CH Random Access Memory (RAM)
The image would remain in the RAM until the CH reboots or until it is overwritten
We recommend that the Image be held in the CH Flash memory for at least two weeks, instead of one
After two weeks, the image may be permanently deleted

## Slide 11: Proposed Solution – DCC’s draft Impact Assessment response

## Slide 12: SECMP0007, Firmware updates to Mandated HAN devices Presentation at Working Group

## Slide 13: Story and Current Status
2016 – SECMP0007, “Firmware updates to mandated HAN devices” raised. Scope is OTA firmware updates to supplier-provided IHDs and PPMIDs
July 2018, First Preliminary Assessment sent to Working Group, scope extended to HCALCS
February 2019, DCC and Service Provider review of requirements with two solutions proposed:
Original Approach, No GBCS Changes
Extend Proven OTA Firmware Method; create a type 1 IHD and extending PPMID’s, HCALCS, and the new type 1 IHD to support firmware distribution in a manner that would be similar to ESME firmware distribution and activation
July 2019, Working Group agrees to two solutions:
Option 1; for PPMIDs and IHDs
Option 2; for HCALCS
November 2019, Full Impact Assessment returned by two SPs
December 2019, streamlining review with Working Group, Service Providers, and BEIS results in reduced scope
Full Impact Assessment, expect July 2020

## Slide 14: Scope Change for Latest Full Impact Assessment (1-6)
In-Home Displays (IHDs): remove IHDs from scope
Local firmware updates: allow local firmware updates to PPMIDs only
Communications Hub memory block rules: restrict PPMID and HCALCS firmware Images to GSME block of Comms Hub
Comms Hub SLA: remove the requirement for a two-day SLA for an Image to stay on the Comms Hub. The Image will remain until it is overwritten
Comms Hub logging of updates: remove the requirement for the Comms Hub to log the progress of up to 15 Devices in the Upgrade Image list
Firmware updates over 750KB: any firmware updates over 750KB in size must be split into separate Images. Each Image can be no larger than 750KB in size. The Service User must then request distribution of each Image separately.

## Slide 15: Scope Change for Latest Full Impact Assessment (7 onwards)
Future-dated Update Activation: limit firmware updates to immediate activation only.
Service Request for PPMID firmware updates: new SR to distribute and activate PPMID firmware, to facilitate separate Anomaly Detection Thresholds (ADTs) required for PPMIDs.
Alerts and notifications remain unchanged
Dual Supplier Scenarios: in a dual Supplier scenario, both Responsible Suppliers shall be able carry out firmware updates to PPMIDs and HCALCS
11. The PPMID generates the success/failure Alert to the DCC. This removes the following Communications Hub requirements:
to record the activation date-time plus [X] minutes
to subsequently read the firmware version on the Device

## Slide 16: PPMID Volumes (and HCALCS?)
Volumes of PPMID Updates
Stated as a maximum of 2 updates per device per year
Average size 350KB, max 750KB
Variance of +/- 10% over the year
Figures include both CSP regions. CSP South and Central accounts for about 68% (ISFT)
Values based on current ratio of PPMID to CHF
For network loading and infrastructure augmentation, we have assumed that installed base = updateable base. And this will have an impact on eventual costs
volumes per minute
- 15 million PPMID updates over 6 months, with two firmware updates per year
- Even Distribution across each of the 6 months
- Equates to an average of 60 firmware downloads per minute
IDCC Public; SECMP0007 CR211
Notes: Two suppliers have indicated that their PPMIDs in production will work with 7. We believe that 7 will work with some PPMIDS out there

## Slide 17: Other Recent (Minor) Updates and Changes
GBCS, DUIS, and MMC Changes in draft form from SECAS; have started reviews at SMETS2 DA
Change EDMI Comms Hub to retain any image for up to 2 weeks (to be agreed, is a flash memory limitation)
Note that FIAs are based on standalone Mod release, all at once standalone delivery. Discussions, costings, and planning to take place for specific delivery. Release CR will cover testing costs and timelines
Extend GBCS Use Case CS08 to include HCALCS (in GBCS legal text)

## Slide 18: Proposed Solution – DCC’s draft Impact Assessment response
DCC’s Firmware Distribution Control proposals

## Slide 19: Firmware Distribution Control (1): In Progress Check
Device-Based Control: Recommend a per device check to block any firmware distribution request (ESME / GSME / PPMID / HCALCS) for HAN device types where there is one in progress
This prevents excessive repeated downloads from the CSP to Comms Hub – preventing an “accidental Denial of Service”
Extend the error response on SR11.1/SR11.4 to include an error and a list of devices rejected due to “firmware distribution in progress” back to the sender of the 11.1 or 11.4
Validation rule (1) – DSP cannot send another HAN device firmware update to the HAN device until the first update is complete. Return failure code and list of devices
Validation Rule (2) - A device can only stay in the ‘In Progress’ status for a limited time to avoid any erroneous deadlocks, thus allowing Service Users to send new firmware update requests. The tracking timeout will be managed as a configurable duration of time
Needs to be worded in SEC Legal Text drafting, especially for DUIS and consultation with Users. [If the download request is rejected, 11.1 has mechanisms and 11.4 will have per-device validation rules]
Notes: Note shared device information on SSI screen
If supplier eventually gets message of a failure, would they think all updates in a batch would fail?
Fail usually means device is “invalid” and SU doesn’t have to do anything
If there is a need to reset the status of a device manually, itcan be done by the DCC Service Desk by using a new interface provided within the SSMI
Comms Hub can prioritise meter updates over PPMID & HCALCS – so PPMID update can be refused (No retry)

## Slide 20: Firmware Distribution Control (2): Too Busy
Add a CSP “Too Busy” Response to prevent CSP system overload
Proposal to modify existing firmware distribution API used for all HAN devices (not just for ESME/GSME) to notify the DSP if the CSP is unable to process the firmware upgrade request
The CSP would return a “Busy” (http 503?) with a reason code.
DSP currently carries out an immediate web service retry and then carries out a retry every hour for 24 hours followed by a timeout
Proposal is to change the DSP to include provision for an http503 (System Busy) response on the firmware distribution API and for this to invoke the “long retry” design pattern. Recommendation that in all cases the "long retry" design pattern is extended to 4 days
This would need to be agreed before Modification approval.

## Slide 21: Firmware Distribution Control (3); Batch Status
CSP and DSP systems SD 4.4.2 / SD 4.4.1 interface change to notify the status of the firmware download over SMWAN, to support both the individual and batch API status notifications.
Anticipate a high volume of such alert status notifications over the interface and recommendation is for the DSP to implement the batch API option, to potentially minimise the load on both the Telefónica and the DSP systems.
The notification interface is included in the DSP changes, but the DSP had assumed an individual notification for each Device. It’s not a big change to handle a “batch” version with multiple devices notified in one message, but it is a change and will need to be agreed including an upper limit and other non-functional requirements.

## Slide 22: Usage Limitation
Although not directly impacting the Service Providers, we have requested that some form of obligation be documented to limit initial take up and general usage of the firmware download channels.
DUIS Guidance to Service Users that after an initial Service Request that they should wait until they get an alert for a successful or discarded transfer before they resend the SR or send a subsequent Service Request. TABASC suggested that this guidance should be applied to all firmware downloads
After sending a firmware image, the supplier should wait for an activation alert or failure message from the PPMID before re-sending the image update.
A managed schedule should be agreed between the DCC and the appropriate parties. TABASC suggested education better, with “educating users” for users who exceed expectations
A statement that firmware updates must be limited to a gap of at least 5 days between attempts, and be limited to download times of 1 hour or less would reduce the loads on the CSP networks.
Notes: While this is not something that has been in place before, it is something that will have a significant impact on additional infrastructure and resources allocated by the Service Providers to firmware downloads.
ADT relates to CNI and should be security based rather than security load

## Slide 23: Working Group Decision
The Working Group and the Proposer are asked to confirm if they agree to the DCC’s firmware distribution control proposals
Note, the DCC is requesting these proposals be delivered in combination, not in isolation

## Slide 24: DCC implementation costs

## Slide 25: SECMP0007 legal text

## Slide 26: SEC impacts
Schedule 8 'Great Britain Companion Specification'
Schedule 9 'Smart Metering Equipment Technical Specifications'
Schedule 10 'Communications Hub Technical Specifications'
Appendix E 'DCC User Interface Services Schedule'
Appendix R ‘Common Testing Scenarios Document’
Appendix AB 'Service Request Processing Document'
Appendix AD 'DCC User Interface Specification’
Appendix AF ‘Message Mapping Catalogue’

## Slide 27: Ongoing changes
DUIS and MMC will require minor changes following to account for the decisions made on firmware distribution control
Any changes could have minor knock-on impacts to the GBCS
We do not anticipate any further changes to the remaining five documents
All draft changes are available on the SECMP0007 webpage

## Slide 28: Business case assessment
Party feedback

## Slide 29: Feedback
We’ve received feedback from five Parties;
  Two Larger Suppliers
  Three Other SEC Parties
  All five agree that there could be adverse impacts if OTA capability is not made available to PPMIDs and HCALCS;
    Security impacts
    Operational impacts
    Compatibility impacts
    Consumer impacts

## Slide 30: Security impacts
If a security risk/vulnerability is to be found with a PPMID of HCALCS, currently a site visit would be required to resolve
This could lead to all the Devices for a given model/version to be disconnected or suspended
Therefore, OTA capability would provide a significant risk mitigation in this respect

## Slide 31: Operational impacts
There are significant costs for replacing Devices:
  Contact Centre appointment booking costs
  Technician time (1 – 1.5 hrs)
  Replacement PPMID hardware costs
  Triage costs
  Disposal cost if scrapped
One Party estimated that it is a minimum of £75-£90 for each replacement PPMID
  A delivery of 10,000 replacement PPMIDs could therefore cost between £750k-£900k

## Slide 32: Compatibility impacts
Lack of OTA capability could lead to increased compatibility issues
  E.g. when updating legacy PPMID firmware following firmware updates to ESME/GSME or the CH
If these Devices become interoperable the PPMID may need replacing; or
A Comms Hub manufacturer would be required to develop, test and release an update to the Comms Hub

## Slide 33: Consumer impacts
All of the previous impacts will have inevitable impacts on consumers:
  Making time to book site visits
  Disposing of old Devices
  Possible vulnerability of personal consumer information
  Loss of faith in smart metering Devices
  Lack of updates to the User Interface
  SECMP0007 would enable customers that already have these devices to benefit from new or additional functionality that might be delivered through firmware

## Slide 34: SECMP0007 implementation approach

## Slide 35: Delivery Options for SECMP0007
Option Appraisal
Charlotte Semp Programme Director

## Slide 36: Context
  SECMP0007 - once approved, needs to be implemented as quickly as possible
  Objective: Review the Service Providers plans & subsequent delivery options
  Option 1 Do nothing/Mod Rejected
  Option 2 Release in June 2022
  Option 3 Deliver DSP requirement in Nov 2021
  Option 4 Delay Nov 2021 until Feb 2022 & deliver DSP & CSP/TEF

## Slide 37
DCC-CR 211 – Indicative PoaP Delivery Plan – Including Improvement Options
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
M11
M12
M13
M15
M14
M16
M17
M18
M19
M20
M21
2020 / 2021/2022
M22
Project Mobilisation
IT Detailed Design, Build, Unit Test
UIT – 8 weeks
 SIT Exit
 UIT Exit
DCC-CR Change Programme
Go Live
 PIT TAD
SIT 12 weeks
CSP South & Central
19 month implementation plan
Ability to mobilise following SEC Gov Approval
IT Detailed Design, Build
PIT1 SIT1 Test Cycle 1
Delivery of CR1047 (GBCS 3.X)
PIT2 SIT2 Test Cycle 2
UIT – 8 weeks
Go Live
IT Detailed Design, Build, Unit Test
CSP North
19 month implementation plan
Ability to commence Design & Build – cannot start Testing until GBCS 3.x is implemented (est. Jan 2020)
SIT 12 weeks
UIT – 8 weeks
Go Live
 PIT TAD
 PIT TAD
 SIT Exit
 SIT Exit
 UIT Exit
 UIT Exit
DSP
11 month implementation plan
Ability to commence following SEC Gov Approval

## Slide 38: Option 2 –Deliver Everything in Jun 2022
Description: All service providers release capability together in the Jun’22 SEC Release. Nov‘21 SEC Release would deliver other Mods but not SECMP0007 | 
RISKS | BENEFITS
Delay in suppliers benefiting from any Firmware reporting | Release dates are consistent with the SEC Sufficient time to make required operational changes Risk averse programme plan for Service Providers – guaranteed delivery date

## Slide 39: Option 3 -Deliver DSP/CGI requirement in Nov 2021
Description: Deliver the DSP element – reporting on firmware uploads in Nov ‘21 Deliver the CSP element – OTA Firmware to HAN devices in Jun ‘22 | 
RISKS | BENEFITS
Unable to issue any OTA firmware updates to HAN devices until Jun’22 | Release dates are consistent with the SEC Sufficient time to make required operational changes DSP functional requirements for Firmware reporting are delivered in the Nov ‘21 release Risk averse programme plan for CSPs, minimising the risk in not meeting the Jun ‘22 delivery date

## Slide 40: Option 4 -Delay Nov 2021 until Feb 2022
Description: Deliver the DSP & CSP South & Central functionality in Feb ‘22 (60% of the Devices) Deliver CSP North functionality in Jun ‘22 | 
RISKS | BENEFITS
Challenging timescales for CSP South & Central – risk of delay past Feb Unable to issue any OTA firmware updates to HAN devices in the North until Jun’22 Feb System release date is no consistent with the SEC - Might not be able to guarantee a systems delivery date in Feb | Significant number of devices are able to receive firmware from Feb 2022 Potential to include more SECMODs then currently planned in the Nov ‘21 release, creating further efficiencies across the shared SIT and UIT costs Offers sufficient time to make required operational changes

## Slide 41: Next steps

## Slide 42: Next steps
TABASC will further review the DCC’s firmware distribution control proposals on 6 August
SECAS will issue a Request For Information (RFI) to better understand PPMID volumes and those already deployed which could support SECMP0007 functionality

## Slide 43: Thank you for listening
Joe Hehir