## Sheet1
Task Name
Common Milestones (assuming HCALCS & CAD solutions assessed together) | Start | Duration (d) | End
DCC Preliminary Impact Assessment | 2019-01-21 | 21 | 2019-02-11
Working Group Consultation | 2019-03-20 | 28 | 2019-04-17
DCC Impact Assessment | 2019-05-22 | 56 | 2019-07-17
Modification Report to Panel |  | 28
Modification Report Consultation to Change Board |  | 28
Authority Decision |  | 56
Implementation (assume 12 months + time to next Release) |  | 365
HCALCS-CONNECTED ELECTRIC VEHICLE | Start | Duration (d) | End
Activities required for Preliminary Assessment | 2018-12-03 |  | 2019-02-11
High Level Design Requirements | 2018-12-03 |  | 2018-12-31
Agree DNO eligible user for HCALCS commands | 2018-12-03 | 1 | 2018-12-04
Develop high level solution design | 2018-12-03 | 7 | 2018-12-10
Agree HLD with Working Group | 2018-12-10 | 21 | 2018-12-31
Preliminary Impact Assessment | 2019-01-21 | 21 | 2019-02-11
Activities required for Working Group Consultation | 2018-01-02 |  | 2019-04-17
Process & Responsibilities | 2019-01-02 |  | 2019-02-13
Agree limitations of use | 2019-01-02 | 14 | 2019-01-16
Agree HL responsibilities & processes | 2019-01-16 | 28 | 2019-02-13
Develop market arrangements | 2019-01-02 |  | 2019-02-27
Identify potential HL impacts to all Codes (or agree not necessary / critical) | 2019-01-02 | 56 | 2019-02-27
Agree DUIS SRV / Access Control / GBCS amendments | 2019-02-11 |  | 2019-02-18
From Preliminary Impact Assessment | 2019-02-11 | 7 | 2019-02-18
Estimate Benefits | 2018-01-02 |  | 2018-02-27
DNO estimate of benefits | 2018-01-02 | 56 | 2018-02-27
Draft WGC | 2019-02-27 | 7 | 2019-03-06
Agree WGC with working group | 2019-03-06 | 14 | 2019-03-20
Working Group Consultation | 2019-03-20 | 28 | 2019-04-17
Activities required for Impact Assessment | 2019-04-17 |  | 2019-07-17
Collate WGC Responses | 2019-04-17 | 7 | 2019-04-24
Identify WG's preferred option(s) | 2019-04-24 | 21 | 2019-05-15
Agree DCC Impact Assessment Request | 2019-05-15 | 7 | 2019-05-22
DCC Impact Assessment | 2019-05-22 | 56 | 2019-07-17
Activities required for Modification Report to Panel | 2019-08-14 |  | 2019-11-06
Collate IA Responses | 2019-08-14 | 7 | 2019-08-21
Identify WG's preferred option | 2019-08-21 | 21 | 2019-09-11
Draft Modification Report Consultation | 2019-09-11 | 28 | 2019-10-09
Solution Overview | 2019-10-09 | 28 | 2019-11-06
Specification Changes | 2019-10-09 | 28 | 2019-11-06
Benefits Case | 2019-10-09 | 28 | 2019-11-06
Other code changes | 2019-10-09 | 28 | 2019-11-06
Agree MRC with working group | 2019-10-09 | 14 | 2019-10-23
Panel Agree Modification Report | 2019-10-23 | 14 | 2019-11-06
Activities required for Modification Report Consultation to Change Board | 2019-11-06 |  | 2019-12-04
Publish MRC | 2019-11-06 | 7 | 2019-11-13
Submit MRC to Change Board | 2019-11-13 | 21 | 2019-12-04
Activities required for Authority Decision | 2019-12-04 |  | 2020-02-05
Submit modification to Authority | 2019-12-04 | 7 | 2019-12-11
Authority Decision | 2019-12-11 | 56 | 2020-02-05
Activities required for Implementation | 2020-02-05 |  | 2021-02-04
SEC / DCC solution Design, Build & Test | 2020-02-05 | 365 | 2021-02-04
Other code solution Design, Build & Test | 2020-02-05 | 365 | 2021-02-04
Design, build & test other responsibilities & processes | 2020-02-05 | 365 | 2021-02-04
Develop consumer messaging | 2020-02-05 | 365 | 2021-02-04
Manage consumer queries strategy | 2020-02-05 | 365 | 2021-02-04
Develop reporting requirements | 2020-02-05 | 365 | 2021-02-04
Implement Code / System changes (next systems release) | 2021-02-04 | 120 | 2021-06-04
CAD-CONNECTED ELECTRIC VEHICLE | Start | Duration (d) | End
Activities required for Preliminary Assessment | 2018-12-03 |  | 2019-02-11
High Level Design Requirements | 2018-12-03 |  | 2019-01-21
Confirm use of ZigBee attribute for 'shed-load' priority instruction | 2018-12-03 | 1 | 2018-12-04
Develop high level solution design | 2018-12-03 |  | 2018-12-31
Define New SR & Access Controls | 2018-12-03 | 7 | 2018-12-10
Identify available ZigBee Attribute | 2018-12-03 | 14 | 2018-12-17
Define New GBCS Use Case | 2018-12-17 | 14 | 2018-12-31
Agree HLD with Working Group | 2018-12-31 | 21 | 2019-01-21
Preliminary Impact Assessment | 2019-01-21 | 21 | 2019-02-11
Activities required for Working Group Consultation | 2018-01-02 |  | 2019-04-17
Process & Responsibilities | 2019-01-02 |  | 2019-02-13
Agree limitations of use | 2019-01-02 | 14 | 2019-01-16
Agree HL responsibilities & processes | 2019-01-16 | 28 | 2019-02-13
Develop market arrangements | 2019-01-02 |  | 2019-02-27
Identify potential HL impacts to all Codes (or agree not necessary / critical) | 2019-01-02 | 56 | 2019-02-27
Agree DUIS SRV / Access Control / GBCS / CH / CAD amendments | 2019-02-11 |  | 2019-02-25
SRV / Access / GBCS / CH From Preliminary Impact Assessment | 2019-02-11 | 7 | 2019-02-18
CAD amendments | 2019-02-11 | 14 | 2019-02-25
Estimate Benefits | 2018-01-02 |  | 2018-02-27
DNO estimate of benefits | 2018-01-02 | 56 | 2018-02-27
Draft WGC | 2019-02-27 | 7 | 2019-03-06
Agree WGC with working group | 2019-03-06 | 14 | 2019-03-20
Working Group Consultation | 2019-03-20 | 28 | 2019-04-17
Activities required for Impact Assessment | 2019-04-17 |  | 2019-08-14
Collate WGC Responses | 2019-04-17 | 7 | 2019-04-24
Identify WG's preferred option(s) | 2019-04-24 | 21 | 2019-05-15
Agree DCC Impact Assessment Request | 2019-05-15 | 7 | 2019-05-22
DCC Impact Assessment | 2019-05-22 | 56 | 2019-07-17
Manufacturer Impact Assessment | 2019-05-22 | 84 | 2019-08-14
Activities required for Modification Report to Panel | 2019-08-14 |  | 2019-11-06
Collate IA Responses | 2019-08-14 | 7 | 2019-08-21
Identify WG's preferred option | 2019-08-21 | 21 | 2019-09-11
Draft Modification Report Consultation | 2019-09-11 | 28 | 2019-10-09
Solution Overview | 2019-10-09 | 28 | 2019-11-06
Specification Changes | 2019-10-09 | 28 | 2019-11-06
Benefits Case | 2019-10-09 | 28 | 2019-11-06
Other code changes | 2019-10-09 | 28 | 2019-11-06
Agree MRC with working group | 2019-10-09 | 14 | 2019-10-23
Panel Agree Modification Report | 2019-10-23 | 14 | 2019-11-06
Activities required for Modification Report Consultation to Change Board | 2019-11-06 |  | 2019-12-04
Publish MRC | 2019-11-06 | 7 | 2019-11-13
Submit MRC to Change Board | 2019-11-13 | 21 | 2019-12-04
Activities required for Authority Decision | 2019-12-04 |  | 2020-02-05
Submit modification to Authority | 2019-12-04 | 7 | 2019-12-11
Authority Decision | 2019-12-11 | 56 | 2020-02-05
Activities required for Implementation | 2020-02-05 |  | 2021-02-04
SEC / DCC solution Design, Build & Test | 2020-02-05 | 365 | 2021-02-04
Other code solution Design, Build & Test | 2020-02-05 | 365 | 2021-02-04
Design, build & test other responsibilities & processes | 2020-02-05 | 365 | 2021-02-04
Develop consumer messaging | 2020-02-05 | 365 | 2021-02-04
Manage consumer queries strategy | 2020-02-05 | 365 | 2021-02-04
Develop reporting requirements | 2020-02-05 | 365 | 2021-02-04
Implement Code / System changes (next systems release) | 2021-02-04 | 120 | 2021-06-04
Formulas:
Start = MIN([Start, row below]:B17)
Start = [Start, row above]
End = [Start]+[Duration (d)]
End = MAX([End, row below]:D17)