SEC Modification Proposal, SECMP0104, DCC CR4112

Security Improvements

Full Impact Assessment (FIA)

| Version: | 1.0 |
| --- | --- |
| Date: | 2nd August, 2021 |
| Author: | DCC |
| Classification: | Public |

Contents

1	Executive Summary	4

2	Document History	5

2.1	Revision History	5

2.2	Associated Documents	5

2.3	Document Information	5

3	Solution Requirements and Overview	6

3.1	Problem Statement	6

3.2	Business Context and Requirements	6

4	Solution Overview	8

4.1	Part 1, Report Service Users not Using XML Signing Certificates	8

4.2	Part 2, Enforce XML Signing Certificates by Validation Checks	8

4.3	Impact on DSP Component	8

4.3.1	Security Library	8

4.3.2	Message Gateway	9

4.3.3	Request Management	9

4.3.4	Data Management	9

4.3.5	Reporting Application Server	9

4.3.6	Technical Specifications	9

4.3.7	Service User Certificate Usage Report Format	10

4.3.8	Feature Switches	10

4.3.9	Non-Functional Impacts	10

5	Testing Considerations	11

5.1	Pre-Integration Testing	11

5.2	System Integration Testing (SIT)	11

5.3	User Integration Testing (UIT)	12

6	Implementation Timescales and Releases	13

6.1	Change Lead Times and Timelines	13

6.2	SEC Release Allocation and Other Code Impacts	13

6.3	Costs and Charges	14

6.3.1	Application Support Costs	14

6.3.2	Changes to the DSP Contract	15

Appendix A: Risks, Assumptions, Issues, and Dependencies	16

Risks		16

Assumptions	16

Issues	16

Dependencies	16

Appendix B: Glossary	17

# Executive Summary

The Change Board are asked to approve the following:

- Total cost to implement SECMP0104 of £494,878 which comprises:

  - £360,992 in Design, Build and PIT costs

  - £133,886 in release costs (SIT, UIT, TTO and Systems Integration)

- The timescale to complete the implementation of ten (10) months

- Include SECMP0104 Part 1 in the December 2021 Maintenance Release and Part 2 in the June 2022 SEC Systems Release

Problem Statement

The Security Sub-Committee (SSC) is concerned that it is possible for Service Users to use Smart Meter Key Infrastructure (SMKI) Keys to sign Service Requests as well as the Pre-Command. The Proposer on behalf of the SSC wishes to introduce new checks within the DCC Total System to check that a User Role Signing Private Key is being used to sign XML format service requests and a separate signing Key is being used for communication with Devices.

In addition, the Enduring Change of Supplier (ECoS) solution to be implemented in June 2022 will require the use of XML Signed Service Request 6.23 messages. Currently there is neither a mechanism to track the certificates used by Service Users to sign the Service Requests nor the ability to block access for non-compliant parties.

SECMP0104 will add functionality to:

- Enable production of a monthly report to the SSC of Users who are not using the private keys associated with a public key that is contained within an Organisation Certificate that has a Remote Party Role of “xmlSign” to Digitally Sign the XML Wrapper. This will be required when SECMP0104 is implemented, and the report will be provided prior to the full implementation. Once the second part of SECMP0104 is implemented, there is no further requirement to produce this report.

- Provide the ability to enforce the mandatory use of a User Role Signing Private Key for every XML format Service Request and Signed Pre-Command sent to the DCC.

Benefit Summary

The Modification will ensure the proper application of the SEC security arrangements, help support the security controls framework, and meet the ECoS requirements for mandatory XML signing.

# Document History

## Revision History

| Revision Date | Revision | Summary of Changes |
| --- | --- | --- |
| 21/06/2021 | 0.1 | Initial compilation |
| 01/07/2021 | 0.22 | Completed DCC internal review, minor typos |
| 02/08/2021 | 1.0 | Reviewed costs |

## Associated Documents

This document is associated with the following documents:

| # | Title and Originator’s Reference | Source | Issue Date |
| --- | --- | --- | --- |
| 1 | MP104 Modification Report | SECAS | 26/11/2020 |
| 3 | SECMP0104 CR4112 - PIA – Security Improvements 1.0 | DCC | 12/02/2021 |

## Document Information

The Proposer for this Modification is Gordon Hextall on behalf of the Security Sub-Committee (SSC). The Modification was previously titled "XML Signing Key".

The Preliminary Impact Assessment was requested of DCC on 26th November 2020. It was completed on 2nd February, 2021. A Full Impact Assessment was requested on 5th May, 2021.

# Solution Requirements and Overview

In this section, the context of the Modification, assumptions, and the requirements are stated.

The problem statement and requirements have been provided by SECAS and the Proposer.

## Problem Statement

SEC Appendix AD ‘DCC User Interface Specification’ (DUIS) section 3.3.1 states that Users shall Digitally Sign every XML format Service Request and Signed Pre-Command sent to the DCC using a User Role Signing Private Key.

That User Role Signing Private Key must be a separate dedicated Key that must not be used for communication with Devices (i.e. different to that used to sign the Great Britain Companion Specification (GBCS) Payload held within Signed Pre-Commands), and a separate User Role Signing Private Key must be used per User Id in use for each User.

Each User shall notify the DCC of the Smart Metering Key Infrastructure (SMKI) Organisation Certificate corresponding to each User Role Signing Private Key that they wish to use for Digitally Signing communications to the DCC. DCC Service Users are required to Digitally Sign XML format Service Requests and Signed Pre-Commands  with a User Role Signing Private Key, which must be a separate dedicated Key not to be used for communication with Devices.

The Security Sub-Committee (SSC) is concerned that it is possible for Service Users to use Smart Meter Key Infrastructure (SMKI) Keys to sign Service Requests as well as the Pre-Command. There is no mechanism today to track the credentials used by Service Users to sign the Service Requests or an ability to block access for parties that do not comply.

## Business Context and Requirements

This Modification seeks to enable DCC systems to apply controls to ensure that a DCC User has used separate XML User Role Signing Private Keys to Digitally Sign each Service request and the GBCS Payload held within Signed Pre-Commands.

This business requirements for this Modification have been aligned with the Department for Business, Energy & Industrial Strategy (BEIS) requirements, which require DCC system changes to enable these specific changes:

- Changes involving XML Signing Certificates for DCC Users that BEIS consulted on in January 2020

- Changes proposed by BEIS related to how Change of Supplier (CoS) Update Security Credentials Service Requests should be processed as part of the ECoS arrangements

Part of the BEIS ECoS proposals is for Market Participant IDentifiers (MPIDs) to be included within the subject common name field of XML signing certificates issued to suppliers. These MPIDs are planned to be used as part of the processing checks applied to CoS requests under ECoS. This is to enable the relationship between supplier and an MPID to be capable of being defined based solely on whether an MPID (Market Participant) is included within the XML signing certificate of a supplier.

The following table lists the requirements for this Modification and identifies the impacts on various functions.

| Req. | Requirement | DSP | Suppliers | Security Sub-Committee |
| --- | --- | --- | --- | --- |
| 1 | The DCC shall check that the User has used an XML User Role Signing Private Key that is associated with a Public key that is contained within an Organisation Certificate that has a Remote Party Role of “xmlSign”, to Digitally Sign the XML wrapper of each Service request and Signed Pre-Command. |  |  |  |
| 2 | The DCC shall cease processing the communication if the User has not complied with Requirement 1. |  |  |  |
| 3 | The DCC shall notify the User if the DCC ceases to process a communication as per Requirement 2. |  |  |  |
| 4 | Before the implementation of Ref 1-3, the DCC shall provide a monthly report to the SSC of: - Users who are not using the private keys associated with a public key that is contained within an Organisation Certificate that has a Remote Party Role of “xmlSign” to Digitally Sign the XML Wrapper as will be required when Ref 1 is implemented. Once Requirements 1-3 are implemented, there are no further requirements for this report to be produced. |  |  |  |
| 5 | The Implementation of Requirements 1-3 is expected to align with the start of the operation of the ECoS function to reduce implementation complexity for Users and DCC. DCC should manage the communication of the requirement for Users to use keys associated with XML Signing certificates alongside communications already planned for ECoS implementation. |  |  |  |

Table 1: Business Requirements and Impacts for SECMP0104, CR4112

Although not specifically stated in the requirements, this solution will be applied to SMETS1 and SMETS2 Devices.

# Solution Overview

Changes to the DSP are required for this Modification solution.

The solution can be divided into two sections of functionality as shown in the following sections.

  - Part 1, Report Service Users not Using XML Signing Certificates

DSP will build a mechanism to track the certificates used by the Service Users to sign Service Requests. The tracking information will be stored in a separate table in Volt DB, created specifically for this purpose. This data will be used to generate a monthly report that contains the certificates used by the Service Users during a given month. It will be delivered to the SSC only.

The report will contain the following fields.

•	Service User ID

•	Certificate Serial Number

•	Certificate Role

•	Latest time of use

Note that DCC Data Systems already supports usage of XML Signing certificates and the Service Users are currently allowed to send the Service Requests signed in this way. However, the usage of XML Signing certificates is not yet compulsory.

The mechanism for reporting the certificates used by Service Users should be made available well in advance of enforcing the new validation checks, in order to identify who is not yet using XML Signing certificates. The Part 1 solution on its own does not need to be part of a SEC Release, and is expected to be delivered by an earlier maintenance release at least six months ahead of the Part 2 delivery, potentially in December 2021.

## Part 2, Enforce XML Signing Certificates by Validation Checks

To support the core functional requirements, DSP will amend the Service User validation checks to verify that the Service Request submitted by a Service User has been signed using an XML Signing Certificate. If the validation fails, DSP will reject the Service Request using a new error code E65 specifically for this scenario. If the Service User uses a version of DUIS that does not support the new error code, they will be notified using the existing error code E100.

The DUGIDS/DUIS documentation and DUIS XML schema changes required to support the new error code E65 will be part of the DUIS version 5.1 documentation. Part 2 of this Modification will go live as part of a SEC Release that includes DUIS uplift to version v5.1.

Note: The solution presented here assumes that the new XML Signing certificates are only for the use of DCC Service Users, not for DCC Parties, and that DSP will therefore continue to use Organisation Certificates in the Role of Access Control Broker (ACB) for signing XML messages.

## Impact on DSP Component

The following sub-systems and components of the DSP are impacted by this change.

### Security Library

A Security Library within DSP will perform the validation check to determine whether the Service Request has been signed using an XML Signing Certificate.

Once the use of XML Signing certificates is enforced (part 2), this validation will return either a ‘SUCCESS’ or ‘ERROR’ status.

Before the use of XML Signing certificates becomes enforced, if the XML Signing certificate validation check fails then the Security Library will return a ‘WARNING’ instead of ‘ERROR’.

### Message Gateway

Message Gateway will invoke the XML Signing validation check by calling the Security Library. If the response from the Security Library is ‘ERROR’, then Message Gateway will return the Response Code E65 or E100 to the Service User and terminate the Service Request processing. If the response is ‘SUCCESS’ or ‘WARNING’, then the Service Request will be forwarded to Request Management for further processing.

### Request Management

When the Request Management component repeats the signature check, the XML Sign check will also be repeated. If the response received from the Security Library is ‘SUCCESS’ or ‘WARNING’, then Request Management will continue to process the request.  In all cases Request Management will record the details of the Service Request (e.g. Service User ID, Certificate Used, Timestamp etc.) in a tracking table. This will be used to create the Service User Certificate Usage Report.

### Data Management

A custom program module that handles creation of the Service User Certificate Usage Report and transfer of the same to Reporting Application Server will be created and scheduled to run within the Data Management container. It will be also possible to invoke this program manually on a need basis.

### Reporting Application Server

Reporting Application Server will be amended to add support for the Service User Certificate Usage Report.

### Technical Specifications

DUIS and DUGIDS documentation will be updated to describe the error code associated with the XML Signing validation check as described in the table below.

| Response Code | Response Code Name | Response Code Type | Description | Applicable to Response Types |
| --- | --- | --- | --- | --- |
| E65 | Failed Validation – Service User / Certificate mismatch | Error | The Service Request is not signed using an XML Signing Certificate (Remote Party Role ‘XMLSign’) | Acknowledgement |

The DUIS Schema will be updated to include the new error code as shown by the change barred sections in the following document.

Other design and solution documentation will be developed during the Detailed Design and Development phases.

### Service User Certificate Usage Report Format

The Service User Certificate Usage Report will contain the following fields, in addition to the header and footer applicable to the Enterprise Systems Interface (ESI) reports. This report will not be encrypted.

- Service User ID

- Certificate Serial Number

- Certificate Role

- Latest time of use

The actual definition of the report format will be finalised during the design phase.

The Service User Certificate Usage Report will be signed by DSP in line with the existing ESI report delivery procedures. This report will not be encrypted.

### Feature Switches

The functionality associated with this Modification will be set by two new feature switches; one for adding the XML Signature check capability and the other for enforcing the usage of it.

Although this adds a level of complexity to the design and testing, it is necessary due to:

- The requirement to turn reporting on and off

- The dependency on the delivery of the ECoS release

### Non-Functional Impacts

The following non-functional changes to the DSP have been identified or discounted.

| Performance | DSP does not expect that there will be a material impact on system performance as a result of this change therefore no performance testing costs have been included. |
| --- | --- |
| Resilience | No change to the system resilience solution as a result of this change. |
| Disaster Recovery | No change to the Disaster Recovery solution or BCDR procedures |
| Security | The DSP Security Assurance team has reviewed this change. No additional Penetration Testing is required |
| Data processing, storage and/or transmission | This Modification does not materially increase processing, data storage or data exchange within the DSP solution. |
| Interfaces | None |
| Infrastructure | None |

# Testing Considerations

This Full Impact Assessment includes the cost to develop, fully test and deliver this SEC Modification.

## Pre-Integration Testing

The DSP PIT team will design and implement the functional updates required to the DSP for the change. As noted previously, the changes will be delivered in two parts:

- Part 1, report the Service Users who use Non-XML Signing Service Requests, to be delivered by way of a maintenance release.

- Part 2, enforce the use of XML Signing Service Requests by adding new validation checks, could be delivered in line with the implementation of the ECoS release. The DSP team will support a PIT complete / exit for this change, including a Factory Acceptance Test delivered to DCC Test Assurance.

Historically there is a level of testing required by the Test Advisory Group (TAG) for any DUIS upgrade. Should the DUIS change contain only the addition of the new DCC Alert as described in this FIA then this would be a minor change to DUIS. However for this FIA, an assumed level of testing representative of previous releases for the DUIS upgrade is included. A more targeted level of regression (i.e. a level lower than the Industry has insisted on previously), would be sufficient if the DUIS release contains only this change. Equally, there would be an efficiency achieved if the testing associated with this change was tested as part of a wider release. Both possible efficiencies would require less testing and result in lower costs.

Once PIT Complete status is achieved, the PIT team will support post PIT activities in the form of technical support and defect fixes to allow DSP to achieve its test exit obligations.

The updates to the DSP system and the timing of the PIT exit will be agreed with the DCC through updates, submission and review of the Solution Design documents.

## System Integration Testing (SIT)

The full scope of SIT within this Modification will consist of:

- SIT Preparation activities, including development of the Heat Map

- Solution Testing with SMETS1 and SMETS2 devices

- DCC test witnessing during Solution Test

The charges for SIT activities provided within this Full Impact Assessment include:

- All the test preparation activities

- Functional Testing

- Updates to the Automation Framework

- SIT Management and Assurance

- DCC support and liaison with DCC delivery and assurance authorities

- Test Reporting, including the completion reporting specific to this Modification

Note that SIT test automation has been significantly increased as part of the Modification costs, reducing the time and costs associated with this phase of testing.

## User Integration Testing (UIT)

The complexity of integration testing is low. SECMP0104 impacts the sending of all SRVs if Service Users do not sign requests with an XML Signing certificate. Therefore, all Service Users configured in each UIT Service User Simulators will require new XML Signing certificates to be created and configured.

# Implementation Timescales and Releases

The full Modification was expected to be included in a SEC Release in June 2022. Implementation timescales will be finalised as part of the relevant SEC Release Change Request.

## Change Lead Times and Timelines

From the date of approval (in accordance with Section D9 of the SEC), to implement the changes proposed DCC requires a lead time of approximately ten months.

The broad breakdown of the testing regime is shown in the following table in months after an approval decision date (D).

| Phase | Duration |
| --- | --- |
| SECAS agreement on scope of release |  |
| CAN signature | D + 1 Month |
| Design, Build and PIT Phase | 4 Months |
| SIT and UIT Phase (functional changes only), aligned with Release Dates | 5 Months |
| Transition to Operations and Go Live | D + 10 Months |

Generation and production of the Part 1 report is likely to be completed within two months of SECAS agreement.

## SEC Release Allocation and Other Code Impacts

The allocation to any release may be dependent on other Modification timings and the suitability of a release. No functionality overlap with other Modifications has been identified, beyond DUIS regression testing as mentioned in section 5.1.

## Costs and Charges

This section indicates the quote for all phases of application development stage for this Modification. Note these costs assume a release of just this SEC Modification without any other Modifications or Change Requests in the release, which is not truly reflective of what the post-PIT test costs or programme duration will look like. A calculation of those costs will be carried out when the contents of the future Release are finalised, and the post-PIT costs determined through a "Grouping CR" also referred to as a "Release CR".

| £ | Design, Build, and PIT | Integration Testing, SIT and UIT | TTO | Total |
| --- | --- | --- | --- | --- |
| SECMP0104 | 360,992 | 66,230 | 67,656 | 494,878 |

| Design | The production of detailed System and Service designs to deliver all new requirements. |
| --- | --- |
| Build | The development of the designed Systems and Services to create a solution (e.g. code, systems, or products) that can be tested and implemented. |
| Pre-Integration Testing (PIT) | Each Service Provider tests its own solution to agreed standards in isolation of other Service Providers. This is assured by DCC. |
| Systems Integration Testing (SIT) | All the Service Provider's PIT-complete solutions are brought together and tested as an integrated solution, ensuring all SP solutions align and operate as an end-to-end solution. |
| User Integration Testing (UIT) | Users are provided with an opportunity to run a range of pre-specified tests in relation to the relevant change. |
| Implementation to Live (TTO) | The solution is implemented into production environments and made ready for use by Users as part of a live service. |

As part of the DCC negotiation with the DSP regarding the Contract Extension, some governance charges may be reduced for post-PIT phases. The negotiation is expected to be completed in October 2021.

As noted above the testing costs include a full regression test of DUIS. This will be reduced as part of the June 2022 Release including Modifications with other DUIS changes and/or targeted regression testing, if agreed by the TAG.

### Application Support Costs

Application Support costs have been calculated for the period after Part 1 of the solution is implemented, and are referred to as Early Life Support.

Application Support costs after Go Live for Part 2 of the solution, with Part 1 switched off, are calculated for the 12 months after Go Live.

| Early Life Support | £13,124 |
| --- | --- |
| Application Support | £27,666 |

### Changes to the DSP Contract

The contract updates will be detailed within the CAN and will impact the following schedules:

- Schedule 2.1: Review to determine whether updates are required as a result of the new functional requirements outlined within this FIA

- Schedule 4.1: Solution Design documents will need to be updated

# Appendix A: Risks, Assumptions, Issues, and Dependencies

The tables below provide a summary of the Risks, Assumptions, Issues, and Dependencies (RAID) observed during the production of the Full Impact Assessment. DCC requests that the Working Group considers this section and considers any material matters that have been identified. Changes may impact the proposed solution, implementation costs and/or implementation timescales.

## Risks

| Ref | Description | Status/Mitigation |
| --- | --- | --- |
| MP104-R1 | If the devices for testing are not delivered on time, there is a high risk that testing will be delayed, which will incur additional costs. | Accepted |
| MP104-R2 | If Service Users do not change their systems in advance of go live which could result in a delay in making the functionality available within Production or result in some Service Users being unable to send certain requests. | Accepted |
| MP104-R3 | Part 1 Reporting functionality should be delivered before the end of 2021, at least 6 months prior to Part 2 Go Live. | Accepted |

## Assumptions

These assumptions have been used in the creation of this Full Impact Assessment. Any changes to the assumptions may require DCC to undertake further assessment, prior to the contracting and implementation of this change.

| Ref | Description | Status/Mitigation |
| --- | --- | --- |
| MP104-A1 | SECMP0104 will be included in the June 2022 SEC Release. The price breakdown, and work start-date is based on the June 2022 Release. | Accepted |
| MP104-A2 | The solution assumes the new XML Signing certificates are only for the use of DCC Service Users, not for DCC Parties, and that DSP will therefore continue to use Organisation Certificates in the Role of ACB for signing of XML messages. | Accepted |

## Issues

None at this time.

## Dependencies

None at this time.

# Appendix B: Glossary

The table below provides definitions of the terms used in this document.

| Acronym | Definition |
| --- | --- |
| ACB | Access Control Broker |
| BCDR | Business Continuity and Disaster Recovery |
| BEIS | Department for Business, Energy & Industrial Strategy |
| CAN | Contract Amendment Note |
| CoS | Change of Supplier |
| CR | DCC Change Request |
| DCC | Data Communications Company |
| DSP | Data Service Provider |
| DUGIDS | DCC User Gateway Interface Design Specification |
| DUIS | DCC User Interface Specification |
| ECoS | Enduring Change of Supplier |
| ESI | Enterprise Systems Interface, a file format |
| FIA | Full Impact Assessment |
| GBCS | Great Britain Companion Specification |
| GFI | GBCS Integration Testing For Industry |
| GSME | Gas Smart Metering Equipment |
| MPID | Market Participant Identifier |
| PIA | Preliminary Impact Assessment |
| PIT | Pre-Integration Testing |
| RAID | Risks, Assumptions, Issues, and Dependencies |
| ROM | Rough Order of Magnitude (cost) |
| SAT | Service Audit Trail |
| SEC | Smart Energy Code |
| SECAS | Smart Energy Code Administrator and Secretariat |
| SIT | Systems Integration Testing |
| SMETS | Smart Metering Equipment Technical Specification |
| SMKI | Smart Meter Key Infrastructure |
| SP | Service Provider |
| SSC | Security Sub Committee |
| SSI | Self Service Interface |
| TOC | DCC Technical Operations Centre |
| TTO | Transition to Operations |
| UIT | User Integration Testing |
| XML | eXtensible Markup Language |

The DCC will notify the SSC if the DCC ceases to process a communication.