## Slide 1: CSP.N Service Scaling and Optimisation
TABASC90_0106

## Slide 2: The Ask
Update - CSP.N Service Scaling and Optimisation - Phase 2
To provide TABASC with a progress update on the next steps for S&O Phase 2
To outline a DCC proposal for a Scheduled Read Window extension trial
For Information – Update and direction of travel for S&O Phase 2
For Discussion – Proposal for Scheduled Read Window extension trial, with input being considered before the trial concept is taken to OPSG for endorsement in June

## Slide 3: CSP.N Scaling and Optimisation – Progress Update and next steps
Non-Technical Operational Options
Scheduled Read Window - Review underway (Trial proposal prepared for discussion with customers)
Summary: Channel Expansion updates to the Radio Network remain on track and agreement has been reached to accelerate Impact Assessment work on identified additional E2E capacity risks associated with wider solution components.
Radio Network
Channel Expansion from 4 to 6 (to mitigate immediate dense cell risk) in progress and now part of BAU Operations
  The highest loaded 290 TKs across the CSP.N Region have now been updated.
  Additional TKs will be updated as and when required as part of a monthly review process.
Option 1 - Increase in RF Channels
  Development of new Channel Plan to extend beyond 6 Channels to 12 Channels per TK remains on track for delivery and implementation, where required, in September ’23.
Option 4 - Modulation Rate Increases to 4FSK
  Impact Assessment in progress. Dependency on Option 11 IA, so response delayed until November 2023.
  Note: Whilst it is currently expected that 4FSK is not required until the number of connected Premises exceeds 5.8m it is noted that it will offer additional performance benefits and as such might be considered regardless of scaling requirements. Within the IA, costs will be split between:
    Part 1: Development of 4FSK and the associated functionality to manage the dual modulation environment.
    Part 2: Uplifting the capacity of the RNI to support >5.8m Premises.
Other CSP.N solution components
RNI Scale Testing underway and due to complete by end July ’23 (which will validate capacity risk timeline).
Option 11 - E2E CSP.N Solution capacity to support RAN increases
  Scope of the RNI Capacity Uplift Impact Assessment agreed between DCC and Arqiva, and PO issued. Response expected September ’23
  IA due to happen in parallel with RNI Scale Testing and not wait for RNI Scale Testing to conclude to reduce analysis timeline
Technical Options
RISKS & ISSUES
RNI Capacity risk identified from Q4 ‘23 (based on forecasted 2.8m connected Premises) through to implementation of RNI Uplift (estimated somewhere between late ‘24 and mid ’25 – subject to IA).
Risk profile to be further validated by the RNI Scale Testing Activity.
Mitigation 1: RNI Impact Assessment accelerated and now planned to happen in parallel with Scale Testing (previously sequential activity).
Mitigation 2: Non-Technical option – Extend Scheduled Read Window to be further discussed / analysed.

## Slide 4
End-to-end Capacity: The Arqiva solution can be split into two key groups of components, the RNI (the green box below) and the Radio Network (the purple box below). Whilst the Channel Expansion (Option 1) will increase the throughput capacity of the Radio Network, the components within the RNI also need to be uplifted (Option 11) to align E2E Solution Capacity.
Enhancements to the Radio Network creates additional capacity at a localised level and mitigates the risk of dense cells, whereas enhancements to the RNI increase the overall capacity at a centralised level and mitigates the risk of total system overload/failure.
Option 1: Channel Expansion
Option 11: RNI Uplift
Option 4: 4FSK Modulation

## Slide 5: CSP.N S&O - Development Roadmap – RNI Scale Risk
Comms
Hubs
3.2m
10.5m
Increase to 6 RF Channels per TK
Radio Network Capacity Increases
5.8m
NOW
2.3m
Option 4
Modulation Rate Increase
7.5m
6.8m
Pending IA
RNI Scaling
Operation of existing RNI version (with NMS)
4.1m
Increasing Risk
Option 1
Increase to 12 Channels per TK
Current Best Guess Level
- Confirmed by RNI Scale Testing IA
Option 11
Phase 0&1
Wider CSP.N solution
component Uplift
Defines Benefits of ALL Phases 0,1,2
Lowest Expected Value
Level 1 – Existing Limit to be confirmed by RNI Scale Testing IA
TBC - Other
Technical Options
Level 2 – Updated Expected Base limit to be confirmed by RNI Scale Testing IA
RNI Scale
Testing
CB-6.7
NCS + RNI (CB-7.0)
CB-6.7.6
Patch Release
CB-6.7.7*
Patch Release
CR-4939
PR-7619
CR-4866
CR-4895
Working Assumptions / Dependencies
Implementing Option 4 - 4FSK solution requires,
New RNI version implemented via CB.7.0
New RNI version also needs new NCS version implemented to replace NMS
Updated Firmware on Comms Hus to support 4FSK
Key Question
What is the current TPS limitation on RNI?
TBC –Further RNI S&0
Undefined ROM
Phase 2
CB-7.n
CB-7.n
CB-7.n
CB-7.n
CB-7.n
CB-7.n
CB-7.n
CB-7.n
CB-7.n
Additional S&O RNI development sprints
IA (above) Includes any further RNI S&0
CR-4939

## Slide 6
CSP.N Scaling & Optimisation Solution Options: Arqiva proposed a number of solution options as an output from Phase 1 with a Preliminary Assessment being created for each option. All options were reviewed and were then either progressed to Impact Assessment as a Phase 2 deliverable or put in a bucket of solutions for future consideration if required.
Option | Description | Action (and status)
1 | Increase RF Channels: New Channel Plan (Bulk Messaging Channels to 12 per TK) | Contracted for Delivery: FIA Completed (CR4866). Development underway. Release September.
2 | Increase Message Queue depth per TK Channel | Parked: No current activity. Option 7 achieves the same outcome but is a better solution.
3 | Message Compression | Parked: No current activity. Complex and solution not favoured.
4 | Modulation Rate Increases to 4FSK | Progressing: FIA in progress (CR4939). FIA on hold as has dependency on RNI FIA. Now due 30 Nov.
5 | Timeslot / Packet Size Redesign | Parked: No current activity. No cost provided. Arqiva and SENSUS not recommending.
6 | Network Optimisation Activities | Parked but for later consideration : No current activity. Needs breakdown by Arqiva. Revisit once priority actions complete.
7 | Increased levels of Arqiva Scheduling | Consider: Outcome dependant on SRW conversation
8 | Deploying additional RF Spectrum | Parked: ROM is for acquisition of spectrum only. Costly and needs Options 1 and 11 before IA possible.
9 | Other CSPN solution Improvements | Parked but for later consideration : No current activity. Needs breakdown by Arqiva. Revisit once priority actions complete.
10 | Scaling Bundled Response | Parked: No current activity.
11 | E2E CSP.N Solution capacity to support RAN increases (option 1) | Progressing: FIA in progress (CR4895). Due September.
N/A | RNI Scale Testing | Contracted for Delivery: (PR-7619). Due July.

## Slide 7: Proposal - Scheduled Read Window (SRW) Trial
  Placeholder Slide
  Content - Trial proposal prepared for discussion with customers
  Placeholder slides expected to be replaced no later than 24hrs ahead of TABASC in agreement with TABASC Chair, Julian Hughes.

## Slide 8: Customer Engagement Plan Proposal 2023*
*to be iterated in line with maturation of programme plan and any alteration to Arqiva’s stated timelines.
Date | Forum | Purpose
25/4 | SEC Panel | As part of a Continuity of Service update – DCC outlined the high-level approach for S&O: the finalisation of a Strategic Outline Case that will be presented to SEC Panel and the discussion of a Scheduled Read Window trial as part of S&O activity
1/6 | TABASC | Progress update on S&O project plan including anticipated Arqiva response and customer engagement timelines Discussion of the Scheduled Read Window trial
8/6 | SMDG | Progress update on S&O project plan including anticipated Arqiva response and customer engagement timelines Feedback from the discussion of the Scheduled Read Window trial at TABASC
13/6 | OPSG | Progress update on S&O project plan including anticipated Arqiva and customer engagement timelines Discussion of the Scheduled Read Window trial for Approval
26/6 | SEC Panel | Outline the Strategic Outline Case and anticipated Arqiva response and customer engagement timelines
TBC (Aug/Sep) | TABASC | Return to discuss Scheduled Read Window trial results to determine next steps
TBC (Aug/Sep) | OPSG | Return to discuss Scheduled Read Window trial results to determine next steps

## Slide 9: Customer Engagement Plan Proposal 2023*
*to be iterated in line with maturation of programme plan and any alteration to Arqiva’s stated timelines.
Date | Forum | Purpose
7/9 | TABASC | Update on the validation of the RNI Scale Testing Complete and Risk Zones activity (set for completion 30/07)
5/10 | TABASC | Update on the delivery of Option 1 - the New Channel Plan (set for completion 20/09) Update on Option 11 - RNI Full Impact Assessment (set for completion on 14/9)
7/12 | TABASC | Update on the deployment of Option 1 - the New Channel Plan (set for completion 31/10)
Jan 2024 | TABASC | Update on Option 4 - 4FSK Full Impact Assessment (set for completion on 30/11)
TBC | SMDG | Further updates to SMDG throughout 2023 as appropriate
TBC | OPSG | Further updates to OPSG throughout 2023 as appropriate
TBC 2024 | SEC Panel | Update on Outline Business Case (submission set for Dec ‘23)
TBC 2024 | SEC Panel | Update on Full Business Case

## Slide 10: Thank you. Smart DCC